The following items are areas considered to be core concerns for the 2016–2021 institutional strategic objectives. The plan is to establish top to bottom alignment of the strategic objectives across all departments and throughout the organization.

Each area of the strategic plan, upon approval, will have the objectives and measurements conveyed to all BHU departments for inclusion in their departmental objectives for the 2016–2017 year. Each department will be responsible for identifying how it will align with the area objectives in order to complete the institutional goals. Each department will also identify the measurements used to show completion of the objectives. It is understood that the objectives will have differing effects on each department. However, every department contributes at some level to complete the objectives. In addition, some of the objectives apply to a longer term, such as 2, 3, or 5 years. The length of the objectives will be identified in the strategic objective document.

The President and the Office of Assessment and Institutional Research will evaluate each department’s initiatives for each area to confirm their objectives and measurements are appropriately aligned, measurable, and attainable. If needed, the department objectives will be revised to align with the strategic objective and the attainment targets.

Test Came Through !!

| Objective | Sub-Objective |  | Target Completion Date | Comments w/ Budget $ |
| --- | --- | --- | --- | --- |
| 1. Academic Programs and Services |  |  |  |  |
| A. Maintain Relevance | 1. Revise Current Programs and Services | a) Program Review – b) Curriculum Review c) OnLine Program | January – February 2016 February – April 2016, Then annually by Dept. February – June 2016, Long-term 2016–2021 | $234,565 Dean: a) Ongoing Dean: b) Revising the process c) Faculty: Begin Curriculum Review for Undergraduate Religious Studies Department January 2017, followed by Curriculum Review for Undergraduate Leadership/ Business Department January 2018. Curriculum Review for Graduate Department, both Religious Studies and Leadership Departments January 2019. Rotation should continue every three years to maintain quality material offered for all departments. d) Online program was restructured with a Dean of Online Learning. The current goal is to build all degree offering out in fully online format. |
|  | 2. Evaluate Market for Future Programs and Services | Technical: a) Nursing - 1yr LPN; 6mo Hosp. Tech.; RN b) Media Svcs. | Through 2016–2017 | Dean: Ongoing |
| B. Explore Collaborative Partnerships | 1. Ecclesiastical Bodies – Domestic and International | a)Develop White paper value proposition b) assess pre-packaged and customized options c) case-by-case agreements which add value to BHU. | a) June 2016 b) June –December 2016 c) 2016-2019 Long-term goals through 2021 | $103,795 Dean: Approval for certificate programs is underway. |
|  | 2. Educational Institutions with Program Linkage | a) Link with H.S. student Comm. Svc. Req’s. and practicums (Fulton Leadership Acad, M. Jackson HS b) Partner with key institutions (Argosy, Richmont, etc.) c) Survey denominations and churches to determine skill set needs | a) 2016-2018 b) 2016-2018 c) Initial: December 2016 Long-term: 2017–2021 | Faculty: a) In working with the Office of Student life and Recruitment, have specific professors available to attend High School Career Days meetings with Recruitment teams introducing BHU to high school graduates. b) Target and identify specific churches to outreach and contact with BHU representatives, introducing student life opportunities to potential “Adult Students” interested in returning to school from first careers c) Aggressively seek terminal degreed professors to be hired full-time. Development Opportunities – Establish financial line-item to support professors attending ongoing training opportunities. Goal: spring 2017. |
| C. Academic excellence | 1. Hiring quality fulltime faculty 2. Providing faculty and department chair development opportunities | a) Ongoing efforts to hire quality faculty - 2 by Spring 2016, 2-3 more by Fall 2017 b) Develop and implement faculty/chairs development programs | a) 2016-2017 b) 2016-2017 |  |
| 2. Facilities |  |  |  |  |
| A. Maintenance and Upgrades | 1. Classrooms | a) Upgrade learning environment décor and electronic capabilities b) Build-out model classroom and fund drive to build-out all classrooms. | March 2016 July–December 2016, Then 2017–2018 | $250,000 Online: Would like to have some “Smart” classrooms with real-time video to provide virtual classrooms and to capture content for online courses. Technology: Working to create smart classrooms and will integrate into the 17-18 budget to address the 7 levels of the classroom and to build studio resources in classrooms specifically for Online instruction. Heavy studio style equipment that is expensive may not be needed in 2016 if we can utilize new technology effectively. Faculty: 1. Classrooms – including assessing on hand materials as well as latest updates. (These comments include all upgrades on current “in class” equipment). Prepare all classrooms with latest high tech equipment and materials available for use by professors in classroom instruction. Establish a DVD library with latest teaching materials to be used by professors. Goal: 2018. |
|  | 2. Faculty Offices | Redesign large room to contain 6-8 assigned and virtual office cubes. | June 2017 | $250,000 Draft designs submitted to P. Karanja @ March 15. Administration: The new design is being budgeted for 17-18. |
|  | 3. Library | a) Re-utilization project b) Fund drives to support e-brary expansion. | 2015 – 2016 2016 –2018 | $187,265 Online: Expand the data sources for online learning resources. Technology: Looking into expanding to include ATLA for the advanced degrees and satisfy the needs of a potential department of defense Memorandum of Understanding. |
|  | 4. General facilities | Plan section-by-section upgrades to BHU physical plant. | Plan complete by March 2017 Physical upgrades by June 2021 | $60,000 Administration: extensive facilities upgrades for 2017 are being added to 17-18 budget. Student life: Upgrades on campus and student housing began September 2016 |
|  | 5. Grounds | Re-vitalization and beautification project | August 2015 – August 2017 | $121,820 Student Life/facility: Continuing grounds re-vitalization October 2016 |
| B. New Facilities | 1. Model classroom | See 2.A.1.b. above | December 2016 | Student Life/Facility: Will implement spring 2017 |
|  | 2. A/V Studio | Evaluate potential for studio to use in curriculum development, marketing, and a potential media program | March 2017 | Technology: Studio is being designed specifically for Marketing efforts. This studio will use mobile devises and apps to lower the cost of constructions. New studio should be complete by mid 2017 and is being added to the 17-18 budget. Student Life/facility: Continuing evaluation. |
| 3. System & Process Efficiencies |  |  |  | $145,000 |
| A. Systems – What we have, what we need, and what are the gaps? | Review Internal flows and process including enrollment management plan, internal admissions/registrar document work flow, financial aid/student account receivables and advising plan. | Assess strengths and weaknesses of existing dbase systems. Use recommendations from online, enrollment/retention committee and Finance/technology committees to resolve issues and increase internal system efficiencies | Initial by June 2016, Annually: 2016–2021 | Reviewing the current student information system to determine the direction of current systems and processes. |
| B. Processes – What works well, what needs modification, what needs to be deleted. |  | Assess the existing processes and procedures for improvements in effectiveness. | Initial by December 2016, Annually: 2016–2021 |  |
| BHU is committed to continuous improvement of institutional effectiveness by identifying and incorporating best practices in each service area. |  |  |  |  |
| 4. Resource Utilization |  |  |  |  |
| A. Human Resources – Alignment (Reduce breadth and increase depth) |  | Executive level – review H.R. alignment for current and future needs (related work functions) | June 2016 | We will evaluate the overall size and scope of the HR office to match the University’s current needs. The office has evolved into a more active role due to the growth and needs of personnel. |
| B. Human Resources – Development (Improve skill sets) |  | Dean & Director Level – a) Classify work function/position descriptions and salary ranges b) develop skill sets of employees | a) August 30, 2016 b) Sept. 1, 2016 –2021 | a) All departments to take initiative to develop the skill sets of their staff. The Financial Aid Office will be undergoing 20 hours of free online training with the DOE, they will also be attending the DOE conference in Atlanta from 11/29-12/02. Administration: New HR personnel training efforts are underway. The University is also looking to add the assistance of an outsourced HR company for specific needs. Registrar: Provide Registrar office training in reporting, FERPA, Improve transcript process, streamline registration / late registration process. |
| C. Faculty – Acquisition and Development |  | Dean and Director Level – a) Develop a clear plan for acquiring more terminal degrees in each department b) develop a clear development plan for all faculty. c) execute approved plans with annual reviews | a) Sept 2015 – June 2016 b) Sept 2015 – June 2016 c) July 1, 2016 – 2021 | $27,540 Online: Would like to hire and develop a cadre of top-notch online instructors who will engage students in online learning. (Ongoing, but by 2018 we would like to have firm faculty list of quality online instructors.) Faculty: Considering points A & B should be handled beyond our department, take time to seriously evaluate all current full-time and adjunct professors. Promote those adjunct professors who have shown effective skill-sets in teaching to be promoted to full-time status. Develop a significant list of doctoral professors available to be hired with the university. This would be ongoing, but hope to reach full status by Spring 2018. |
| D. Material Resources – reduce variables and surplus supplies | 1. Identify materials management process 2. Identify materials management coordinator | Dean and Director Level – a) Identify materials needed for efficient processes. b) Standardize equipment and materials to reduce carry costs of materials. c) evaluate annually | a) Jan 2016 – June 2016 b) July 2016 – June 2017 c) May-June 2016 – 2021 | $20,000 Administration: A technology review is underway to evaluate computers, printers/copiers, phone systems, software, project management tools, general office supplies to determine If each department is being serviced and provided the recourses needed to succeed. This review should be over by the 1st quarter of 2017 and implementation should be complete by 3rd quarter of 2017. |
| 5. University Image & Recognition |  |  |  |  |
| A. Facilities – physical improvement: attractive and inviting | Create a University “creative lab” specifically to boost University Image and recognition with a combination of internal and external focus. | See “2. Facilities” above. | March 2016 – 2021 Technology Review started 2nd qtr - 2017 | Technology review is underway and should be complete by the 1st quarter of 2017. After needs are determined, a detailed project plan will be disbursed that includes training so we can maximize tools efficiently. |
| B. Web site – Regularly evaluate BHU’s web site for current, accurate, branded data in the following areas. | Create an industry competitive website that is interactive with our constituency including students, staff, faculty, donors, board members, alumni and the community. | 1. User friendly – users can find the information needed with ease. 2. Sensible navigation – Information is accessed through a minimal number of steps. 3. Current and easily digestible information – Review and insure BHU information is easily understood and acted upon. 4. Clear communication channels and contact information – users can easily contact the right department or individual. | Bi-annually – 2021 Bi-annually – 2021 Bi-annually – 2021 Bi-annually – 2021 | $145,000 Preliminary diagnosis indicates that a new design is needed. The current site is nearly 5 years old and a redesign is needed almost every 2-3 years. The technology review will be looking at the current set up that is tied to our student management system and will be used to gauge whether our site should be independent or not. This review should be done by end of 1st quarter 2017. |
| C. Public Relations / Marketing – Tell the BHU story | Increase BHU market presence by focusing on social media engagement, specific print collateral, videos, demographic specific email marketing, brand management, and the BHU app. | Evaluate and construct the messages that convey a real and relevant story which differentiates BHU from its competitors. | Bi-annually – 2021 | $250,000 |
| D. Centennial Celebration | City-wide recognition of BHU’s centennial. | a) Develop plans b) Implement plans | March – July 2016 August 2016 – July 2018 | $500,000 |
| 6. Centennial Initiatives |  |  |  |  |
| A. Centennial Celebration (July 2018) |  | Develop plans for 2018 celebrations | August 2016 (Rollout at Team Summit) | See 6.D above |
| B. Debt Retirement Fund Drive |  | Silent Drive $ | 2016–2018 Extension: 2019–2021 |  |
| C. Endowment Fund Drive |  | Open Drive $ | 2016–2021 | $1,860,000 |
| D. Regional Accreditation | Evaluate the future viability of regional accreditation. | a) Align ABHE, TRACS and SACS standards b) Complete gap analysis c) Evaluate level of effort and budget costs d) Devise a draft implementation plan. e) Cabinet and Board Presentation for approval (revise as needed) f) Execute Implement Plan | a) March – June 2016 b) July 2016 c) July – August 2016 d) August – October 2016 e) October 2016 – March 2017 f) March 2017 – 2018 | $ 93,000 |
| 7. BHU 5 Year Accreditation Review | Set objectives for TRACS Review | a) Conduct departmental reviews and develop response package b) Prepare for TRACS Team Visit. | a) March – Nov. 2016 b) November 2016 – January 2017 |  |
| 8. Development / Advancement |  |  |  |  |
| A. General Giving / Donations | Private giving helps ensure Beulah Heights University’s excellence in higher education. Private gifts allow the University to fund programs, ministries, scholarships, fellowships, professorships, campus renovations, and new facilities. | - Raise annual giving to $300,000 and retire all debt - Engage at least 5 grants per year (federal and private) | a) July 2018 | The University has refinanced all loans in preparation of retiring all debts. The sale of undeveloped real estate will help the University get to 50% of the goal by the end of 2016. The University will look to add advancement personnel or an outsourced firm to manage all campaign solicitations on a yearly basis to aggressively pursue development and advancement opportunities. The University’s new Title III status with the DOE will also allow us to aggressively pursue federal grants on a yearly basis. We have identified a professor that will be charged with grant writing specifically. |
| B. Funding: Grants, Endowments, Bequeaths, Beneficiaries, etc. | Title III, Foundations, Corporations, Ministry Initiatives, Churches, and Individuals. | Design and implement a development campaign w/ ongoing plan objectives. | Phase 1: 2016–2017 Phase 2: 2018-2021 | $150,000 |
| C. Material and Library Resources |  | See 2.A.3.b. a) Identify resource needs b) initiate a fund drives to secure needed resources (e.g. e-brary, digital access, etc. | a) March – July 2016 b) 2016–2021 | $40,000 Addition of ATLAS to Library Services |
| D. Technology Initiative |  | See 2.B.1. Build on fund drive initiative to continually acquire new technologies and improve usage models institution-wide. | Phase 1: 2016–2017 Phase 2: 2018-2021 | Administration: A technology review is underway to evaluate computers, printers/copiers, phone systems, software, project management tools, general office supplies to determine If each department is being serviced and provided the recourses needed to succeed. This review should be over by the 1st quarter of 2017 and implementation should be complete by 3rd quarter of 2017. |
| E. Partnerships with service providers |  | Leverage BHU value proposition into added monetary, human, and material resources through co-marketing, directed advertising, etc. | Phase 1: 2016–2017 Phase 2: 2018-2021 | $60,000 Development of FWS for local Community Center’s Career Services Dept., which will allow us to provide current students with a Career Services resource. |
| 9. Enrollment Growth – Domestic, International, and OnLine Students |  |  |  |  |
| A. Degree Seeking (Traditional and Adult Degree Completion) |  | 1. Define a clear decision process and the criteria for proving in new programs and partnerships. | March – July 2016 | Online: ACC and Cabinet will approve the mode for initial launch of new program offerings. |
|  |  | 2. Evaluate migration to 8-week terms for all courses. | March 2016 – February 2017 | Online: In Online this is underway and will be the standard starting Fall 2016. – Halted June 2016 |
|  |  | 3. Evaluate the long-term direction for the OnLine Program and Recommend to AAC and BHU Cabinet | March – July 2016 | Online: See committee report and recommendation. Dr. Hardgrove named Dean of Online and is moving forward on the roadmap for Online / Distance Learning. August 2016 Dean transitioned to Dr. Dennis Malone. Evaluation is underway for a new multilingual, multi-modal, single enrollment platform engaging both synchronous and asynchronous modes in a single course. |
| B. Non-degree seeking |  | 1. Continuing Education – Evaluate the potential (5-6 initial courses) and recommend to AAC, Cabinet, and President. | March – July 2016 | New ESL program is a new target group with high potential. |
|  |  | 2. Certificate – Evaluate the potential and recommend to AAC, Cabinet, and President. | March – July 2016 |  |
|  |  | 3. Free Courses / DVD Sales – Evaluate the potential and recommend to AAC, Cabinet, and President. | March – July 2016 |  |
| 10. Success Paradigm |  |  |  |  |
| A. Actions of Success |  | 1. “Coaching Success” Initiative | Graduation rate: ≥ 50% by May 2017 ≥ 60% by May 2018 ≥ 70% by May 2019 ≥ 75% by May 2020 ≥ 80% by May 2021 |  |
|  |  | 2. Professionalism | 2016–2021 |  |
| B. Talk of Success |  | Forward Thinking | 2016–2021 |  |
| C. Look of Success |  | Plan for 1st Impressions | 2016–2021 |  |