## Sheet1
Completion Date | Intervention | Person Responsible | Level of intervention | Evaluation-Effective, Efficient, Adequate, Appropriate
2011-05-15 | Develop parish nurse program | Public health nurse | Primary, Community | Was parish nurse hired and trained?
2011-05-15 | Contact all churches for support-schedule meeting | Public health nurse | Primary, Secondary, Individual, Family | Did all churches respond, attend a meeting?
2011-05-31 | Provide education to community on obesity-office, home visits | School Nurse, Parish Nurse, Public health nurse | Primary, Community | Is the parish nurselay teachers holding classes, attendance ?
2011-06-15 | Schedule Lay teacher training- 3 lay teachers | School Nurse, Parish Nurse, Public health nurse | Primary, Community | Is the parish nurse training 3 teachers?
2011-05-31 | Newspaper articles-once a week for 6 weeks | Parish Nurse | Primary, Community | Did the parish nurse develop article and submit?
2011-05-31 | Hold classes at library regarding obesity- 2 classes per week | Parish Nurse, Lay Teachers | Primary, Community | Did the parish nurse develop article and submit?
2011-05-31 | Mail brochures to all residents | Parish Nurse, Lay Teachers | Primary, Community | Did residents receive brochures, understand, call to schedule class?
2011-06-30 | Develop classes through churches-nutrition, exercise,healthy lifestyle | Parish Nurse | Primary, Community | Is the parish nurse fulfilling the duties-lay teachers and classes?
2011-06-30 | Provide nursing care to community | Parish Nurse | Primary, Secondary, Individual, Family | Is the nurse scheduling office and home visits-documenting?
2011-07-15 | Increase exercise to 30 minutes / day | Parish Nurse, Lay Teachers | Primary, Secondary, Individual, Family | How many residents are attending exercise/walking on their own?
2011-07-15 | Develop Structured exercise programs-4 new programs | Parish Nurse, Lay Teachers | Primary, Secondary, Individual, Family | How many programs developed with teachers, participants?
2011-07-15 | Organize water aerobices at pool-once weekly | Parish Nurse, Lay Teachers | Primary, Secondary, Individual, Family | How many residents are attending aerobics/swimming on their own?
2011-07-15 | Walking groups at school track and state park, 5K | Parish Nurse, Lay Teachers, School Nurse | Primary, Secondary, Individual, Family | How many residents are attending groups or walking, or 5K?