## Sheet1
Parts Manager - Greg Scott
Asst Parts Manager - Mohammed Cheikh
Fixed Operation Manager - Dave Verboom
| Specific Action/Step | Necessary Resources? | Who is Accountable? | Expected Result? | Expected Completion Date
| Set up monthly review on Inventory Movement Report | DMS, Google Calendar | Me | Report reviewed monthly, status of progress tracked | Ongoing, set up completed
| Identify technical obsolescence parts that should be sold | DMS | Greg Scott | Find all 13+ month parts | 2022-01-15
| List relevant parts for resale on Kijiji | PC | Greg Scott | List all parts on our Kijiji account | 2022-02-01
| Put all old tonneau covers onto spreadsheet | Excel, DMS | Mohammed Cheikh | All old tonneaus tracked on the sheet | 2022-02-01
| Find used Tacomas, Tundras to use tonneaus on (review inventory as it comes in) | DMS, IMS | Nicholas Gibson | Check each truck as it comes in to see if we can accessorize it | Ongoing
| Talk to wholesale customer, see if they have interest in buying some old accessories at a discount | none | Dave Verboom | Hopefully sell some old accessories to wholesale customer, recoup some $ | 2022-03-01
| Identify potential obsolescence parts | DMS | Mohammed Cheikh | Understand what will become technical obsolescence soon | 2022-02-01
| Create a sales plan for potential obsolescence parts | DMS | Mohammed Cheikh | Sell some parts, discount some of these parts to ensure they are sold | 2022-02-15
| Sell online (Kijiji, etc.) all remaining potential obsolescence parts before they turn into technical obsolescence | DMS, online sales tools | Greg Scott | Anything that can't be sold normally will be cleared out before becoming technical obsolescence | 1 Mar 2022, Ongoing
| Set up regular review of Inventory Movement Report | DMS | Greg Scott | Parts manager to review report monthly, review with fixed ops manager in monthly meeting | Ongoing
| Review SOP process | DMS, standard operating procedures in Google Drive | Greg Scott, Nicholas Gibson | Ensure our SOP system is moving out all parts in reasonable timeframe (1-2 months) regardless of customer pay, nothing should age into obsolescence | 2022-02-15