Bickford Ford Parts Department

SMART action plan to incorporate the Parts Special Order Request Process:

Specific:

Develop and implement the Parts Special Order Request Process in the parts department

Reduce returned special order shop parts by 40%

Increase shop parts sales by improving customer service and car repair notifications and tracking

Measurable:

Track the number of returned special order shop parts before and after the implementation of the new process

Monitor shop parts sales before and after the implementation of the new process

Monitor the number of special order parts requests and their turnaround time

Achievable:

Review the current special order parts process to identify areas for improvement

Allocate sufficient resources to implement the new process, including staffing and training

Relevant:

The new Parts Special Order Request Process will help improve customer service and increase shop parts sales

The reduction in returned special order shop parts will help to reduce waste and improve efficiency

Time-bound:

Start date: April 2

Goal date: October 2

Action Steps:

Review the current special order parts process and identify areas for improvement. (April 2 - April 16)

Develop the new Parts Special Order Request Process and document it. (April 17 - May 14)

Train staff on the new process. (May 15 - June 15)

Implement the new Parts Special Order Request Process. (June 16 - July 15)

Monitor the number of special order parts requests and their turnaround time. (July 16 - September 30)

Monitor the number of returned special order shop parts and shop parts sales. (July 16 - September 30)

Evaluate the effectiveness of the new process and make any necessary adjustments. (October 1 - October 2) notifications and tracking.