| Name | Dario Albarron | Class # | N430 |
| --- | --- | --- | --- |
| Dealership | Bridgewater KIA | Date | 6/6/2024 |

| Current Situation or Challenge to be Addressed: | We want to increase our used vehicle turn rate resulting in 20-25% increase in used vehicle sales. |  |  |
| --- | --- | --- | --- |
| Current Performance Level (include specific measure): | We are currently selling an average of 77 per month. From January 1st through May 31'st we have sold 386 units for 1,519,277 for 3936 per copy |  |  |
| Goal (what do you want to achieve?) | Our goal is to sell 100 used vehicles per month while keeping gross at 3500 p/c or better. |  |  |
| Goal Performance Level (include specific measure) | Had we sold 100 per month for the first 5 months we would have 500 used cars sold for 1,750,000 ytd @ 3500 p/c for a total gross increase of $230,723 or $46000 per month. |  |  |
| Goal Start Date: | 6/1/2024 | Goal End Date: | 8/31/2024 |
| First Check-in Date: | 6/15/2024 | Performance Objective: | Adjust pricing daily to maximize turn rate |
| Second Check-in Date: | 6/30/2024 | Performance Objective: | Analyze used sales and make adjustment to pricing methodology if needed to get to 100 |
| Third Check-in Date: | 7/31/2024 | Performance Objective: | Increase purchasing to allow for maintenance of 100 used per month |
| Fourth Check-in Date: | 8/31/2024 | Performance Objective: | anylize inventory greater than 45 days old, reduce prices and plan an exit for these vehicles at 60 days if they do not sell |
| How does your goal align with the dealers’ vision? | The dealers vision is to add 3 more dealerships before end of year. As inventory normalizes dealerships are becoming available, there are plenty of under performing stores available right now. We need a rock solid plan to offset losses with used cars sales from day 1, we cannot aford to add a store that is currently losing 180,000 per month without a plan to offset thst loss. We don’t need to be profitable the first couple months as we transition but we need to limit the loses |  |  |
| What are the potential benefits of achieving your goal? | We will increase the monthly bottom line at this location by 46,000 per month, while fine tuning our process so we can replicate it at our next location |  |  |
| What are the potential consequences if you don’t achieve your goal? | We would continue to average 77 used cars per month, but would not have a viable plan to offset potential losses at the location we are negotiating on now. |  |  |
| Why is the goal important to you? | When we add a second store, I will become the GM for both stores. This is a huge step in my career. The owners have had enough faith in me to sponsor my NADA training and I am prepared for any future challenges. |  |  |
| Potential Obstacles | Trouble sourcing the right type of inventory to move the needle and increase units. |  |  |
| Potential Solutions | .We are adding a KBB buying center that should allow us to purchase an additional 25-30 units per month hoping that 15 or so will be retail pieces we will be more aggressive with the off lease vehicles to ensure we have a constant pipeline of quality certified inventory available, |  |  |
| BOTTOM LINE! Financial Impact of Achieving Your Goal (expressed in dollars) | The financial impact of increasing sales is 46,000 per month for annual revenue increase of 552,000 plus whatever we make on the additional wholesale units after covering the expense of the KBB buying center |  |  |

What specific actions or steps will you take to accomplish your goal?  What will you do differently or improve? For each, be sure to include necessary resources, who is accountable, the measurable result, and dates.

| Specific action/step | Necessary resource(s) | Accountable person(s) | Expected result | Start, End, & CHeckpoint Dates |
| --- | --- | --- | --- | --- |
| Adjust target pricing to 98%-102% | Vauto | Used car manager | Increase used car floor traffic | 6/6 through 8/31 checking on 7/1 and 7/15 and 8/15 |
| Add kbb buying center | KBB buying center | BDC manager | Ability to purchase 25-30 units off the street for both retail sale and wholesale profit | Start asap check at end of June, mid July, July end, mid August and the end of August |
| Move more units through used car prep | Service technicians to work on the cars | Service manager | He has told me it will not be aproblem to prep an additional 25 used cars each month | Monitor time to prep used cars daily with a 3 days to front line target in mind |
| Prepare for additional lead traffic | Staffing for bdc | BDC manager | Increase in used car leads as well as selling us carleads | Monitor weekly to make sure leads are being responded to timely and apporpriately |
| F&I coverage | When we get to 225 or more units regularly we need 3 Finance manager | Finance director is resposible for staffing | As we grow in units we will grow in staff, sales, bdc, finance | When we get to 225 unitsregularly |
| Track sales and gross | Dms reports | General Manager | To see the increase in units and gross | I will track this daily but deep dive review it every Monday |
| Share our vision with staff | Kick off meeting | General manager | Some salespeople will push back at lower profit margins, but they will see the big picture more sales, more gross, more volume bonus opportunities. | Kick off meeting on 6/8 to launch of program with a check in meeting on the 17th to review process and share our progress |

As you work toward your goal, it’s important to have interim check points with specific, measurable objectives so your team can hold themselves accountable. If everyone knows the goal and objectives, you don’t have to spend your valuable time micromanaging.

Once you’ve accomplished your goal, added or adjusted policies, procedures, and behaviors, now what? How will you ensure you and your staff do not fall back into the previous habits that produced poor results? Be specific.

Continuous monitoring, daily pricing updates. The GM inspecting what he is expecting regularly and holding everyone accountable.

Describe any planning or implementation meetings conducted as part of development of your plan.

I have met with owners and used car manager ti discuss this plan on two separate meetings. The first meeting I laid out my plan, outlined the process and what resources would be needed. In the second meeting I answered their questions and addressed any concerns. They were all supportive and optimistic of this growth opportunity

| Sponsor Signature: |  |
| --- | --- |