| Name | JOHN LEAL | Class # | N430 |
| --- | --- | --- | --- |
| Dealership | TEAM NISSAN | Date | 2/9/2024 |

| Current Situation or Challenge to be Addressed: | CUTTING DOWN RECON DAY TO FRONT LINE |  |  |
| --- | --- | --- | --- |
| Current Performance Level (include specific measure): | CURRENTLY 10-12 DAYS |  |  |
| Goal (what do you want to achieve?) | 5-7 DAYS |  |  |
| Goal Performance Level (include specific measure) | GET MY USED CARS TO THE FRONT LINE WITH IN 7 DAYS TO COMPETE IN PRICE TO MARKET AND INCREASE TURNS PER YEAR FROM 7 T0 10 WITH NEW PROCESS |  |  |
| Goal Start Date: | 3/1/2024 | Goal End Date: | 5/31/2024 |
| First Check-in Date: | 3/18/2024 | Performance Objective: | TO SEE A CHANGE IN DAYS TO FRONT LINE |
| Second Check-in Date: | 3/1/2024 | Performance Objective: | CHECK TO NAKE SURE THE NEW PROCESS IN WORKING AND DAYS TO FRONT LINE ARE IMPROVING |
| Third Check-in Date: | 3/31/2024 | Performance Objective: | RUN TURN EVALUATION TO CHECK PERFORMACE |
| Fourth Check-in Date: | 4/15/2024 | Performance Objective: | MAKE ANY CHANGES TO POLICY IF NEEDED |
| How does your goal align with the dealers’ vision? | ALWAYS CHANGE TO IMPROVE EACH DEPARTMENT |  |  |
| What are the potential benefits of achieving your goal? | MORE GROSS ,MORE SALES ,MORE UNITS SOLD |  |  |
| What are the potential consequences if you don’t achieve your goal? | MISSING THE PRIME WINDOW FOR COST TO MARKET PRICING AND LOSS GROSS DUE TO LOSS TURNS ON INVENTORY |  |  |
| Why is the goal important to you? | INCREASE BOTTOM LINE GROSS PROFIT |  |  |
| Potential Obstacles | PARTS BACK ORDER, SPECIAL ORDER PARTS, RECALLS OR TO MUCH RECON NEEED TO FIT PRICING MODLE |  |  |
| Potential Solutions | WHOLESALE THE CARS THAT DON’T FIT PRICING MODEL FASTER |  |  |
| BOTTOM LINE! Financial Impact of Achieving Your Goal (expressed in dollars) | 12050 GROI $144,000 YEARLY |  |  |

What specific actions or steps will you take to accomplish your goal?  What will you do differently or improve? For each, be sure to include necessary resources, who is accountable, the measurable result, and dates.

| Specific action/step | Necessary resource(s) | Accountable person(s) | Expected result | Start, End, & CHeckpoint Dates |
| --- | --- | --- | --- | --- |
| CREATE ECXEL SPREED SHEET | EXCEL | USED CAR MANAGER | ORGANIZE INVRNTORY | 03/01/2024 03/10/2024 END |
| EXCEL INPUT CELLS | EXCEL | USED CAR MANAGER SERVICE MANAGER | INPUT STATUS OF RECON VEHICLES | 03/01/2024 05/001/2024 END |
| MEET WEEKLY ON SPREED SHEET INPUT | EXCEL | USED CAR MANAGER. SERVICE MANAGER GENERAL MANAGER | IMPROVE DAY TO FRONTY LINE | 03/01/2024 03/31/2024 |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |

As you work toward your goal, it’s important to have interim check points with specific, measurable objectives so your team can hold themselves accountable. If everyone knows the goal and objectives, you don’t have to spend your valuable time micromanaging.

Once you’ve accomplished your goal, added or adjusted policies, procedures, and behaviors, now what? How will you ensure you and your staff do not fall back into the previous habits that produced poor results? Be specific.

WEEKLY MEETING ADDING TO STORE POLICY

Describe any planning or implementation meetings conducted as part of development of your plan.

WEEKLY MEETINGS

| Sponsor Signature: |  |
| --- | --- |