| Name | Ernest Johnson | Class # | N432 |
| --- | --- | --- | --- |
| Dealership | Cavender Toyota | Date | 3/7/2024 |

| Current Situation or Challenge to be Addressed: | The internet lead closing ratio performance. |  |  |
| --- | --- | --- | --- |
| Current Performance Level (include specific measure): | Internet lead closing ratio average across the group is 10.8%. |  |  |
| Goal (what do you want to achieve?) | Increase internet lead closing ratio. |  |  |
| Goal Performance Level (include specific measure) | Increase internet lead closing ration from 10.8% to 12.3% |  |  |
| Goal Start Date: | 4/1/2024 | Goal End Date: | 9/30/2024 |
| First Check-in Date: | 5/1/2024 | Performance Objective: | 11.05% |
| Second Check-in Date: | 7/1/2024 | Performance Objective: | 11.55% |
| Third Check-in Date: | 9/1/2024 | Performance Objective: | 12.05% |
| Fourth Check-in Date: | 10/1/2024 | Performance Objective: | 12.3% |
| How does your goal align with the dealers’ vision? | Internet leads are an important component of our sales culture. It begins our end-to-end customer experience. |  |  |
| What are the potential benefits of achieving your goal? | The more exposure and presence our stores have digitally, we will ideally increase our opportunities in converting interest into appointment, and ultimately, into sold units. |  |  |
| What are the potential consequences if you don’t achieve your goal? | While less units sold is an obvious realization, there is a distinction to make. Poor leads need to also be vetted out so the store has an appropriate set of information to have an opportunity to successfully increase the average closing ratio.Missing oppertunities to upsell or even cross sell can ultimately impact the botton line. |  |  |
| Why is the goal important to you? | The majority of shoppers start their journey on the internet. We are know for all exceptional service and want to ensure all customers, even potential ones, recognize this value. |  |  |
| Potential Obstacles | Challenges identified include but not limited to: 1. Lack of understanding on the internet process and impact. 2. Employee turnover. 3.Learning curve for new hires. 4.Low inventory. 5.Technology is not able to handle dynamic customer needs. |  |  |
| Potential Solutions | Enterprise goals are shifting and intensifying. With today's acceleratied pace, agility and flexibility are essential. Focusing on operational training processes to ensure that new employees are able to adopt a new mindset when it comes to internet sales as well as ensure our technology can supprt customers needs. |  |  |
| BOTTOM LINE! Financial Impact of Achieving Your Goal (expressed in dollars) | Total additonal gross for Dealarship Group $314,215.00 |  |  |

What specific actions or steps will you take to accomplish your goal?  What will you do differently or improve? For each, be sure to include necessary resources, who is accountable, the measurable result, and dates.

| Specific action/step | Necessary resource(s) | Accountable person(s) | Expected result | Start, End, & CHeckpoint Dates |
| --- | --- | --- | --- | --- |
| Physically visit stores to asses and for the implementation of training processes | Computer | Variable Ops Trainer | A faster learning curve and buy in from understanding the process and its importance | Monthly visit April 2024 to Sept 2024 |
| Virtual meetings with Internet Managers and Internet Sales | Computer, phone, and teams meeting | Variable Ops Trainer Sales Managers Internet Managers Internet Sales | To quickly adjust or shift if need be while still woriking our current process as group | As needed for any pivot or changes that might be necessary |
| Send mid-month progress checks to all stores | CRM, E-Leads, CDK, and email | Variable Ops Trainer | For each store to know pace and make the adjustments to hit or raise its objective | The 16th of every month. April 2024 to Sept 2024 |
| Hold month end recap meetings | CRM, E-Leads, CDk, and email | Variable Ops Trainer | Intent to gather feedback amongst stores for growth oppertunities | The 4th of following new month.May 2024 to October 2024 |
| Continue to canvas for new technologies for us to potentially use | Internet, Nada Shows and Acadamy | Variable Ops Trainer | Find another tool that we can add in an effort to increase our lead engament | Continuously |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |

As you work toward your goal, it’s important to have interim check points with specific, measurable objectives so your team can hold themselves accountable. If everyone knows the goal and objectives, you don’t have to spend your valuable time micromanaging.

Once you’ve accomplished your goal, added or adjusted policies, procedures, and behaviors, now what? How will you ensure you and your staff do not fall back into the previous habits that produced poor results? Be specific.

All my specific actions, steps and checkpoints dates will be perpetual and a part of monthly duties.

Describe any planning or implementation meetings conducted as part of development of your plan.

I plan with three platform directors for the dates of visiting their stores located in 8 different cities.

| Sponsor Signature: |  |
| --- | --- |