| Name | Ron George | Class # | N432 |
| --- | --- | --- | --- |
| Dealership | Korum Ford 2/19/2024 | Date | 2/19/2024 |

| Current Situation or Challenge to be Addressed: | Used car department being unprofitable due to poor appraisal process and extended reconditioning time. Additionally pricing tactics, and side processes and personnel issues must be considered. |  |  |
| --- | --- | --- | --- |
| Current Performance Level (include specific measure): | Approximately 10% of the inventory remains "aged"at 90 days or more. Current front end gross is $800 below target and back end gross is $300 below target. Turns are at five per year and need to move up to eight. |  |  |
| Goal (what do you want to achieve?) | Resolve the aged issue favorably by effectively retailing vehicles via pricing, promotion and personnel starting the month of April 2024, |  |  |
| Goal Performance Level (include specific measure) | Providing a positive level of profitablity in the used car department. |  |  |
| Goal Start Date: | 2/1/2024 | Goal End Date: | Use Dropdown to enter a date. |
| First Check-in Date: | 5/1/2024 | Performance Objective: | Break even, no loss |
| Second Check-in Date: | 6/1/2024 | Performance Objective: | Profit |
| Third Check-in Date: | 7/1/2024 | Performance Objective: | Profit |
| Fourth Check-in Date: | 8/1/2024 | Performance Objective: | Profit |
| How does your goal align with the dealers’ vision? | 100% |  |  |
| What are the potential benefits of achieving your goal? | The obvious benefits are to stop losing a significant amount per month are immense, to be part of the process will be tremendously rewarding. |  |  |
| What are the potential consequences if you don’t achieve your goal? | The dealership will continue to lose money, potentially getting out of the used car business, cutting life time warranty's in an attempt to lower costs, reducing marketing, literally a market contraction. |  |  |
| Why is the goal important to you? | I have a personal investment in the success of the dealership, as he has sponsord me for the NADA school. John Hall is literally the first person to help me in forty years. |  |  |
| Potential Obstacles | Difficulty in acquisition of vehicles at desired costs. Current reconditioning costs exceed estimates, and our ability to recapture in retail prices. |  |  |
| Potential Solutions | Determine an agreed upon process with key managers, and execute consistently. |  |  |
| BOTTOM LINE! Financial Impact of Achieving Your Goal (expressed in dollars) | Overcome the 2023 calendar year net loss of $349,000 in the used vehicle department. Starting in April a profit of $50,000 per month for the remainder of the year would generate a net profit of $450,000 for the year. |  |  |

What specific actions or steps will you take to accomplish your goal?  What will you do differently or improve? For each, be sure to include necessary resources, who is accountable, the measurable result, and dates.

| Specific action/step | Necessary resource(s) | Accountable person(s) | Expected result | Start, End, & CHeckpoint Dates |
| --- | --- | --- | --- | --- |
| Reduce distance/range of competitive criteria to no more than 100 miles. | Agreement and participation | Sales managers General Sales managers Used car manager General manager | Reduction in available vehicles in competitive set. | 2/1/2024 Check daily |
| Remove series from competitive criteria. Model specific criteria, or 4 door versus hatch back etc. Use of Stockwave or similar software to prevent overspending due to market variance. | Trust in the process. Understanding that people will not drive 500 miles for a sedan, but within 50 miles would purchase the same model in either a hatchback or sedan. | Sales managers General Sales managers Used car manager General manager | Slight increase in available vehicles for competitive set. | Check daily |
| Switching market mode to Recent from Active. | Awareness | Sales managers General Sales managers Used car manager General manager | Will use historical data, as opposed to daily records for comparison giving a larger pool of data to work from. | Check daily |
| Review of all appraisals by senior manager | Discipline and time | General sales manager Used car manager General manager | Reduction of vehicles overpriced for the market, or using an incorrect competitive set. | Check daily |
| Adjustment of reconditiong costs and timleness. | Study of current system focusing on bottlenecks and potential opportunities. | General Sales Manager Used Car Manager Service Manager Reconditiong Manager | Expedited reconditiong at a lower expense | 3/1/2024 Checkpoint will be monthly |
| Creation of published reconditiong menu similar to what is in provision. Exceptions would need to be approved by the Reconditioning manager in writing. | Acceptance of a standardized pricing model. | Used car manager Service manager Reconditioning manager General Sales manager | Stream lined service with known reconditiong costs should limit reconditiong expense to what a customer is willing to pay. Keeping us within the market value | 4/1/2024 |
| Retailing Increase F&I production by $300 PVR | Additional training and dedication | Finance director Finance managers | Initial resistance to change Bigger than expected improvement | 4/1/2024 |

As you work toward your goal, it’s important to have interim check points with specific, measurable objectives so your team can hold themselves accountable. If everyone knows the goal and objectives, you don’t have to spend your valuable time micromanaging.

Once you’ve accomplished your goal, added or adjusted policies, procedures, and behaviors, now what? How will you ensure you and your staff do not fall back into the previous habits that produced poor results? Be specific.

Daily review of each trade appraisal by a supervising manager, (me) with immediate adjustments made to the front side of the deal. The philosophy going forward must be that we will not put the used car inventory in jeopardy by overpaying/overpricing the vehicles. We cannot "retail" our way out of a vehicle if no one ever sees it due to it beiing at the bottom of the SRP pile. We must do everything possible to move our vehicles to the top listing page.

Describe any planning or implementation meetings conducted as part of development of your plan.

Saturday mornings at 8:00 am with all Sales Managers and Senior Managers for the last several months discussing the potential advantages of Vauto. Additional training of Sales managers on a daily basis, and review of appraisals with our account rep.

| Sponsor Signature: |  |
| --- | --- |