Increase used vehicle sales volume and profitability by decreasing the time to lot from acquisition to retail ready and published on our website.

Time to lot / ready to retail from acquisition is currently 11 days on average

We want to speed the process by creating a sense of urgency around time to lot, in the acquisition logistics, the recon evaluation and repair, and the picturing and publishing retail information on our website

Our goal is 3 days on average

Goal start date is 4/1/24 – Goal End Date is 8/01/24

4 Check in dates, first of the month, beginning 5/1/24 to 8/1/24, Performance objective should be 9, 7, 5, and 3 on each first of the month respectively

Goal aligns with our vision of being a premier source of quality used vehicles for our community through fresh availability and fast turnover.   Also, increased profitability in selling fresh units.

By not achieving our goal we run the risk of inventory depreciation, cash baing tied up, and eventual large wholesale losses.  Also, used vehicle business may suffer if customers perceive we do not have fresh inventory when vehicle turn is low.

The used vehicle market is 4x larger than the new market and is not limited by factory and allocation constraints.  Used vehicles can also be more profitable at the sale transaction, and through the reconditioning process.  This source of business will also limit new vehicle sales dependence.

Potential obstacles may exist in the determination of proper recondition content, labor and parts availability, urgency among the team, technology challenges in pictures flowing to the website.

Potential Solutions will involve firstly a method to measure time to lot, then a standardized process around minimum levels of reconditioning needed.  Implementing a “good, better, best” approach in recon options from internal service can be instrumental here.  An analysis and consequent stocking of fast moving recon parts can help alleviate parts delays.  Again, a clearly established and communicated process designed around taking and posting of pictures will be helpful as well.

Financial Impact can be measured most simply in the lack of wholesale loss.  Last year, we experiences a $340k loss here, almost exclusively due to lack desired of inventory turn.  With the time to lot metric achieved we will be able to avoid these losses.

| Specific Action | Necessary Resource | Accountable Person | Expected Result | Start/End/Checkpoint Dates |
| --- | --- | --- | --- | --- |
| Written process and time goals of pictures and posting to website | Input from all involved in the process. - Vauto Inventory feeds properly set up | Used vehicle manager | Measureable process with accountability milestones | Start 4/1, weekly check in, complete by 4/10, in place by 4/15 |
| Evaluation of fast moving recon parts & stocking plan | Data from DMS - Accounting approval to purchase | Parts Manager | Less recon delays due to parts availability | Start 4/1, weekly check in, complete by 4/10, in place by 4/15 |
| Establish method to monitor time to lot | We will use Rapid Recon | Internal Service Manager | Ability to measure and communicate time to lot metrics | Start 4/1, weekly check in, implementation of software complete by 4/5, in place by 4/15, training complete by 4/19, useful information achieved by 5/3 |
| Internal service to provide "good/better/best" recon options to used vehicle manager | DMS/Update Promise service tool | IT Leader / Service manager / Internal service manager | Vehicles reconditioned to proper standard. Case by case by vehicle. Less vehicles getting kicked to Auction | Start 4/1, weekly check in, implementation of software changes, customizations complete by 4/19, in place by 5/3, training complete by 5/17, goal achieved by 6/1 |

Monitoring of Time to lot metri in a public setting, perhaps a daily update posted in internal reconditioning area, or on the sales board.  Continued focus and monitor of aging inventory, turn rates, and of wholesale p&l