| Name | James Hutchinson | Class # | N432 |
| --- | --- | --- | --- |
| Dealership | Pine Belt Chevrolet Buick | Date | 4/18/2024 |

| Current Situation or Challenge to be Addressed: | Social Media Merchandising by Salespeople |  |  |
| --- | --- | --- | --- |
| Current Performance Level (include specific measure): | Currently vehicles have few pictures and vague description , if any at all. |  |  |
| Goal (what do you want to achieve?) | I would like to have all employees that use social media for marketing themselves complete social media classes in their Center Of Learning training path. |  |  |
| Goal Performance Level (include specific measure) | Have all vehicles that are marketed have at least 7 pictures, unique description, and possibly even a short video clip of the exterior. |  |  |
| Goal Start Date: | 4/18/2024 | Goal End Date: | 6/22/2024 |
| First Check-in Date: | 4/18/2024 | Performance Objective: | Have half of staff listing vehicles with at least 7 pictures. |
| Second Check-in Date: | 5/17/2024 | Performance Objective: | Spot check and verify that we are giving a unique description of the vehicle. |
| Third Check-in Date: | 6/18/2024 | Performance Objective: | Have 360 videos incorporated into ads as well to show spin view. |
| Fourth Check-in Date: | 7/18/2024 | Performance Objective: | Ask for screenshots of messages to verify that they are responding in a timely matter, with a clear balanced message. |
| How does your goal align with the dealers’ vision? | It would allow all advertising performed by individuals to align with our online marketing campaigns and have crisp pictures, unique messaging, and value added to every form of social media marketing. |  |  |
| What are the potential benefits of achieving your goal? | Increased sales on social media, reaching untapped market, tapping into different demographics that we may not be reaching. |  |  |
| What are the potential consequences if you don’t achieve your goal? | No additional sales due to bland ads. |  |  |
| Why is the goal important to you? | I want to reach out and tap the market that we aren't currently selling to. |  |  |
| Potential Obstacles | Pushback from employees thinking its taking to much time. |  |  |
| Potential Solutions | Offer assistance by asking employees that aren't currently listing ads, or listing basic ads, to work with others that are having success listing the new way. |  |  |
| BOTTOM LINE! Financial Impact of Achieving Your Goal (expressed in dollars) | Sell minimum of 5 additional cars on social media by using advertising created by individuals at @ PVR of $4000 would possibly create an additional $20000 monthly. |  |  |

What specific actions or steps will you take to accomplish your goal?  What will you do differently or improve? For each, be sure to include necessary resources, who is accountable, the measurable result, and dates.

| Specific action/step | Necessary resource(s) | Accountable person(s) | Expected result | Start, End, & CHeckpoint Dates |
| --- | --- | --- | --- | --- |
| Online training | Global Connect, Dealer University Training | Salespersons | Learn how to market vehicles the correct way and gain the most clicks possible. | Start 05/18/2024, end 07/18/2024. C.P. 05/18/24, 06/18/2024, 07/18/2024 |
| Hold accountable for listings | Access to social media sites | Salespersons | Staff will be held accountable for not following new way of listing vehicles. | 04/18/2024 05/18/2024 |
| Coaching | Marketing Manager | Jennifer May | Verify that everyone has access to all materials and training available | 04/18/2024 06/18/2024 |
| Taking professional looking photo | Digital camera, training on uing correct lighting and editing, picture space | Jennifer May Salespersons | Crisper, cleaner, more professional looking pictures to increase clicks/views | 04/18/2024 05/18/2024 |
| Creating Unique Message | Chat GPT | Jennifer May | To be able to write a quick, unique description of each vehicle. | 04/18/2024 05/18/2024 |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |

As you work toward your goal, it’s important to have interim check points with specific, measurable objectives so your team can hold themselves accountable. If everyone knows the goal and objectives, you don’t have to spend your valuable time micromanaging.

Once you’ve accomplished your goal, added or adjusted policies, procedures, and behaviors, now what? How will you ensure you and your staff do not fall back into the previous habits that produced poor results? Be specific.

We will discuss and look at listings as an exercise weekly with the team during the sales meeting.

Describe any planning or implementation meetings conducted as part of development of your plan.

We will set aside 10-15 minutes of the sales meeting weekly to ensure everyone is listing ads properly.

| Sponsor Signature: |  |
| --- | --- |