| Name | Jessie Bryant | Class # | N432 |
| --- | --- | --- | --- |
| Dealership | Step One Kia Ft Walton beach | Date | 5/20/2024 |

| Current Situation or Challenge to be Addressed: | Video Response rate for internet leads below industry and dealership expectations |  |  |
| --- | --- | --- | --- |
| Current Performance Level (include specific measure): | 22% Video included |  |  |
| Goal (what do you want to achieve?) | Raise video response for internet leads to 75% to better serve customers that are beginning purchase journey online and build trust relationship |  |  |
| Goal Performance Level (include specific measure) | 75% |  |  |
| Goal Start Date: | 5/25/2024 | Goal End Date: | 9/30/2024 |
| First Check-in Date: | 6/30/2024 | Performance Objective: | 30% |
| Second Check-in Date: | 7/30/2024 | Performance Objective: | 45% |
| Third Check-in Date: | 8/30/2024 | Performance Objective: | 60% |
| Fourth Check-in Date: | 9/30/2024 | Performance Objective: | 75% |
| How does your goal align with the dealers’ vision? | Kia Ft Walton is located in a vacation hot spot. Most leads generated begin as internet leads. Dealer desires better engagement to convert more leads to appointments. Dealers goal is to build trust and establish relationships with consumer through video in order to achieve greater sales and CSI numbers with the OEM. |  |  |
| What are the potential benefits of achieving your goal? | Increased unit sales and profits. More educated consumer shopping base earlier in the process. |  |  |
| What are the potential consequences if you don’t achieve your goal? | Other dealers are becoming experts in this practice. Failure to respond quickly, and with great quality could lead to lost sales and profits. |  |  |
| Why is the goal important to you? | Giving the customer the best experience and ultimately capturing every prospect. We spend so many ad dollars to get the customer interested, we need to see a return. |  |  |
| Potential Obstacles | Old school mind-set. Fear of being on video or performance anxiety for staff. Laziness and covid culture of waiting for the customer to come to us. |  |  |
| Potential Solutions | Reward good behavior with spiffs for aligning with our vision. Create a culture of excitement around the process. |  |  |
| BOTTOM LINE! Financial Impact of Achieving Your Goal (expressed in dollars) | We should recognize an additional 26 sales per assuming the video helps up our close rate to the industry average. With our current all in PVR of $4168 all in, we should see an additional profit of $108368.00 |  |  |

What specific actions or steps will you take to accomplish your goal?  What will you do differently or improve? For each, be sure to include necessary resources, who is accountable, the measurable result, and dates.

| Specific action/step | Necessary resource(s) | Accountable person(s) | Expected result | Start, End, & CHeckpoint Dates |
| --- | --- | --- | --- | --- |
| Morning Meeting to inspect lead handling | Checklist Staff | General Sales Manager | Video response monitored and coached daily | 05/25 - No end |
| Training | Simple Step by step guide | BDC Lead/Sales Managers | All employees understand how to properly produce and send video response | 05/25 - Ongoing with new staff, etc. |
| Monthly check-ins | Checklist and comparable results | Varaible Ops Director, GSM, BDC and Sales Managers | Accountability and alignement to goal | 05/25 - 09/25 |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |

As you work toward your goal, it’s important to have interim check points with specific, measurable objectives so your team can hold themselves accountable. If everyone knows the goal and objectives, you don’t have to spend your valuable time micromanaging.

Once you’ve accomplished your goal, added or adjusted policies, procedures, and behaviors, now what? How will you ensure you and your staff do not fall back into the previous habits that produced poor results? Be specific.

This will become a part of our measureables during all sales meetings. We will also report the final numbers per sales person in a corporate meeting once per month. We will have a plan to put salesperspons on corrective action if they are not following the process and completing video responses for all leads.

Describe any planning or implementation meetings conducted as part of development of your plan.

We will meet with GSM, Sales and BDC managers first to establish expectations. We will then meet with sales representatives and other lead handling personnell to establish expectations as well.

| Sponsor Signature: |  |
| --- | --- |