| Name | Dan Davenport | Class # | N432 |
| --- | --- | --- | --- |
| Dealership | Mercedes-Benz of Baton Rouge | Date | 5/1/2024 |

| Current Situation or Challenge to be Addressed: | Create new processes to increase dealer's retail tire sales. |  |  |
| --- | --- | --- | --- |
| Current Performance Level (include specific measure): | Current monthly average of 262 retail tires sold. |  |  |
| Goal (what do you want to achieve?) | Increase tire sales along with alignments performed. Will increase production hours and gross profit. |  |  |
| Goal Performance Level (include specific measure) | 400 tires per month by end of 2024. |  |  |
| Goal Start Date: | 5/1/2024 | Goal End Date: | 12/31/2024 |
| First Check-in Date: | 5/31/2024 | Performance Objective: | 300 tires |
| Second Check-in Date: | 6/30/2024 | Performance Objective: | 325 tires |
| Third Check-in Date: | 7/31/2024 | Performance Objective: | 350 tires |
| Fourth Check-in Date: | 8/31/2024 | Performance Objective: | 375 tires |
| How does your goal align with the dealers’ vision? | Goal aligns with dealer vision. Not only will it increase profitablilty, but will provide our customers with the one stop shop and build loyalty. |  |  |
| What are the potential benefits of achieving your goal? | Increased customer retention/loyalty. Increased staff knowledge. Increased gross profit and staff pay. |  |  |
| What are the potential consequences if you don’t achieve your goal? | Potential of lost business and allowing ISPs or other dealers to capture our customers. |  |  |
| Why is the goal important to you? | Tires are something that are needed and are tangible items. It is a small increase in business, but is one of the things that keeps customers loyal. |  |  |
| Potential Obstacles | Lack of advisor knowledge or ability to overcome objections. |  |  |
| Potential Solutions | Invested in training, offered price matching, monthly specials on tires and alignments. |  |  |
| BOTTOM LINE! Financial Impact of Achieving Your Goal (expressed in dollars) | If 400 tires sold, with average of 1 alignment every 4 tires, we would see an incremental profit of $23,000+ |  |  |

What specific actions or steps will you take to accomplish your goal?  What will you do differently or improve? For each, be sure to include necessary resources, who is accountable, the measurable result, and dates.

| Specific action/step | Necessary resource(s) | Accountable person(s) | Expected result | Start, End, & CHeckpoint Dates |
| --- | --- | --- | --- | --- |
| Increased Training | Dealer tire consultants and web based training. | Service Manager | Increased knowledge and awareness amongst staff. | Starting 5/1/24, monthly check-in from rep. |
| Price Matching | Ability to verify pricing by sku# from competitor and match. | Parts manager | To not lose a sale over price from a competitor. | Continual. |
| Additional advisor incentives | Money! And monitoring. | Service Manager | Increased sales with consistant awareness and motivation. | Starting 5/1/24, progress updates with % to goal sent out 3x per week. |
| Continuos performance monitoring and reporting | DMS reports | Service Manager | Increased tire and alignment sales. | 5/1/24 - 3x per week progress reports sent to all staff. |
| Altered service drive process to include pre-inspection. | Staff | Greeters, Charles and Eric have volunteered as champions. | Create more customer awareness up front by having the tire discussion when customer arrives. | 5/1/24, with continal monitoring. |
| Increased video MPI usage and tire process. | MyKaarma video inspection tool. | Shop foreman | Include tire view and measurements with all video MPIs, will aid in increased retail tire sales. | 5/1/24, monthly usage % check ins. Bonus offered to forman and techs for MPI increase. |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |

As you work toward your goal, it’s important to have interim check points with specific, measurable objectives so your team can hold themselves accountable. If everyone knows the goal and objectives, you don’t have to spend your valuable time micromanaging.

Once you’ve accomplished your goal, added or adjusted policies, procedures, and behaviors, now what? How will you ensure you and your staff do not fall back into the previous habits that produced poor results? Be specific.

I have found that once you are monitoring something behaviors will change. If you quit monitoring, they will change back. We have commited to continuing our reporting and getting it in front of the staff on a a regular basis and as often as possible.

Describe any planning or implementation meetings conducted as part of development of your plan.

Had a meeting with dealer tire reps (account manager and consultant) for discussion on process changes as well as incentive ideas. Met with service and parts managers regardign goal and rollout of plan. Met with advisor staff to explain long term goal and rewards for achieving along with resources availible to help with overcoming objections. Aranged for Dealer Tire consultant to spend a week in store to help with training.

| Sponsor Signature: |  |
| --- | --- |