| Name | Warren Smith | Class # | ATD 50 |
| --- | --- | --- | --- |
| Dealership | The Pete Store | Date | 5/10/2024 |

| Current Situation or Challenge to be Addressed: | Time from acquisition to when new and used trucks are considered ready for sale. |  |  |
| --- | --- | --- | --- |
| Current Performance Level (include specific measure): | The average time to reach the frontline is currently 12 days. |  |  |
| Goal (what do you want to achieve?) | Reduce the average time to the frontline. |  |  |
| Goal Performance Level (include specific measure) | My goal is to have an average time to the frontline of 5 days. |  |  |
| Goal Start Date: | 5/1/2024 | Goal End Date: | 5/1/2025 |
| First Check-in Date: | 6/1/2024 | Performance Objective: | 11 days |
| Second Check-in Date: | 8/1/2024 | Performance Objective: | 9 days |
| Third Check-in Date: | 11/1/2024 | Performance Objective: | 7 days |
| Fourth Check-in Date: | 2/1/2025 | Performance Objective: | 6 days |
| How does your goal align with the dealers’ vision? | My dealer's vision to "UNDER COMMIT AND OVER DELIVER" means that we need to keep our promise to our customers of a timely delivery. |  |  |
| What are the potential benefits of achieving your goal? | This could increase customer satisfaction, save money on selling expenses, and increase profit margins. |  |  |
| What are the potential consequences if you don’t achieve your goal? | Floorplan, advertising, and payroll costs could cause us to break even or even lose money on a sale. |  |  |
| Why is the goal important to you? | Keeping our commitment to our customers increases satisfaction and brand loyalty, turning one-time customers into customers for life. |  |  |
| Potential Obstacles | Time to adoption and acceptance of new policies and procedures by staff. |  |  |
| Potential Solutions | Show sales and service departments how new policies will benefit both departments. |  |  |
| BOTTOM LINE! Financial Impact of Achieving Your Goal (expressed in dollars) | Savings on daily selling cost of units. Not forfeiting $272.97 per truck per day on a truck that isn’t ready to sell. |  |  |

What specific actions or steps will you take to accomplish your goal?  What will you do differently or improve? For each, be sure to include necessary resources, who is accountable, the measurable result, and dates.

| Specific action/step | Necessary resource(s) | Accountable person(s) | Expected result | Start, End, & CHeckpoint Dates |
| --- | --- | --- | --- | --- |
| Increase sales labor rate to the current door rate. | Buy in | Sales Manager Service Manager | The service department will gladly move recent acquisitions to the front of the line. | Start: 6/1/24 End: Never Check-in: Every week |
| New & used trucks are checked in and written up within 48 hours. | Staff Buy in Communication | Service Manager Service Advisor Shop Forman | Strict standards ensure the service department always treats the sales department as a preferred captive customer. | Start: 6/1/24 End: 6/1/25 Check-in: Once a month |
| Used truck triage started within 72 hours of being checked in | Staff Time Buy in Communication | Service Manager Service Advisor Shop Forman | Time to the frontline will be decreased. | Start: 6/1/24 End: 6/1/25 Check-in: Once a month |
| New truck PDI started within 72 hours of being checked in. | Staff Time Buy in Communication | Service Manager Service Advisor Shop Forman | Time to the frontline or a customer’s yard decreases | Start: 6/1/24 End: 6/1/25 Check-in: Once a month |
| Regular updates given to the sales team through decisive. | Staff Time Buy in | Service Manager Service Advisor Shop Forman | Communication will ensure timelines are met. | Start: 6/1/24 End: Never Check-in: Every other week |
| Timeline for reconditioning established after triage. | Staff Time Buy in Communication | Service Manager Service Advisor Shop Forman | Ensure sales staff knows what will need to be done in order to sell the unit. | Start: 6/1/24 End: 6/1/25 Check-in: Every other week |
| Account for the increased labor rate with appraisals. | Time Training | Sales Manager Sales Director | The sales department is able to maintain normal margins. | Start: 6/1/24 End: Never Check-in: Every 3 months |

As you work toward your goal, it’s important to have interim check points with specific, measurable objectives so your team can hold themselves accountable. If everyone knows the goal and objectives, you don’t have to spend your valuable time micromanaging.

Once you’ve accomplished your goal, added or adjusted policies, procedures, and behaviors, now what? How will you ensure you and your staff do not fall back into the previous habits that produced poor results? Be specific.

In order to prevent staff from falling back into old habits, data must be collected on the timelines for each step of the PDI and Recon process. Once the habit has been established, bi-monthly check-ins on the process and monthly reviews of the data will be required. When checking in with staff on the process, ideas for improvements and possible snags will be taken in. If there are significant sustained changes in the monthly average days to the frontline, then special attention will be put towards reinforcing the process.

Describe any planning or implementation meetings conducted as part of development of your plan.

I am planning to conduct a joint meeting with the sales and service staff to discuss the implications of the labor rate increase. This meeting will also cover the benefits that the sales staff could reap from reducing their time to the frontline. A separate meeting with the sales staff is also on the agenda to strategize how we can accommodate the labor rate increase during the appraisal of used trucks. In both meetings, I intend to clearly define the standards to which each department will be held, and assign responsibilities accordingly.

| Sponsor Signature: |  |
| --- | --- |