# COMMUNICATION STREAMLINED

Student Name: Zachary Conaway

Class & Student Number: ATD050-008

Academy Week (Var II): 005

# Current situation or challenge you want to address: (must be quantifiable)

- Streamlining communication is and will remain a challenge for any company attempting to promote progress in an ever-changing industry.  Our inability to streamline communication serves as the root cause of inhibition for all other initiatives.  By streamlining communication at Truckworx of Jackson we will increase productivity and efficiency within all departments at all echelons.   We will increase efficiency and productivity by increasing time allowed for these initiatives.    Time saved by opening the calendar and reducing meetings as well as objectives completed in a more timely manner will serve as the quantifiable data for this initiative.

# Overall Objective and Specific Desired Results:

- Decrease the amount of time spent in meetings

  - Reduce time in meetings by 50% in a month (from 15 hrs per month to 7.5 hours) by 31 DEC 2024.

  - Move to 2 meetings per month (1 hr each / 2hr total) by JULY 2025

- Establish priorities at echelon and promote specific conversations

  - Streamline and encourage dialogue

- Foster in awareness at all echelons and get to right action faster

  - Reduce hiring process by 1 week.  Currently takes 2 weeks to hire someone given the process

  - Reduce 1-2week approval times to same day approvals

- Eliminate the bureaucracy within communication and make point to point conversation more routine

# Describe your action plan in detail (be specific and include before and after Measurements)

- Establish a new calendar and develop a central update using formats from military experience.  On slide per department.  INTENT: Train brevity and prioritization by limiting to one slide

  - While conducting update and Managers meeting.  Identify and eliminate redundant communication.  Eliminate meetings on calendar as we find redundancies.  Reduce hours in meetings to 7.5/month.

- Have update and Format approved by Corporate Department Chairs NLT 5 JULY 2024.

  - Establish priority information and preferred updates

  - Place branch in proactive state addressing issues as they see them beginning to rather than reacting to them as they become a problem.

- Have Owner and COO approve update and format.  INTENT:  Establish Critical information for their update.  Eliminate time spent in the countless meetings they have to gain awareness of each department.

  - Routinely take new visions and ideas to reality quicker.

- Implement initiative with first update NLT 19 JUL 2024.  Leverage managers meeting on 22 JUL 2024 for critique and refinement of process.

- Continually refine updates and track efficiency slowly eliminating meetings as we leverage the update and Managers meeting to cover critical information at all echelons.

  - As we get better at this we should begin to act and think as those who are at corporate would.  Considering Risk, limitations and constraints as they would and thus eliminating the routine request for approvals when necessary.  Once we have reached this point (defined by Corporate Department Chairs) we should be able to encourage and empower subordinates with more responsibility therefore eliminating the need for approvals and generating growth from within.

- Begin establishing Quarterly Priorities by department will goals to complete by following quarter.  Leverage this initiative to update on steps / process / vision going forward.

# Timeline:

Describe specific short term and long-term checkpoints to monitor progress

  - Short Term Checkpoint 1: Establish new Calendar and begin eliminating execess meetings By AUG 1

    - Reduce the number of meetings held by 10 percent each month

    - Limit the length of meetings to 30 minutes

    - Send out and provide agendas for all meetings

  - Short Term Checkpoint 2: Reduce time in Meetings / Minimize redundancy 31 DEC 2024

    - Reduce number of meetings by 50 percent.

    - Codify Update format

  - Long Term Checkpoint 1: Take Dealership from 16 ORG meetings/month to 2/month by 1JULY2025

    - Compare monthly numbers (see attachment) and be attentive to awareness within each department.  Have we become more efficient?  Are we effective, are we productively communication.  Consider refining the entire process and begin again.

  - Long Term Checkpoint 2:  Foster rapid change and enable exceeding annual budget through empowerment at department level.  Exceed budget mark 6 months out of the year in 2025.  Currently hit 1 month out of 7 in 2024

# Meeting with Stakeholders (dealership personnel)

Describe what behavior change is needed to support desired goal.  Address required coaching, training and/or consequences (PINO, Gain, Pain).  Include timelines / Accountability / Monitoring process

- Who: Parts Manager, Service Manager, Office Manager and General manager

- What: Maximize time spent put toward initiatives by eliminating the time the spent away from them.  Align priorities and usher in perspective  / leverage expertise by enabling conversation(s) / dialogue with Bi weekly update.

- By When: The first update with an intent to refine the process will occur 19 JUL 2024 no later than 12:00 central time.

- How: Every Tuesday (every other week) we do not have a Managers meeting the attached update will be sent from the respective department head to their corporate counterpart / Department Chair.  All department chairs are aware of the initiative and will assist in shaping information they prefer to update.  Once received all department chairs will reply with appropriate actions that need to take place or will leverage the update to provoke dialogue in the weekly mangers meeting.  ENDSTATE:  The Branch leadership Team made aware of all department initiatives and priorities allowing all departments to align initiatives.  Decreased time in meetings allows for these initiatives to occur at a more rapid pace.

# Dealer agreement:

If you need your sponsors support or approval to implement your plan, have it signed off before you start.  If you can proceed on your own, present this action plan to your sponsor before next class.   Describe the meeting:

The initiative has been approved by both the Owner and the COO.  Pending the results at our dealership a decision to implement Organization wide will be made.