# Departmental Action Plan Template

Student Name: Andrew Hopkins

Class & Student Number: ATD050-007

Academy Week (Var II): 005

# Current situation or challenge you want to address: (must be quantifiable)

- Currently, we have an issue getting the new trucks delivered from the factory prepped for sale in a timely manner. Often times other repairs or projects take priority on getting these trucks completed. The result of this is having these PDI’s[pre-delivery inspection] take between a week and two weeks to complete.

# Overall Objective and Specific Desired Results:

- Our goal is to have all new trucks arriving from the factory completed within 48 hours of arrival.

# Describe your action plan in detail (be specific and include before and after Measurements)

- The first step of my plan is to start with the parts department. Often times parts is to blame for service’s shortcomings in getting trucks prepared.

  - I plan to meet with the parts manager on 7/15 to discuss stock levels of all items required to complete a PDI’s. I will encourage him to increase these stock levels to a stocking level of around 60 days, to prevent shortages once trucks arrive.

  - As part of this discussion, I will bring up getting parts to technicians. Once a technician orders parts, the main priority of the parts department needs to be getting those parts to said technician to prevent further delays.

- The next step is to meet with the sales department on 7/22. My plan is to add a step in their sales process, which is emailing the service department once their truck has been marked as shipped by the factory. This will allow the service department to forecast when the trucks will arrive and have staff and parts in place to have the PDI completed in a timely manner.

- Finally, I plan to meet with the service department on 7/26.

  - First, I will meet with the service manager with the technicians and discuss the significance of getting trucks completed in a timely manner, including customer cancellations and the lack of future orders as a result.

  - Following that, I will meet with the service manager and service writers to introduce a bonus for the service writers. This bonus will pay them an additional $ 15 for each truck completed in under 48 hours after arrival to our dealership. My hope is that this will result in a harder push from the service writers in getting technicians away from the back counter and back on their assigned trucks.

# Timeline:

Describe specific short term and long-term checkpoints to monitor progress

- At the end of every week, I will sit down with the service manager to review a report of all units that arrived at our dealership.

  - This report will include the date and time it arrived, how long it took for the RO to be opened, how long it took to pulled into the shop and how long it took to complete the repair.

  - We will discuss an RO’s that fell outside of the 48-hour window.

- At the end of each month, I will meet with the service manager, parts manager and sales manager to review the report mentioned above.

  - At this time, we will discuss the RO’s that weren’t completed in the 48 hour window, why they weren’t completed and what we need to do to fall inside the 48 hour time set.

  - This will be a positive meeting with a goal of pushing for feedback, seeing what we can do to improve.

# Meeting with Stakeholders (dealership personnel)

Describe what behavior change is needed to support desired goal.  Address required coaching, training and/or consequences (PINO, Gain, Pain).  Include timelines / Accountability / Monitoring process

- Who: Parts Manager – Patrick B, Service Manager - John D, Sales Manager – Steve S., General Manager – Andrew H.

- What: Have the PDI completed on new trucks arriving from the factory, completed in 48 hours.

- By When: The changes discussed above will go into effect immediately with a hard start date of 8/1.

- How: I will hold the department managers accountable for the actions of their team. They will have the opportunity to change the dynamic and show their team the importance of accomplishing this goal. The managers have the month of July to prepare their team, and coach them through the changes taking place so by August 1st, there will be no question of how they should be performing. Our weekly and monthly meetings will be an additional opportunity to set the expectation of what is needed, and to discuss the consequences of continued delays, such as losing customers. With the recommendation from Zach, I will add a report which measures the amount of trucks completed, versus the amount of trucks not completed. This will be a highlight of the meeting.

# Dealer agreement:

If you need your sponsors support or approval to implement your plan, have it signed off before you start.  If you can proceed on your own, present this action plan to your sponsor before next class.   Describe the meeting:

I didn’t get an opportunity to meet with the sponsor to present this action plan but I was able to present it to my counterpart Zach Conaway, GM of a different Truckworx location. He felt it was a good idea to put in place and offered some feedback, which included a report to measure success. As noted above, I will be putting this in place.