# GL Sayre VO2 Action Plan

Student Name:

Bo Sayre

Class & Student Number:

ATD50 #25

Academy Week (Var II):

# Current situation or challenge you want to address: (must be quantifiable)

F&I Penetration at 7%

# Overall Objective and Specific Desired Results:

Get F&I to 40%

# Describe your action plan in detail (be specific and include before and after Measurements)

My action plan boils down to really getting the customer in greater contact with the F&I manager and having the F&I manager more involved in the purchasing process, to ensure the customer has the chance to warm and rapport with them. My idea is to have the F&I manager introduced to the part 3 or more times throughout a sale, and eventually there being a brief sales pitch for F&I (though hopefully the customer will want it before the pitch.) I believe that a well put together pitch alone should be able to increase our buy in by 5% alone at least.

I also want the salesmen to try and sell the F&I before they even get to the F&I Manager. Suggesting at least once every contract.

After the change in procedure, I hope to have a gradual increase of our penetration. Going from the 7% now, then getting to about 20% by the end of the year, and 40% by this time next year.

# Timeline:

Describe specific short term and long term checkpoints to monitor progress

By September 2024

- Establish new F&I strategy

- Get sales training for our F&I Manager

- Get basic F&I training for salesmen, so they can more intelligently communicate about it.

- Create F&I brochure to help with pitch.

- Create Pitch for F&I Manager

- Have F&I walk salesmen through the whole process and vise versa to give both halves a better Idea of their workflows

- Increase penetration to 10%

By December 2024

- Require 1 Salesmen suggestion per purchase

- Require 1 F&I Manager pitch per purchase, and 3 interactions

- Increase penetration to 20%

- Examine results and tweak process to direct towards goal (i.e. adjust number of F&I interactions)

By August 2025

- Continue watching process and tweeking

- Hopefully arrive at 40% penetration

# Meeting with Stakeholders (dealership personnel)

Describe what behavior change is needed to support desired goal.  Address required coaching, training and/or consequences (PINO, Gain, Pain).  Include timelines / Accountability / Monitoring process

- Who: Nicole

- What: Sales Training

- By When: By 9/1/24

- How: Send Nicole to a Sandler intensive, hopefully giving her more tools to help her customers. Tom will oversee scheduling.

- Who: Mark M., Mark S., Chris John

- What: F&I Manager

- By When: 9/1/24

- How: Have Nicole run through some of the basics of F&I with the salesmen, over the course of 2 hours, so they are better equipped to talk about it with their customers. Tom oversee scheduling and a tendence.

- Who: Sales Team

- What: New F&I agreed upon process

- By When:8/1/24, 9/1/24

- How: To create a more synergistic process between Sales and F&I, have a brainstorming on how best to fold into the sales process. Then get a process written down, and everyone must abide by it. Tom oversees and facilitates. Check back in September.

# Dealer agreement:

If you need your sponsors support or approval to implement your plan, have it signed off before you start.  If you can proceed on your own, present this action plan to your sponsor before next class.   Describe the meeting:

Well, the meeting went okay. Our president liked the Idea of increasing our F&I penetration and thought most of my ideas were good. Particularly the shared process plan he seemed receptive too.  He did however say the F&I plan is a little vague, not really touching on slot of specifics on how to make the F&I more appealing (I personally thing we have an appealing F&I program already, we just are not great at talking about it and putting energy into it). He also said that the F&I, though a clearly good place to put work into, is not the biggest fire to put out, so this would most likely go on the back burner. But, since we are already low on penetration, he said “When you hit rock bottom, the only way left is up!”