# Departmental Action Plan Template

Student Name: Colton Pinchin

Class & Student Number: ATD 050

Academy Week (Var II): Week 5

# Current situation or challenge you want to address: (must be quantifiable)

The current challenge that we want to address is our aged and stock piling cores to be rebuilt. Currently we have $78,277.15 in dirty cores, with dirty cores aging back to September of 2022.

# Overall Objective and Specific Desired Results:

The overall objective is to reduce our dirty cores and maintaining an amount of $30,000.00 while eliminating aged dirty cores. We will keep our oldest  warranty dirty core to under 180 days old to keep a buffer for warranty cores. If the core isn’t warranty, we will return it within 60 days.

# Describe your action plan in detail (be specific and include before and after Measurements)

To start we will download the report from menu screen PSR15B in Blaze and sort by aged cores. Once we have the list of all aged cores, we will review it with our core manager to confirm if the cores are in the parts warehouse or if the cores have been lost.

Any cores that have been lost will be written off ($1,000.00 per month) until we are left with just the cores in our inventory.

Any aged cores in our inventory found after the review will be sent back immediately (latest August 1, 2024).

Our parts manager will monitor the cores monthly to ensure returns are being kept up with and that we are maintaining our goal of $30,000.00 in dirty cores.

# Timeline:

Describe specific short term and long term checkpoints to monitor progress

Short term:

July 1, 2024 – Download dirty core report and review with core manager

July 15, 2024 – Determine dirty cores that have been lost and need to be written off

1st of each month – write off minimum $1000.00 of lost cores until all have been accounted for

August 1, 2024 – Be down to $60,000 in cores

September 1, 2024 – Be down to $30,000 in cores

# Meeting with Stakeholders (dealership personnel)

Describe what behavior change is needed to support desired goal.  Address required coaching, training and/or consequences (PINO, Gain, Pain).  Include timelines / Accountability / Monitoring process

- Who: Core Manager (Andrew Wasend)

- What: Download aged core report

- By When: July 1, 2024

- How: PSR15B Report in blaze

- Who: Core Manager

- What: Review all aged cores and determine which cores are lost

- By When: July 15, 2024

- How: Take physical inventory and put hands on all dirty cores to determine if they are in our warehouse or not

- Who: Core Manager

- What: Return all dirty cores that don’t have to be held for warranty

- By When: August 1, 2024

- How: Get hands on parts in inventory and package to return for core credits

- Who: Parts manager

- What: Review lost cores with core manager and determine which cores to write off

- By When: The first of each month until all lost cores written off

- How: Review report from PSR15B in blaze and determine any cores over 180 days old. If core is over 180 days old, determine if it is lost, and if it is lost write it off.

# Dealer agreement:

If you need your sponsors support or approval to implement your plan, have it signed off before you start.  If you can proceed on your own, present this action plan to your sponsor before next class.   Describe the meeting:

Discussed with sponsor and the plan was determined to help eliminate obsolescence, reduce our inventory amount and bring more cash in. This plan aligns with what our dealership is currently trying to do to survive the downturn in the economy and matches the company’s current efforts. The sponsor was happy with the implementation of this plan.