| Name | John Madsen | Class # | ATD 050-18 |
| --- | --- | --- | --- |
| Dealership | Peterbilt Pacific Inc. Abbotsford | Date | 6/27/2024 |

| Current Situation or Challenge to be Addressed: | We have 10 new highway trucks that the deals have fallen through on due to changes in the available work. We need to retail these trucks to stop paying $1000.00 per month on each unit for flooring costs. We also have 24 new dump chassis on the ground waiting for build slots for boxes, also incurring flooring costs. |  |  |
| --- | --- | --- | --- |
| Current Performance Level (include specific measure): | Flooring cost calculation is $1000.00 per month per chassis on the 34 units. Flooring costs total $34,000.00 |  |  |
| Goal (what do you want to achieve?) | Sell the 10 highway units within the next 5 months in addition to the highway sales we have that will still complete as intended. Have the 24 dump chassis delivered to customers by end of year 2024. |  |  |
| Goal Performance Level (include specific measure) | Sell an additional 2 highway units per month for the next 5 months. Deliver 4 dump chassis per month for the remaining 6 months in the year, clearing up build slots for potential orders to go into next year 2025. |  |  |
| Goal Start Date: | 7/2/2024 | Goal End Date: | 12/31/2024 |
| First Check-in Date: | 8/1/2024 | Performance Objective: | To have completed delivery of 2 additional highway units, and 4 dump units to customers. |
| Second Check-in Date: | 9/2/2024 | Performance Objective: | To have completed delivery of 2 additional highway units, and 4 dump units to customers. |
| Third Check-in Date: | 10/1/2024 | Performance Objective: | To have completed delivery of 2 additional highway units, and 4 dump units to customers. |
| Fourth Check-in Date: | 11/1/2024 | Performance Objective: | To have completed delivery of 2 additional highway units, and 4 dump units to customers. |
| How does your goal align with the dealers’ vision? | Flooring costs are making our branch run the risk of losing money overall on a month by month basis regardless of fixed ops absorption and sales profits. Reduction of inventory will return us to profitability. |  |  |
| What are the potential benefits of achieving your goal? | Inventory reduction will reduce monthly flooring costs. Limit the branch financial losses, and new units on the road will increase our Service and related Parts department revenues when doing warrantable repairs for the new trucks. |  |  |
| What are the potential consequences if you don’t achieve your goal? | Inventory will continue to age, adding cost to the individual units, and making each sale less and less profitable. Additional costs incurred due to "lot rot", dead batteries, leaking seals etc will also drive up costs and lower incomes. |  |  |
| Why is the goal important to you? | Sales is the catalyst for the rest of the dealership. Getting this inventory to the end user increases our market share, visibility in the industry, and drives Service and Parts sales. |  |  |
| Potential Obstacles | The highway freight market has dropped off very substantially in the last 8 months, and shows little sign of improvement before the fall months. Our body builder for the dump boxes has over committed to us on what they can produce on a month by month basis. They continue to struggle with the volume of trucks in need of their boxes from all OEMs. |  |  |
| Potential Solutions | Ensure that our marketing of the new highway units is on point, in particular on our website to drive interest, and create opportunities that show up in the branch. We must work with our supplier to get build slots scheduled our 4 units per month minimum into their facility so we can deliver to customers. Regular meetings with the supplier to help them keep their commitments. |  |  |
| BOTTOM LINE! Financial Impact of Achieving Your Goal (expressed in dollars) | Savings of $1000.00 per month per unit delivered. Better cash flow, and return to profitability. |  |  |

What specific actions or steps will you take to accomplish your goal?  What will you do differently or improve? For each, be sure to include necessary resources, who is accountable, the measurable result, and dates.

| Specific action/step | Necessary resource(s) | Accountable person(s) | Expected result | Start, End, & CHeckpoint Dates |
| --- | --- | --- | --- | --- |
| Update photos for each available new unit for posting to our website. | Cleaned and presentable trucks. IT support for posting photos. | John Madsen | Increased website traffic, driving new sales leads for on highway units. | Completion by July 15, 2024 |
| Meet with Steve Reeves at K-Line to get build slot commitments. | Salesmans time and availability. | Jessy Gill | Commitment of 4 build slots minimum per month. | Initial meeting completed by July 5. Schedule monthly review until year end. |
| Monthly review with supplier to review results. | Time | Jessy Gill, John Madsen | Supplier accountability for 4 slots per month. | August 1, to year end. |
| Monthly inventory meeting with sales staff. | Sales team | Chuck Dietrich VP of sales | Awareness at other branches of available inventory. | Ongoing, no end date. |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |

As you work toward your goal, it’s important to have interim check points with specific, measurable objectives so your team can hold themselves accountable. If everyone knows the goal and objectives, you don’t have to spend your valuable time micromanaging.

Once you’ve accomplished your goal, added or adjusted policies, procedures, and behaviors, now what? How will you ensure you and your staff do not fall back into the previous habits that produced poor results? Be specific.

Monthly company wide inventory meetings are already in progress. Monthly review of branch specific inventory to be on going to ensure stock units are not aging.

Describe any planning or implementation meetings conducted as part of development of your plan.

Monthly inventory meetings, and lower mainland branch manager meetings are in progress. Specific meeting with Jessy Gill regarding getting commitments from our body builder.

| Sponsor Signature: |  |
| --- | --- |