| Name | Warren Smith | Class # | 50 |
| --- | --- | --- | --- |
| Dealership | The Pete Store | Date | 7/19/2024 |

| Current Situation or Challenge to be Addressed: | At my dealership, we currently have over 800 hours of work-in-progress time. Given that we’re a fairly small dealership with only 9 technicians, this amount is excessively high. |  |  |
| --- | --- | --- | --- |
| Current Performance Level (include specific measure): | Currently we have 88 hours of WIP per tech. |  |  |
| Goal (what do you want to achieve?) | I would like to decrease the WIP to 40 hours per tech or lower. |  |  |
| Goal Performance Level (include specific measure) | <40 hours of WIP per tech |  |  |
| Goal Start Date: | 8/1/2024 | Goal End Date: | 1/1/2026 |
| First Check-in Date: | 9/1/2024 | Performance Objective: | Monthly average WIP < 70 hours per tech |
| Second Check-in Date: | 12/1/2024 | Performance Objective: | Monthly average WIP < 50 hours per tech |
| Third Check-in Date: | 6/1/2025 | Performance Objective: | Reach monthly average of <40 hours per tech |
| Fourth Check-in Date: | 12/1/2025 | Performance Objective: | Maintine <40 hours per tech average |
| How does your goal align with the dealers’ vision? | My dealer’s vision to ‘PROVIDE EXTRAORDINARY SERVICE’ directly aligns with my goal. Lowering WIP will allow us to deliver prompt and efficient service. When WIP spirals out of control, it hinders the extraordinary dealership experience. Excessive WIP can obscure the small details that keep our customers coming back. |  |  |
| What are the potential benefits of achieving your goal? | Reducing our WIP enhances cash flow for expense payments and boosts customer satisfaction by shortening repair completion time. A low WIP can be a good sign of a service departments overall health as long as there is enough work to keep technicians busy. |  |  |
| What are the potential consequences if you don’t achieve your goal? | High WIP can have severe consequences. It may tie up our cash flow, leading to delayed bill payments. Additionally, it can hinder growth and create a reputation for long wait times, which is detrimental to our customers’ businesses. Most importantly, allowing WIP to run wild results in mediocrity. We don’t get out of bed to be mediocre. |  |  |
| Why is the goal important to you? | Reducing our WIP is crucial as it enhances our shop’s efficiency, improves customer service, and positively reflects the Peterbilt brand. As trucking is America’s backbone and Peterbilt produces exceptional vehicles, my contribution, however minor, to this industry’s improvement is my motivation. |  |  |
| Potential Obstacles | Numerous common obstacles hinder achieving an acceptable amount of work-in-progress (WIP). One significant challenge we face is complex diagnostics. For instance, issues like persistent vibrations can lead technicians to spend over 100 hours diagnosing and correcting problems, even with engineering support. Critical backordered parts can also delay large jobs such as inframes or harness repairs, leaving them open for weeks or months. Additionally, some obstacles arise from the service department waiting until the end of the month to close all R.O.s, although we seem to have a good handle on that. |  |  |
| Potential Solutions | A service department’s ability to maintain low WIP is directly tied to its profitability. To reduce WIP at a dealership effectively, focus on vigilant repair planning and improved technician training. Communication between Service Managers, Advisors, Foremen, and Back Counter Parts is crucial for lead times, parts needs, and repair planning. Additionally, staying updated on bulletins and training can save time on repairs. An open line of communication benefits overall dealership efficiency, ensuring regular updates and clarifications for technicians from the Foreman and Service Manager. |  |  |
| BOTTOM LINE! Financial Impact of Achieving Your Goal (expressed in dollars) | With over $163,000 tied up in labor sales alone and around the same tied up in parts freeing around half of that capital would greatly bennefit investments that can be made in the dealership and the company. |  |  |

What specific actions or steps will you take to accomplish your goal?  What will you do differently or improve? For each, be sure to include necessary resources, who is accountable, the measurable result, and dates.

| Specific action/step | Necessary resource(s) | Accountable person(s) | Expected result | Start, End, & CHeckpoint Dates |
| --- | --- | --- | --- | --- |
| Weekly WIP meeting. | Time | Service Manager Regonal Service Manager Forman | Better communicate problems and solutions to outstanding tickets. | Start: 8/1/24 Checkpoint Dates: Every week End: Never |
| Close any outstanding tickets that haven’t received repair approval after 30 days. | Time Customer Communication | Service Manager Service Advisors | Lower the number of hours on the books and free up cash for operations. | Start: 8/1/24 Checkpoint Dates: Every month during WIP meeting End: Never |
| Have the back counter staff provide copies of the special order parts list, including lead times, to the service department during the morning meeting at the shop. | Time Paper | Back Counter Parts Service Advisor Forman Service Manager | Improve communication on special order parts lead time and improve repair planning. | Start: 8/1/24 Checkpoint Dates: 8/16/24 , 11/1/24 , 2/1/25 End: 2/1/25 |
| Attempt to expect the unexpected. Enhance job planning by determining lead times and potential sources for unforeseen parts. Train technicians to request all possible parts for a task. Label parts as necessary or potentially needed for the job. | Cash Time Buy-in | Back counter parts Forman Techs | Decrease job hopping. Keeping techs on the same job will allow them to complete a job faster thus decreasing WIP. | Start: 8/1/24 Checkpoint Dates: 8/16/24 , 11/1/24 , 2/1/25 End: 2/1/25 |
| Implement a robust quality control checklist. | Comprehensive comeback analysis Time Buy-in | General Manager Forman Techs | More time spent on rework means less time on existing workload. | Start: 8/1/24 Checkpoint Dates: Every month for the first 6 months then every 3 months. End: 1/1/26 |
| Improve the first time fill rate and efficiency of the back counter person. Improve lost sales tracking and keep most commonly used shop items on shelves close to the back counter or have parts runners. | Warehousing Cash Additional Employees | Back Counter Parts Parts Manager Inventory Control | Allow for more efficient jobs and less job hopping. | Start: 8/1/24 Checkpoint Dates: 9/1/24, 12/1/24, 6/1/25 End: 6/1/25 |
| Improve training for Forman and Techs for interactions with Engineering. | Training Time Buy-in Incentives for completing training and showing understanding | Regonal Service Manager Service Manager Forman Techs | An improved ability to follow and understand the directions of TCS, PACCAR's engineering support team will decrease diagnostic time and time spent on uncommon or complex diagnostics. | Start: 8/1/24 Checkpoint Dates: Every month End: Never |

As you work toward your goal, it’s important to have interim check points with specific, measurable objectives so your team can hold themselves accountable. If everyone knows the goal and objectives, you don’t have to spend your valuable time micromanaging.

Once you’ve accomplished your goal, added or adjusted policies, procedures, and behaviors, now what? How will you ensure you and your staff do not fall back into the previous habits that produced poor results? Be specific.

Maintaining weekly WIP meetings between department managers and regional/general managers is crucial. High WIP is a common obstacle that service departments encounter, and it’s easy to fall back into old habits. Staying vigilant with training will also be key.

Describe any planning or implementation meetings conducted as part of development of your plan.

To enhance efficiency, we should focus on planning a warehousing format that enables the back counter parts person to work more effectively. Additionally, technicians require ongoing training and feedback to understand directions and follow proper procedures for diagnostics and repairs, as directed by engineering support. Initially, our weekly WIP meeting will involve reviewing any tickets with more than 20 hours on them or that have been open for longer than one month, along with potential solutions for closure. We’ll also need additional planning and feedback from the service team to address common quality control mistakes observed in the shop and find effective prevention strategies. WIP in a dealership will always exist but it's important to keep it in check.

| Sponsor Signature: |  |
| --- | --- |