| Name | Anthony(Tony) Grist | Class # | N433 |
| --- | --- | --- | --- |
| Dealership | CMA's Hyundai of Winchester | Date | 5/10/2024 |

| Current Situation or Challenge to be Addressed: | Need to get sales people to consistently add video content to Internet response's |  |  |
| --- | --- | --- | --- |
| Current Performance Level (include specific measure): | We are at 10% ( 1 sales person has commited into it) out of 6 and even he is not doing it consistently |  |  |
| Goal (what do you want to achieve?) | Over 4 months get to 80% Video response rate. |  |  |
| Goal Performance Level (include specific measure) | 80% over 3 month (May, June &July). "Snap cell" is new application we are adding . Its tied to CRM (Vin-Solutions) , so we can track video response rate for the team and the individuals. |  |  |
| Goal Start Date: | 5/1/2024 | Goal End Date: | 8/31/2024 |
| First Check-in Date: | 5/30/2024 | Performance Objective: | 20% Video repsonse rate |
| Second Check-in Date: | 6/30/2024 | Performance Objective: | 40% Video Response rate |
| Third Check-in Date: | 7/30/2024 | Performance Objective: | 60% Video Response rate |
| Fourth Check-in Date: | 8/30/2024 | Performance Objective: | 80% Video response rate |
| How does your goal align with the dealers’ vision? | Video repsonse rate has been determined to increase customer response rate considerably. More responses , More appointments, sell more cars. CMA is commited to it |  |  |
| What are the potential benefits of achieving your goal? | If we increase our video response rate, we will incraese the number of appointments set weekly . At a 24% closing ration on appointments. We will sell more cars. |  |  |
| What are the potential consequences if you don’t achieve your goal? | We need to incraese our sales efficincy to 100%. We currently are at 79%. If we do not achomplish this consequesces will be fewer sales and possible termination |  |  |
| Why is the goal important to you? | I want to keep my job!! |  |  |
| Potential Obstacles | Getting sales people and management to buy into the value of video response and the impact on there pocket and the stores net income is parimount. |  |  |
| Potential Solutions | Management must track daily the email/text response from salespeople and make sure they add video response to the content when they respond |  |  |
| BOTTOM LINE! Financial Impact of Achieving Your Goal (expressed in dollars) | With 517 "Good" leads YTD and 120 Appointments scheduled (23%) we are looking to increase our Number of appointments by 20% (144 appointments). At an appointments closing ratio YTD of 70%. This will generate an additional 17 daels for use ( YTD) At an average PVR of $3215 YTD on Retail. This will equate to 17 x $3215 = $54,655.00 ( This is pur profit. Divided by 4.5 is an additional $12,145.00 per month . $12,145 x 12= $145,746.00 for the year if implemented. This is pure profit or Net!! |  |  |

What specific actions or steps will you take to accomplish your goal?  What will you do differently or improve? For each, be sure to include necessary resources, who is accountable, the measurable result, and dates.

| Specific action/step | Necessary resource(s) | Accountable person(s) | Expected result | Start, End, & CHeckpoint Dates |
| --- | --- | --- | --- | --- |
| Train Sales People. Jeff Garber | Manager using "Snap Cell" in conjuction with Vin Solutions app to Track consistence | Andy Gray & Brian Charland | 20% Increase Monthly until we hit 80% Through July | May 31st- Aug 31st, Check progress every 30 days , At the end of each month . Goal is 20% increase Monthly |
| Train sales People: Ethan Wrights | Manager using "Snap Cell " In conjunction with Vin Solutions To Track production | Andy Gray & brian Charland. Sales mnagers | 20% Increase Monthly until we hit 80% Through July | May 31st- Aug 31st, Check progress every 30 days , At the end of each month . Goal is 20% increase Monthly |
| Train sales People: David Kreamer | Manager using "Snap Cell " In conjunction with Vin Solutions To Track production | Andy Gray & brian Charland. Sales mnagers | 20% Increase Monthly until we hit 80% Through July | May 31st- Aug 31st, Check progress every 30 days , At the end of each month . Goal is 20% increase Monthly |
| Train sales People: Usman Khan | Manager using "Snap Cell " In conjunction with Vin Solutions To Track production | Andy Gray & brian Charland. Sales mnagers | 20% Increase Monthly until we hit 80% Through July | May 31st- Aug 31st, Check progress every 30 days , At the end of each month . Goal is 20% increase Monthly |
| Train sales People: Tim Obarr | Manager using "Snap Cell " In conjunction with Vin Solutions To Track production | Andy Gray & brian Charland. Sales mnagers | 20% Increase Monthly until we hit 80% Through July | May 31st- Aug 31st, Check progress every 30 days , At the end of each month . Goal is 20% increase Monthly |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |

As you work toward your goal, it’s important to have interim check points with specific, measurable objectives so your team can hold themselves accountable. If everyone knows the goal and objectives, you don’t have to spend your valuable time micromanaging.

Once you’ve accomplished your goal, added or adjusted policies, procedures, and behaviors, now what? How will you ensure you and your staff do not fall back into the previous habits that produced poor results? Be specific.

Change payplan for sales people . Must have Video response content in 80% of Internet responses or they will lose a % of gross on used and reduce their flats on new

Describe any planning or implementation meetings conducted as part of development of your plan.

Meet with management team and explain gaols and when we track our success. How this will impact our bottom line!

| Sponsor Signature: |  |
| --- | --- |