| Name | Casey Menten, Drake Menten | Class # | 433 |
| --- | --- | --- | --- |
| Dealership | Sawgrass Ford | Date | 4/29/2024 |

| Current Situation or Challenge to be Addressed: | Lack of personalized responses to online leads, a disconect from our online presence and in-person sales team |  |  |
| --- | --- | --- | --- |
| Current Performance Level (include specific measure): | Currently we have a 5% Video response for online leads |  |  |
| Goal (what do you want to achieve?) | Within the next 6 months, the car salesman at Sawgrass Ford will produce and send personalized video presentations to at least 55% of online customers who express interest in a specific vehicle, aiming to increase customer engagement and drive sales |  |  |
| Goal Performance Level (include specific measure) | We will check the percentage of video responses to credible leads. Currently, we have a 5% response rate. We plan to track this weekly, along with tracking which salesman have utilized video and the amount of videos produced. These are the goal response percentage per month May:25% June:30% Jul:40% Aug:45% Sept:50% Oct:55% |  |  |
| Goal Start Date: | 5/1/2024 | Goal End Date: | 10/31/2024 |
| First Check-in Date: | 5/31/2024 | Performance Objective: | 25% respond rate |
| Second Check-in Date: | 6/30/2024 | Performance Objective: | 30% respond rate |
| Third Check-in Date: | 8/31/2024 | Performance Objective: | 40% respond rate |
| Fourth Check-in Date: | 9/30/2024 | Performance Objective: | 45% respond rate |
| How does your goal align with the dealers’ vision? | Our Dealer strives to create a customer-centric experience, that is transparent and efficient for customers. This goal allows us to create personal experiences for customers and streamline the sale of a car from online to in-person. |  |  |
| What are the potential benefits of achieving your goal? | Achieving this goal would align our customer's online experience with Sawgrass Ford's Vision. If done correctly, CSI will increase without a single expense and the dealership will improve the success rate of online leads. |  |  |
| What are the potential consequences if you don’t achieve your goal? | Without accomplishing this goal we could potentially fall behind in this rapidly changing industry. Being the first in our market to indroduce videos will set us apart as a unique dealership focused on customer service. However, if we fall behind we will simply be an inauthentic dealership jumping on the bandwagon. |  |  |
| Why is the goal important to you? | Being a family owned dealership, it is important that our employees, customers, and community prioritized in a way no larger autogroup can. Taking the next step to make every customer feel important is crucial to the success of Sawgrass Ford's vission. I want to show off our amazing Sales team, and there is no better way than connecting directly with the customer before they even step foot at the dealership |  |  |
| Potential Obstacles | Those on the Sales Team with tenure may be reluctant to switch up their regular routine and adopt video into the mix. |  |  |
| Potential Solutions | We will have monthly video contests paired with a monthly bonus for number of videos sent |  |  |
| BOTTOM LINE! Financial Impact of Achieving Your Goal (expressed in dollars) | The average gross per vehicle (per month)= $3,479 Lost Leads (per month)= 852 10% of lost leads= 85 Monthly potential increase in Sales Gross= $295715 If Sawgrass Ford began sending video leads back to leads, suposing a 10% increase in appointment shows, there will be 85 new customers coming in to the dealership. With the average vehicle grossing $3,479, there is potential to increase sales gross by around $295,715 |  |  |

What specific actions or steps will you take to accomplish your goal?  What will you do differently or improve? For each, be sure to include necessary resources, who is accountable, the measurable result, and dates.

| Specific action/step | Necessary resource(s) | Accountable person(s) | Expected result | Start, End, & CHeckpoint Dates |
| --- | --- | --- | --- | --- |
| Train sales on Video | 15 minute Sales Meetings | GSM | Sales members feel cinfident taking videos | TBD |
| Train BDC to direct car-specific leads to Sales members | New Process | BDC Manager | Proper process linking leads to Sales Team | TBD |
| Implement Weekly Video competition | Spiff $$$ | GSM, Managers | Create a fun incentive for videos, Highlighting funny/top videos | TBD |
| Implement Monthly Bonus based on Videos produced | Spiff $$$ | GSM, Managers | Ensure Sales members are meeting response rate percentage | TBD |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |

As you work toward your goal, it’s important to have interim check points with specific, measurable objectives so your team can hold themselves accountable. If everyone knows the goal and objectives, you don’t have to spend your valuable time micromanaging.

Once you’ve accomplished your goal, added or adjusted policies, procedures, and behaviors, now what? How will you ensure you and your staff do not fall back into the previous habits that produced poor results? Be specific.

We plan to begin with incentives and recognition and then transition to encouraging more autonomy and ownership of their videos. Throughout this process we will provide regular feedback to ensure all saleman feel confident in the videomaking process. After our goal is completed we will continue to monitor video responses and take action if we see a dip in response rate.

Describe any planning or implementation meetings conducted as part of development of your plan.

1)Meet with our GSM to go over what video responses are and how we plan to enroll this goal 2)Work to implement training in our current sales meetings 3)Meet with the GSM on a bi-weekly basis to discuss success of video responses 4)Have 1-on-1 meetings with sales team to discuss what is going right/ wrong and what can be clarified/ improved on

| Sponsor Signature: |  |
| --- | --- |