| Name | Dylan Berk Aldinc | Class # | 433-10 |
| --- | --- | --- | --- |
| Dealership | Greenway Hyundai of Orlando | Date | 3/13/2024 |

| Current Situation or Challenge to be Addressed: | Sending too many vehicles to wholesale. |  |  |
| --- | --- | --- | --- |
| Current Performance Level (include specific measure): | 61% Wholesale to Retail Ratio. Retailed average of 90 used and 55 in wholesale a month |  |  |
| Goal (what do you want to achieve?) | Lower the wholesale ratio down to 30% |  |  |
| Goal Performance Level (include specific measure) | We will decrease the number of cars being sent to auction by April 20th |  |  |
| Goal Start Date: | 3/15/2024 | Goal End Date: | 5/20/2024 |
| First Check-in Date: | 3/16/2024 | Performance Objective: | Adjust prices for faster sales |
| Second Check-in Date: | 3/25/2024 | Performance Objective: | Optimize inventory turnover |
| Third Check-in Date: | 4/15/2024 | Performance Objective: | Improve Retail Sales Volume |
| Fourth Check-in Date: | 5/20/2024 | Performance Objective: | Balanced New to Used Sales Ratio |
| How does your goal align with the dealers’ vision? | The vision of the dealer is to keep more cars for retail |  |  |
| What are the potential benefits of achieving your goal? | Balanced New to Used Sales Ratio. More internal gross for Service Department. More Variable Gross |  |  |
| What are the potential consequences if you don’t achieve your goal? | Overspending in recon for thoe vehicles will lead to frozen capital and bigger wholesale loss in the future. |  |  |
| Why is the goal important to you? | More volume means more momentum. Better momentun creates Synergy and positive enviroment. Keeping cheaper vehicles that sells faster rather than sending them to wholesale is very important to me |  |  |
| Potential Obstacles | Average Recon Time, Overspending in Recon, Not moving the unit fast enough |  |  |
| Potential Solutions | Efficient Reconditioning, Minimize the time vehicles stay in your inventory, Better communication with Service and Parts Department |  |  |
| BOTTOM LINE! Financial Impact of Achieving Your Goal (expressed in dollars) | 396 Used Vehicles Sales annualy. $712,000 in Variable Gross ($2,000 front and back) $396,000 in Internal Gross ($1,000 "gross" per vehicle) $1,108,000 Additional Annual Gross |  |  |

What specific actions or steps will you take to accomplish your goal?  What will you do differently or improve? For each, be sure to include necessary resources, who is accountable, the measurable result, and dates.

| Specific action/step | Necessary resource(s) | Accountable person(s) | Expected result | Start, End, & CHeckpoint Dates |
| --- | --- | --- | --- | --- |
| Set up a step called "Before Wholesale" and send a notifaction to Service Manager Assistant | Recon Velocity | Jafar Naama | Jafar will review the RO and see what he can do to save the vehicle from going to wholesale | 03/15/2024 Check it daily |
| Set Up a step called "Save the Vehicle" | Recon Velocity | Jafar Naama Rene Lazoromero | Only safety items will remain on the RO. Jafar will put the vehicle in "Save the Vehicle Step" where Rene will receive a notication with revised UCM approval | 03/15/2024 Check it Daily Check every 7 days to see the progress |
| Set up a Step called "Saved the Vehicle" | Recon Velocity | Rene Lazoromero Jafar Naama | Rene will approve the work and park the car in "Saved the Vehicle" step. | 03/15/2024 Check it Daily |
| Adjust prices based on the Market Data | Vauto | Rene Lazoromero Berk Aldinc CarData | Increase the Speed at which you sell cars | 03/20/2024 Check dailiy |
| Take 8 Quality Pictures | Good Appraisal Pictures, Vauto | Cardata | More exposure on the vehicles and utilize the marketting dollars | 03/20/2024 |
| Create an another Step on Recon Velocity for the GSM or GM to receive a notification for the final review before the vehicle goes to wholesale | Recon Velocity. Comminucation between all departments | Ken Sidana Berk Aldinc Jafar Naama James Ferrell | Coming to an agreement between parts, service and used car department and saving a potential vehicle | 03/25/2024 Check weekly reports |
| Offer a Bonus Structure to both Used Car Manager and Used Car tech, when achieved 30% wholesale to Retail Ratio | Need an approval from the GM | Ken Sidana | More Low Priced Inventory to sell. More Volume | 03/31/2024 Check at the end of each month |

As you work toward your goal, it’s important to have interim check points with specific, measurable objectives so your team can hold themselves accountable. If everyone knows the goal and objectives, you don’t have to spend your valuable time micromanaging.

Once you’ve accomplished your goal, added or adjusted policies, procedures, and behaviors, now what? How will you ensure you and your staff do not fall back into the previous habits that produced poor results? Be specific.

We will have sent out weekly reports of total vehicls sold at the wholesale. We will cap the number of vehicles allowed to go to wholesale. We could offer a performance based payplan where service can sell more hours and used car managers can make more money if they can achieve the goal of 30 percent wholesale to retail ratio.

Describe any planning or implementation meetings conducted as part of development of your plan.

I spoke with my General Manager. We both emphisized the importance of having more cheap vehicles in the lot and how fast they sell compared to higher priced vehicles. We believe in the impact that it will create on the bottom line. How it will compound to more gross for all departments and give more inventory to Sales Consultants to sell. Service director and his assistant are on the same page. Service assistant already started getting involved on the wholesale vehicles to see if he can save them from going to wholesale. We are working on the planning.

| Sponsor Signature: |  |
| --- | --- |