| Name | Dan Chamberlain | Class # | N434 |
| --- | --- | --- | --- |
| Dealership | Henley Honda | Date | 3/10/2024 |

| Current Situation or Challenge to be Addressed: | Sales team not using video response for lead follwup |  |  |
| --- | --- | --- | --- |
| Current Performance Level (include specific measure): | 0 Videos per day being sent by sales team |  |  |
| Goal (what do you want to achieve?) | 3 Videos per day/ per sales team |  |  |
| Goal Performance Level (include specific measure) | To have the sales team respond to all customer inquiries within 20 minutes WITH video response. Also using video to leverage followup/birthday messaging to clients |  |  |
| Goal Start Date: | 3/11/2024 | Goal End Date: | 3/10/2025 |
| First Check-in Date: | 4/30/2024 | Performance Objective: | 1x Videos sent per day/ sales associate |
| Second Check-in Date: | 5/6/2024 | Performance Objective: | 2x Videoes on average being sent per day / sales associate |
| Third Check-in Date: | 7/31/2024 | Performance Objective: | 3x Videos per day being sent / sales person |
| Fourth Check-in Date: | 11/1/2024 | Performance Objective: | 3x Videos per day / sales person AND service advisors |
| How does your goal align with the dealers’ vision? | Our deleaership vision as all about communication and transparency. Using video response and elad followup will increase both of these metrics while also enhancing the customer experience |  |  |
| What are the potential benefits of achieving your goal? | Increased customer engagement. Customer gets a sense of transparency and a service level that sets us aparyt from the competition |  |  |
| What are the potential consequences if you don’t achieve your goal? | We will"Blend" in with the crowd and fail to meet opportunities to exceed customer expecations and improve the customer experience. |  |  |
| Why is the goal important to you? | It is important to me because I feel as if we have always aimed to provide above average service in our dealership and this allows us to take the next step. |  |  |
| Potential Obstacles | Sales team could be resistant. Not all team memebers are comfortable in front of a camera |  |  |
| Potential Solutions | Show them ways to complete videos without having to be "In" them. Customer can still get a sense of personality and engagement with "walk around" style video |  |  |
| BOTTOM LINE! Financial Impact of Achieving Your Goal (expressed in dollars) | I believe the bottom line here could be massive. Hard to specifically quantify. But lets say it adds 3 deals per month. 3 x 12 = 36 deals a year. Average Gross is 4300 per units. $154,000 in additional gross per year by just completing videos is very possible. |  |  |

What specific actions or steps will you take to accomplish your goal?  What will you do differently or improve? For each, be sure to include necessary resources, who is accountable, the measurable result, and dates.

| Specific action/step | Necessary resource(s) | Accountable person(s) | Expected result | Start, End, & CHeckpoint Dates |
| --- | --- | --- | --- | --- |
| Conduct manager meeting with sales managers and service managers. | Sales managers buyin is needed for accountability and coaching. | Sales Managers | Schedule meeting with sales team to explain program and expectations | Start March 12th 2024. No check in |
| Conduct staff meeting on Wednesday with sales team | Boardroom. Laptop and CRM to show how to log videos | All sales team | Team understands vision and program expecations. | Meeting March 13th. No checkin required |
| Research video software to help team shoot and send. | GoVideo/Other Software | Dan Chamberlain | Purchase software suite to ensure we have resources to execute | March 15th 2024. |
| Traing all staff on specific software to ensure they are comfortable. | Trainer from software company to assist | Dan Chamberlain | Team understands and pilot program begins to start 1x per day | March 22nd. Checking March 31st. Program Launch April 1st/ |
| Schedule Meeting May 1st to follow up with first 30 days of use. | Boardroom, sales managers | Dan Chamberlain and Sales Managers | Team is executing minimum 2x per day and logged in CRM for validations. Rewards. | May 1st 2024. |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |

As you work toward your goal, it’s important to have interim check points with specific, measurable objectives so your team can hold themselves accountable. If everyone knows the goal and objectives, you don’t have to spend your valuable time micromanaging.

Once you’ve accomplished your goal, added or adjusted policies, procedures, and behaviors, now what? How will you ensure you and your staff do not fall back into the previous habits that produced poor results? Be specific.

We will continue to monitor performance in CRM and reward top performers. Coaching and development plans for those who do not buy in. I will attempt to quantofy results for top performers to show other memnbers of the team what is possible.

Describe any planning or implementation meetings conducted as part of development of your plan.

We will meet weekly with sales managers and include service managers to make sure we are all bought in and "rowing" in the same direction. We will ensure all members of team have resources needed. Software training will be done in conjunction with vendor to ensure no questiuons unanswered.

| Sponsor Signature: |  |
| --- | --- |