| Name | Kurt Richardson | Class # | N434 |
| --- | --- | --- | --- |
| Dealership | Caskinette Ford | Date | 3/11/2024 |

| Current Situation or Challenge to be Addressed: | Used Inventory Turn |  |  |
| --- | --- | --- | --- |
| Current Performance Level (include specific measure): | Current Inventory Turn is 4.6 |  |  |
| Goal (what do you want to achieve?) | I would like to double our turn rate by the end of 2024 or before. |  |  |
| Goal Performance Level (include specific measure) | This goal can be achieved by implementing the proper processes. While being aggressive and persistent are necessary approaches, a quick result cannot be expected. "1 degree turns at a time" or "slow and steady wins the race" are the proper and realistic approaches. |  |  |
| Goal Start Date: | 3/11/2024 | Goal End Date: | 12/31/2024 |
| First Check-in Date: | 3/31/2024 | Performance Objective: | Any amount of increase in turn rate. |
| Second Check-in Date: | 6/30/2024 | Performance Objective: | Turn rate of 6 or above. |
| Third Check-in Date: | 9/30/2024 | Performance Objective: | Turn rate of 8 or above. |
| Fourth Check-in Date: | 12/31/2024 | Performance Objective: | Turn rate of 10 or above. |
| How does your goal align with the dealers’ vision? | This goal aligns well with the dealer and GM's vision. We get paid to turn a net profit, and the higher the turn - the higher the net profit. |  |  |
| What are the potential benefits of achieving your goal? | The biggest potential benefit is a much higher GROI per unit which then adds to the dealerships total gross. Other benefits are, but not limited to, much more controlled inventory/days supply, lower floor plan expense, more efficient recon process, etc. |  |  |
| What are the potential consequences if you don’t achieve your goal? | The potential consequences are more of the same of what we are currently facing. Aged inventory, dead money, high day count in recon, etc. |  |  |
| Why is the goal important to you? | This is one of the most imporant areas of a dealerships profitability and what I do every day. Not having a used car floor plan is great, but cannot be the reason why there is not an emphasis on higher turn rate for our dealership. |  |  |
| Potential Obstacles | Kickback from sales managers and sales representatives, but strictly from a pay plan standpoint - and that is understandable. It will be our job to show them how taking the hit now on the super aged inventory is beneficial in the long run. Same goes for hitting our stride with the higher turn which potentially comes with a lower front-end gross average, but that can be made up in volume. |  |  |
| Potential Solutions | Educating the proper people on "The Power of The Turn". Educating them and then proving it to them over time. |  |  |
| BOTTOM LINE! Financial Impact of Achieving Your Goal (expressed in dollars) | $3,969,288 yearly projected gross varience by doubling our turn rate. WHO SAYS NO??!! |  |  |

What specific actions or steps will you take to accomplish your goal?  What will you do differently or improve? For each, be sure to include necessary resources, who is accountable, the measurable result, and dates.

| Specific action/step | Necessary resource(s) | Accountable person(s) | Expected result | Start, End, & CHeckpoint Dates |
| --- | --- | --- | --- | --- |
| Appraising | vAuto | Myself and Sales Managers | Higher Look to Book % while also owning acquired vehicles correctly. | Start: Now End: Never Checkpoint: Weekly |
| Exit Strategy @ Acquisition (Retail or Wholesale) | vAuto | Myself and Sales Managers | Hoping to gain a few more retail units out of this to help with volume, GROI, turn, etc. | Start: Now End: Never Checkpoint: Daily |
| Reconditiong | Rapid Recon | Myself, Service/Parts/Spa Managers | Substationally decrease the amount of time a unit is in this process. Currently it is 25 days. | Start: Now End: Never Checkpoint: Daily |
| Merchandising | vAuto, Social Media Platforms | Myself, Marketing Dept, Sales Managers & Sales Reps | Daily videos. Deal of the day. Deal of the week. Just more overall exposure of what we have to offer. | Start: Now End: Never Checkpoint: Daily |
| Pricing | vAuto | Myself | Re-price more often to stay competitive and aggressive in the market. | Start: Now End: Never Checkpoint: Multiple times per week |
| Exit Strategy @ The Aged Stage | vAuto | Myself | Not letting inventory age past a set days in inventory. | Start: Now End: Never Checkpoint: TBD |
| Ultimate Goal: Increased Turn Rate | vAuto | Myself and Whole Sales Dept | Higher Turn Rate | Start: Now End: Never Checkpoint: Quarterly |

As you work toward your goal, it’s important to have interim check points with specific, measurable objectives so your team can hold themselves accountable. If everyone knows the goal and objectives, you don’t have to spend your valuable time micromanaging.

Once you’ve accomplished your goal, added or adjusted policies, procedures, and behaviors, now what? How will you ensure you and your staff do not fall back into the previous habits that produced poor results? Be specific.

We don’t fall back into the previous habits by making this our new habit. I believe this is achieved by accepting nothing less from myself and the people who are around me. Realizing there will be kickbacks and handling that with data, facts and real time results will be key in moving us all in this new direction.

Describe any planning or implementation meetings conducted as part of development of your plan.

This process starts with letting everyone involved know what our new habit is going to be and that is where our journey begins.

| Sponsor Signature: |  |
| --- | --- |