| Name | Mariana Orshak, Mark Flaherty, Greg Vandeloo, Kirk Whitt | Class # | N435 BCE |
| --- | --- | --- | --- |
| Dealership | Crossroads Ford of Dunn-Benson | Date | 6/20/2024 |

| Current Situation or Challenge to be Addressed: | Currently, we do not source many vehicles from customers as "street buys." Vehicles sourced that way are more profitable and turn faster than any other way (outside of trading.) |  |  |
| --- | --- | --- | --- |
| Current Performance Level (include specific measure): | 2.5 vehicles acquired from individuals monthly average YTD |  |  |
| Goal (what do you want to achieve?) | Increase the amount of vehicles purchased directly from customers. This will increase our pre-owned vehicle sales as a result of having more inventory at the right price. |  |  |
| Goal Performance Level (include specific measure) | A monthly average of 15 vehicles sourced directly from customers as "street buys". |  |  |
| Goal Start Date: | 8/1/2024 | Goal End Date: | 12/31/2024 |
| First Check-in Date: | 8/1/2024 | Performance Objective: | Developed improved process for getting a check to a customer same day. |
| Second Check-in Date: | 8/15/2024 | Performance Objective: | Train the process to a desginated sales person |
| Third Check-in Date: | 9/30/2024 | Performance Objective: | 5 Customer Purchases |
| Fourth Check-in Date: | 12/31/2024 | Performance Objective: | 50 total customer purchases. |
| How does your goal align with the dealers’ vision? | This aligns with our vision to improve absorption. We need to increase our overall pre-owned gross % and volume, to decrease our dependence on shrinking new vehicle grosses. |  |  |
| What are the potential benefits of achieving your goal? | Direct Purchase vehicles transacted 10 days quicker and with 25% more profitability than auction purchases at our dealership. Hitting this goal will lower our dependence on auctions, increase transactions, & increase our gross and volume potential. |  |  |
| What are the potential consequences if you don’t achieve your goal? | Not increasing direct purchases will lower our gross potential in our Used Department and make us more dependent on new vehicle sales. |  |  |
| Why is the goal important to you? | Leaning on auction purchases has yielded a roughly 11% Gross ROI over the course of the last year. Although profitable,it is marginal. Lowering our transaction price and increasing our gross ROI is essential to our business. We are not competive in $10k - $20k price band and being competitive in terms of avaiable units and price to market at that price point will make our dealership financially secure over the long-term. We can not do this effectively through auction purchases, so we need to find other means of sourcing. |  |  |
| Potential Obstacles | Developing a process of getting a check to a customer same day of purchase. This will require a major shift in our central accounting model. The store will need to be able to cut checks, or issue some sort of voucher (per the Carmax model) that can be easily and quickly cashed by the customer. |  |  |
| Potential Solutions | Training employees on what documents are needed to buy a vehicle. Training them how to communicate that with the customer. Bonusing the employees on successful transactions. |  |  |
| BOTTOM LINE! Financial Impact of Achieving Your Goal (expressed in dollars) | We estimate a $500 / pre-owned vehicle increase in transaction gross, and a 15 car increase in volume (from current average of 20) to 35 units per month. $500 * 35 units = $17,500 / month. |  |  |

What specific actions or steps will you take to accomplish your goal?  What will you do differently or improve? For each, be sure to include necessary resources, who is accountable, the measurable result, and dates.

| Specific action/step | Necessary resource(s) | Accountable person(s) | Expected result | Start, End, & CHeckpoint Dates |
| --- | --- | --- | --- | --- |
| Develop New Direct Purchase Process | Existing Customer Purchase Paperwork | Greg, Mariana, Kirk | New Direct Purchase Process | 7/1 to 7/5 |
| Develop Target list of vehicles for sales | Market Data on most purcahsed vehicles in the market | Greg, Kirk | Top 10 purchased vehicles in the market | 7/5 to 7/10 |
| Implement purchase bonus based on target vehicle, and new Direct Purchase Process | Bonus, target list, process docs | Greg, Kirk | 3 to 5 purchases in July | 7/15 to 8/1 |
| Review purchase porcess with GM and accounting | All purchased vehicles paperwork | Gary, Greg, Kirk, Mariana | Good and bad points of the program, and adjustments. | 8/1 to 8/5 |
| Review purchase porcess with GM and accounting | All purchased vehicles paperwork | Gary, Greg, Kirk, Mariana | Good and bad points of the program, and adjustments. | 9/2 to 9/5 |
| Review purchase porcess with GM and accounting | All purchased vehicles paperwork | Gary, Greg, Kirk, Mariana | Good and bad points of the program, and adjustments. | 10/1 to 10/4 |
| Review purchase porcess with GM and accounting | All purchased vehicles paperwork | Gary, Greg, Kirk, Mariana | Good and bad points of the program, and adjustments. | 1/2 to 1/5 |

As you work toward your goal, it’s important to have interim check points with specific, measurable objectives so your team can hold themselves accountable. If everyone knows the goal and objectives, you don’t have to spend your valuable time micromanaging.

Once you’ve accomplished your goal, added or adjusted policies, procedures, and behaviors, now what? How will you ensure you and your staff do not fall back into the previous habits that produced poor results? Be specific.

The bonus structure that comes out of the process should encourage continued results. Added to this will be semi-monthly tracking of direct purchases taken in, turn rate, and gross ROI. Tracking and displaying the improved ROI along with the correct reminder to the GMs will encourage continued performance.

Describe any planning or implementation meetings conducted as part of development of your plan.

Developing a New Direct Purchases process will be the first step in the process. It will be important to determine how quickly and in what circustances we will issue a check. We have attempted this before to limited results, but there is increased urgency now to source vehicles so that should help to focus the staff on getting it right.

| Sponsor Signature: |  |
| --- | --- |