| Name | TREY DRESSLER | Class # | N435 |
| --- | --- | --- | --- |
| Dealership | MERCEDES BENZ OF BIRMINGAM | Date | 6/19/2024 |

| Current Situation or Challenge to be Addressed: | Transition incoming phone calls and internet lead management from BDC agents to salespeople on the showroom floor, achieving faster response times and higher lead conversion rates within 3 months. |  |  |
| --- | --- | --- | --- |
| Current Performance Level (include specific measure): | 11% Closng ratio utilitizing 2 person BDC |  |  |
| Goal (what do you want to achieve?) | 13 to 15% closing ratio utilitizng 1 BDC Agent assisting floor sales consultants |  |  |
| Goal Performance Level (include specific measure) | Document current average lead response time, conversion rate, and customer satisfaction scores. |  |  |
| Goal Start Date: | 7/1/2024 | Goal End Date: | 9/30/2024 |
| First Check-in Date: | 7/15/2024 | Performance Objective: | Analyze current lead management processes, identify metrics, and determine areas for improvement. |
| Second Check-in Date: | 8/15/2024 | Performance Objective: | Evalaute Current Performance Provide 3rd Party Training for Call Scripts and Texting/ Utilizing AI |
| Third Check-in Date: | 9/16/2024 | Performance Objective: | Evaluate the effectiveness of the transition and process implimented by 3rd Party Training. Identify areas of opportunity for improvement |
| Fourth Check-in Date: | 9/30/2024 | Performance Objective: | Increase the lead conversion rate by 4 percentage points. |
| How does your goal align with the dealers’ vision? | The goal is to provide our clients with more professional experience on a faster timeline which should help to differentiate our store from what they have experienced elsewhere. "We are a Luxury retailer, not a car dealer, our success will be measured in that light" |  |  |
| What are the potential benefits of achieving your goal? | The dealership can ensure a smooth and effective transition from BDC agents to salespeople managing incoming phone calls and internet leads, resulting in improved efficiency and customer satisfaction. |  |  |
| What are the potential consequences if you don’t achieve your goal? | Less online bussiness, Loss of market share. |  |  |
| Why is the goal important to you? | Salespeople handling leads directly can provide a seamless and personalized customer experience. Customers often appreciate talking to knowledgeable staff immediately rather than being routed through multiple channels. We also think It ensures consistency and communication from the initial inquiry to the final sale, building trust and rapport with potential buyers. |  |  |
| Potential Obstacles | Some Salespeople may lack the necessary skills for handling incoming calls and internet leads effectively, they may also may resist the new responsibilities, preferring the existing system. |  |  |
| Potential Solutions | Hold informational sessions to explain the reasons for the change, explain the how both the client and the sales consultants will benefit from the change. Schedule extensive in-house as well as third-party training to better skills and responses. |  |  |
| BOTTOM LINE! Financial Impact of Achieving Your Goal (expressed in dollars) | $80 TO $90K GROSS PER MONTHS. |  |  |

What specific actions or steps will you take to accomplish your goal?  What will you do differently or improve? For each, be sure to include necessary resources, who is accountable, the measurable result, and dates.

| Specific action/step | Necessary resource(s) | Accountable person(s) | Expected result | Start, End, & CHeckpoint Dates |
| --- | --- | --- | --- | --- |
| Analyze current lead handling by BDC agents | Access to CRM data | Sales Manager | A report detailing current performance metrics. | 06/20/2024 07/01/2024 |
| Document lead response times, conversion rates, and customer satisfaction scores | Time for meetings and analysis | BDC Agent | Improve lead handling processes based on feedback. | 06/20/2024 07/01/2024 |
| Develop manuals, scripts, and role-playing exercises | Training materials and CRM access/ Third Party Trainers | Sales Manager | Completion of training by all salespeople | 07/02/2024 07/16/2024 |
| Conduct training for salespeople on lead handling | Trainers or external training providers | Sales Manager/ Outside trainers | Completion of training by all salespeople | 07/02/2024 08/15/2024 |
| Implement CRM and Call Routing Systems | IT staff for setup and testing and CRM provider support | IT Manager Sales Manager | Leads routed to the floor within 5 minutes and calls answered within 30 seconds. | 07/17/2024 07/30/2024 |
| Provide Ongoing Support and Monitoring | Time for meetings and access to performance data | Sales manager and CRM adminstrator | Improvement in lead handling performance metrics. | 08/08/2024 09/30/2024 |
| Celebrate Milestones and Communicate Results | Budget for recognition event | Sales Manager | Successful internal communication of the positive outcomes. | UNDETERMINED |

As you work toward your goal, it’s important to have interim check points with specific, measurable objectives so your team can hold themselves accountable. If everyone knows the goal and objectives, you don’t have to spend your valuable time micromanaging.

Once you’ve accomplished your goal, added or adjusted policies, procedures, and behaviors, now what? How will you ensure you and your staff do not fall back into the previous habits that produced poor results? Be specific.

Once this transition has been made, there is no turning back. The personal changes that we come as a byproduct of this change will effectively "burn the boats" so we will not be able to simpy flip a switch and go back. Theses changes in processess will have no choice but to be successful.

Describe any planning or implementation meetings conducted as part of development of your plan.

Extensive converation/meeting with Sales Management Team over lead distribution and opporunites to close gaps in current Phone and Internet Procedures while improving overall client experience.

| Sponsor Signature: |  |
| --- | --- |