| Name | DAIN WHYTE | Class # | N436 |
| --- | --- | --- | --- |
| Dealership | FRED HAAS NISSAN | Date | 4/30/2024 |

| Current Situation or Challenge to be Addressed: | Pre-owned inventory turn rate |  |  |
| --- | --- | --- | --- |
| Current Performance Level (include specific measure): | Currently at 7.4 |  |  |
| Goal (what do you want to achieve?) | Want to be at NADA Guide (12) |  |  |
| Goal Performance Level (include specific measure) | Reduce time to frontline ready from 10-12 days to 3 days |  |  |
| Goal Start Date: | 5/1/2024 | Goal End Date: | 8/31/2024 |
| First Check-in Date: | 5/31/2024 | Performance Objective: | Try to get to 8 |
| Second Check-in Date: | 6/30/2024 | Performance Objective: | Try to get to 9.5 |
| Third Check-in Date: | 7/31/2024 | Performance Objective: | Try to get to 10.5 |
| Fourth Check-in Date: | 8/31/2024 | Performance Objective: | Want to be at 12 |
| How does your goal align with the dealers’ vision? | We all have the same goal |  |  |
| What are the potential benefits of achieving your goal? | Not take a lost because the unit is aging |  |  |
| What are the potential consequences if you don’t achieve your goal? | Lose money |  |  |
| Why is the goal important to you? | To run a healthy store and always have updated inventory available for our customers |  |  |
| Potential Obstacles | Getting the units front line ready |  |  |
| Potential Solutions | Work closer with the used make ready dept to make sure they get the units ready quickly |  |  |
| BOTTOM LINE! Financial Impact of Achieving Your Goal (expressed in dollars) | $100,000 per month |  |  |

What specific actions or steps will you take to accomplish your goal?  What will you do differently or improve? For each, be sure to include necessary resources, who is accountable, the measurable result, and dates.

| Specific action/step | Necessary resource(s) | Accountable person(s) | Expected result | Start, End, & CHeckpoint Dates |
| --- | --- | --- | --- | --- |
| PURCHASE FRESH INVENTORY | USE ALL BUYING PLATFORMS | BUYER | EXTRA 20 UNITS AT THE RIGHT VALUE | 05/01/24, AUG 30, 2024 END OF MAY31, 2024 END OF JUN 30, 2024 END OF JULY 31, 2024 AND AUG 30,2024 |
| MAKE SURE THE INVENTORY PURCHASE AND TRADE INS ARE MADE READY FOR FRONT LINE | MAKE READY DEPT | MAKE READY MANAGER AND USED VEHICLE MANAGER | HAVING THE UNIT READY IN LESS THAN 3 DAYS | 05/01/24, AUG 30, 2024 END OF MAY31, 2024 END OF JUN 30, 2024 END OF JULY 31, 2024 AND AUG 30,2024 |
| PRICE THE MARKET NO MATTER THE COST OF THE UNIT | ADVERTISING AGENCY | MARKETING MANAGER | MAKE SURE THE UNITS ARE ADVERTISED AGRESSIVELY THE FIRST TIME | 05/01/24, AUG 30, 2024 END OF MAY31, 2024 END OF JUN 30, 2024 END OF JULY 31, 2024 AND AUG 30,2024 |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |

As you work toward your goal, it’s important to have interim check points with specific, measurable objectives so your team can hold themselves accountable. If everyone knows the goal and objectives, you don’t have to spend your valuable time micromanaging.

Once you’ve accomplished your goal, added or adjusted policies, procedures, and behaviors, now what? How will you ensure you and your staff do not fall back into the previous habits that produced poor results? Be specific.

HAVE WEEKLY MEETINGS WITH ALL DEPARTMENT HEADS AND HOLD THEM ACCOUNTABLE

Describe any planning or implementation meetings conducted as part of development of your plan.

EVERY THURSDAY WE HAVE A MEETING WITH DEPARTMENT MANAGER TO DISCUSS ANY PROBLEMS, NEW PROJECTS AND IDEAS TO IMPROVE THE DAILY OPERATIONS.

| Sponsor Signature: |  |
| --- | --- |