| Name | Jodi Baynes | Class # | N436 |
| --- | --- | --- | --- |
| Dealership | MTN View Nissan | Date | 6/1/2024 |

| Current Situation or Challenge to be Addressed: | Trade-in days to lot |  |  |
| --- | --- | --- | --- |
| Current Performance Level (include specific measure): | 7 day turn around |  |  |
| Goal (what do you want to achieve?) | 3 day turn around |  |  |
| Goal Performance Level (include specific measure) | Decrease turn around by 4 days |  |  |
| Goal Start Date: | immediate | Goal End Date: | 8/31/2024 |
| First Check-in Date: | 6/30/2024 | Performance Objective: | 6 day turn around |
| Second Check-in Date: | 7/15/2024 | Performance Objective: | 5 day turn around |
| Third Check-in Date: | 7/31/2024 | Performance Objective: | 4 day turn around |
| Fourth Check-in Date: | 8/15/2024 | Performance Objective: | 3 day turn around |
| How does your goal align with the dealers’ vision? | Consistency in processes |  |  |
| What are the potential benefits of achieving your goal? | Units available for sale sooner |  |  |
| What are the potential consequences if you don’t achieve your goal? | Missed sales |  |  |
| Why is the goal important to you? | Make units available for resale and not aging in service |  |  |
| Potential Obstacles | Service behind from other units |  |  |
| Potential Solutions | Sales manager communicates with Service manager about incoming PDI's and Purchased units so the department and plan ahead |  |  |
| BOTTOM LINE! Financial Impact of Achieving Your Goal (expressed in dollars) | This will save money on units aging, floorplan interest (currently 6.43), fresh trade appeal to customers VIA advertising. |  |  |

What specific actions or steps will you take to accomplish your goal?  What will you do differently or improve? For each, be sure to include necessary resources, who is accountable, the measurable result, and dates.

| Specific action/step | Necessary resource(s) | Accountable person(s) | Expected result | Start, End, & CHeckpoint Dates |
| --- | --- | --- | --- | --- |
| SRV employee Assist with appraisals | Diagnostic equipment | SLS Manager SRV Manager | SRV mgr has dedicated SRV employee | immediate |
| SRV employee Assist with appraisals | Diagnostic equipment | SLS Manager SRV Manager | 6 days | 06/30/2024 |
| SRV employee Assist with appraisals | Diagnostic equipment | SLS Manager SRV Manager | 5 days | 07/15/2024 |
| SRV employee Assist with appraisals | Diagnostic equipment | SLS Manager SRV Manager | 4 days | 07/31/2024 |
| SRV employee Assist with appraisals | Diagnostic equipment | SLS Manager SRV Manager | 3 days | 08/31/2024 |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |

As you work toward your goal, it’s important to have interim check points with specific, measurable objectives so your team can hold themselves accountable. If everyone knows the goal and objectives, you don’t have to spend your valuable time micromanaging.

Once you’ve accomplished your goal, added or adjusted policies, procedures, and behaviors, now what? How will you ensure you and your staff do not fall back into the previous habits that produced poor results? Be specific.

We have a spreadsheet that will be monitored and bonuses given to dedicated service employee if days stay at 3 for additional incentive.

Describe any planning or implementation meetings conducted as part of development of your plan.

Met with Service manager and GSM and together came up with the plan of action to implement this change

| Sponsor Signature: |  |
| --- | --- |