| Name | Ryan Snel | Class # | N439 |
| --- | --- | --- | --- |
| Dealership | OpenRoad Lexus Richmond | Date | 8/15/2024 |

| Current Situation or Challenge to be Addressed: | Internet Lead Conversion is abismal. Needs to improve immediately. |  |  |
| --- | --- | --- | --- |
| Current Performance Level (include specific measure): | June conversion rate is 10% for new car department and 7% for used car department. |  |  |
| Goal (what do you want to achieve?) | Improve overall process, increase appointment settting and closing metrics. |  |  |
| Goal Performance Level (include specific measure) | Looking for a minimum 15% close ratio. |  |  |
| Goal Start Date: | 9/1/2024 | Goal End Date: | 12/31/2024 |
| First Check-in Date: | 9/15/2024 | Performance Objective: | Won't see immediate results. August 1st we implemented a requirement of 50% video replies to customer leads. Right now we are tracking manually, but are inquiring about integrated software available |
| Second Check-in Date: | 10/1/2024 | Performance Objective: | 10% close ratio for both new and used. We are still developing the process. |
| Third Check-in Date: | 10/31/2024 | Performance Objective: | 12% close should be attainable. At this point we will need to have added two new memebers to the Internet Department. |
| Fourth Check-in Date: | 11/31/2024 | Performance Objective: | 15% close ratio consistently. Using new tools at our disposal. |
| How does your goal align with the dealers’ vision? | Covid glory days are over, it's back to business as usual. We have been re-educating the team on how to sell and not just be order takers. Reevaluate current processes and update them, and improve on existing training. |  |  |
| What are the potential benefits of achieving your goal? | YTD we've received 1166 total Internet Leads with a combined clos ratio of 8% means we have sold a total of 93 cars through the first 6 months. If we extrapolate the leads at a 15% close ratio that gives us an additional 82 deals with an average of $5,500 per deal = $451,000 additional GP for the store. |  |  |
| What are the potential consequences if you don’t achieve your goal? | Lost/wasted revenue. It is getting harder to generate customers these days. We need to maximize on the existing leads we have and squeeze all revenue we ca. |  |  |
| Why is the goal important to you? | I try to create efficiencies where I can. Reduce bottlenecks and increase profitability. Our current close ratio is well below acceptable. |  |  |
| Potential Obstacles | Not enough manpower to generate videas and processes we need in order to be successful. |  |  |
| Potential Solutions | We need to utilize new technologies so we don't have to rely so heavily on human capacity. |  |  |
| BOTTOM LINE! Financial Impact of Achieving Your Goal (expressed in dollars) | With a YTD Operating Profit ratio of 50% for New and Used Departments this would bring in an additional $225,500 in DOP. I like money! |  |  |

What specific actions or steps will you take to accomplish your goal?  What will you do differently or improve? For each, be sure to include necessary resources, who is accountable, the measurable result, and dates.

| Specific action/step | Necessary resource(s) | Accountable person(s) | Expected result | Start, End, & CHeckpoint Dates |
| --- | --- | --- | --- | --- |
| Audit current process, where are the pitfalls | Current SOP, and testing (secret shop campaign) | Internet team, myself and Sales Manager | Determine current bottlenecks | August 30/31 |
| Eliminate the identified bottlenecks | Results from secret shop | same | Increase efficiencies and create smoother customer experience | September 15th-30th |
| Create a video library at specific touch points, should be standardized | Video examples from other stores and online resources | Marketing Team, myself and Sales Managers | Will have a selection of videos pre-loaded to create efficiencies for Internet Team to use | October 1st - ongoing |
| Grow current team to expand on current operations. | Job Posting resources | HR and Sales Managers to recruit, train and onboard | Start with adding two new members, and work from there | October 1st to December 31st |
| Monthly reviews with team and establish kpi's and 'increased' monthly targets | Established best practices and kpi's | Sales Managers and Internet Team | Continued accountability should help increase closing ratio | October 1st - ongoing |
| Review, repeat and twek | Continue to track with established metrics | Myself, Sales Managers and Internet Team | Do we need to increase incentives or make personel changes. | October 1st - ongoing |
| Celebrate in our achievements | Champagne? | Me | Drink champagne and tell everyone how I increased profitability | December 30th - December 31st |

As you work toward your goal, it’s important to have interim check points with specific, measurable objectives so your team can hold themselves accountable. If everyone knows the goal and objectives, you don’t have to spend your valuable time micromanaging.

Once you’ve accomplished your goal, added or adjusted policies, procedures, and behaviors, now what? How will you ensure you and your staff do not fall back into the previous habits that produced poor results? Be specific.

We will create an Internet Team Champion once we have established who is capable of leading the team. That Champion will be part of our bi-monthly manager meetings. Quick updates and weekly tracking of the important KPI's. There will be a small bonus componant to the Champion's pay plan for continued incentive.

Describe any planning or implementation meetings conducted as part of development of your plan.

There will be established 'goal posts' once the process is underway. The Sales Managers will do cross-training on managing the Internet Team once the process is established, likely every 6 months. Other meetings will be as per above.

| Sponsor Signature: |  |
| --- | --- |