| Name | Matthew Spitzer | Class # | N440 |
| --- | --- | --- | --- |
| Dealership | Ron DuPratt Ford | Date | 6/1/2024 |

| Current Situation or Challenge to be Addressed: | Our recon time is too slow to keep up with used car sales |  |  |
| --- | --- | --- | --- |
| Current Performance Level (include specific measure): | Avg of 17-18 ncars donew per week with acg of 15 day recon time |  |  |
| Goal (what do you want to achieve?) | 7 day recon time max |  |  |
| Goal Performance Level (include specific measure) | Avg time of cars time to line |  |  |
| Goal Start Date: | 6/1/2024 | Goal End Date: | 9/30/2024 |
| First Check-in Date: | 7/1/2024 | Performance Objective: | 13 days |
| Second Check-in Date: | 8/1/2024 | Performance Objective: | 11 days |
| Third Check-in Date: | 9/1/2024 | Performance Objective: | 9 days |
| Fourth Check-in Date: | 10/1/2024 | Performance Objective: | 7 days |
| How does your goal align with the dealers’ vision? | Growing the used car department as we have been trying to requires faster recon |  |  |
| What are the potential benefits of achieving your goal? | More used car sales with more gross |  |  |
| What are the potential consequences if you don’t achieve your goal? | Stunting growth of used car sales |  |  |
| Why is the goal important to you? | More used cars reconed is also more service revenue from gurenteed customers. |  |  |
| Potential Obstacles | Tech talent, sense of urgency from service employees |  |  |
| Potential Solutions | Bonuses for lower avg recon time, explaination of the benefits over all |  |  |
| BOTTOM LINE! Financial Impact of Achieving Your Goal (expressed in dollars) | Quicker recon turn allows more gross to be captured quicker in each used car |  |  |

What specific actions or steps will you take to accomplish your goal?  What will you do differently or improve? For each, be sure to include necessary resources, who is accountable, the measurable result, and dates.

| Specific action/step | Necessary resource(s) | Accountable person(s) | Expected result | Start, End, & CHeckpoint Dates |
| --- | --- | --- | --- | --- |
| Hire more techs dedicated to used cars | Time to interview and hire | Service manager | More cars worked on at one time | 6/1-9/30 |
| Rearrange techs to have enough talent working on used cars | None | Service manager | Less come backs on used cars, more efficent work | 6/1-9/30 |
| Explore alternative schedules for more hours available throughout the week | None | Service manager | Used cars worked on Monday-Saturday, no sitting cars over weekend | 6/1-9/30 |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |

As you work toward your goal, it’s important to have interim check points with specific, measurable objectives so your team can hold themselves accountable. If everyone knows the goal and objectives, you don’t have to spend your valuable time micromanaging.

Once you’ve accomplished your goal, added or adjusted policies, procedures, and behaviors, now what? How will you ensure you and your staff do not fall back into the previous habits that produced poor results? Be specific.

Continue to measure time to line and keep pushing to reduce it with new ideas and solutions

Describe any planning or implementation meetings conducted as part of development of your plan.

Weekly used car meetings already happen to discuss with sales pain points and find solutions

| Sponsor Signature: |  |
| --- | --- |