| Name | Marsha Abbot | Class # | Click or tap here to enter text. |
| --- | --- | --- | --- |
| Dealership | K. Neal Truck and Bus | Date | 9/23/2024 |

| Current Situation or Challenge to be Addressed: | Create a process to control old Used inventory |  |  |
| --- | --- | --- | --- |
| Current Performance Level (include specific measure): | We have several old inventory units that we have had for more than 180 days |  |  |
| Goal (what do you want to achieve?) | Create a process by which units are moved out of the system by 180 days |  |  |
| Goal Performance Level (include specific measure) | Currently very poor |  |  |
| Goal Start Date: | 10/1/2024 | Goal End Date: | 12/31/2024 |
| First Check-in Date: | 10/15/2024 | Performance Objective: | Old inventory on its way out, all new inventory evaluated, pricing and timing |
| Second Check-in Date: | 11/1/2024 | Performance Objective: | Plan around any inventory that is aging, all old inventory gone |
| Third Check-in Date: | 11/15/2024 | Performance Objective: | SOP in place and plan working on any aging inventory |
| Fourth Check-in Date: | 12/16/2024 | Performance Objective: | All inventory under 180 days and all processes are being adhered to |
| How does your goal align with the dealers’ vision? | This goal aligns with the dealers vision of taking care of the customer, taking care of the associate and bottom line. This goal ensures that customers have relevant pieces of inventory to purchase, it also ensures that the inventory we have is priced right and our sales people have an opportunity to sell it at a market driven price. |  |  |
| What are the potential benefits of achieving your goal? | The potental benefits are ; sellable invetory, opportunity to play in the market with relevant inventory price driven by the market. |  |  |
| What are the potential consequences if you don’t achieve your goal? | If we do not achieve our goal our used department will continue to loose money, inventory will age and we will not be succesful |  |  |
| Why is the goal important to you? | This goal is important to me because our used department has not done well in years and we could make a huge difference on this side of the business |  |  |
| Potential Obstacles | Push back from dealer principal or current staff on wholesaling the units that are in inventory |  |  |
| Potential Solutions | Seek other options or suggestions, involve others in this plannign process |  |  |
| BOTTOM LINE! Financial Impact of Achieving Your Goal (expressed in dollars) | Current financial impact with the units we have in inventory and their age would be over 9.2 million |  |  |

What specific actions or steps will you take to accomplish your goal?  What will you do differently or improve? For each, be sure to include necessary resources, who is accountable, the measurable result, and dates.

| Specific action/step | Necessary resource(s) | Accountable person(s) | Expected result | Start, End, & CHeckpoint Dates |
| --- | --- | --- | --- | --- |
| Identify the impact of the aged inventory. 10 units in inventory over 180 days old. Financial impact of over 6 million dollars | Inventory list | Used truck manager, General Manager | For everyone to understand the reason and the impact of having aged inventory | Start 10/15/24 End 10/20/24 |
| Evaluate the current market and understand it | Internet and resources like Rig Dig, and auction websites | Used Truck Manager | For the Used Truck Manager to have a throrough understanding of the market in our area | 10/22/24 - 10/30/24 |
| Evaluate pricing on current inventory and reprice as market allows | Inventory list and knowledge of current market | Used truck Manager , General Manager | Units that need to be repriced identified | 11/1/24 - 11/15/24 |
| Evaluated marketing of the current units in inventory | Marking information and know how | Used Truck Manager, Marketing manager | New marketing format for all used trucks to be followed | 11/15/24 - 11/30/24 |
| Complete process of how used inventory will be dealt with in the future | All knowledge collected at this point | Used Truck Manager, General Manager | Complete process for Used Truck Department | 12/1/-12/15/24 |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |

As you work toward your goal, it’s important to have interim check points with specific, measurable objectives so your team can hold themselves accountable. If everyone knows the goal and objectives, you don’t have to spend your valuable time micromanaging.

Once you’ve accomplished your goal, added or adjusted policies, procedures, and behaviors, now what? How will you ensure you and your staff do not fall back into the previous habits that produced poor results? Be specific.

Consistent weekly follow up meetings to discuss, and tweek policies as needed

Describe any planning or implementation meetings conducted as part of development of your plan.

Weekly follow up meetings, and every other week pricing meetings

| Sponsor Signature: |  |
| --- | --- |