| Name | Michael Crawford | Class # | A051 |
| --- | --- | --- | --- |
| Dealership | Ohio Peterbilt | Date | 9/27/2024 |

| Current Situation or Challenge to be Addressed: | Used Truck inventory is currently at 4.5 months supply and doesn’t align with the company goal of 2.5 months. |  |  |
| --- | --- | --- | --- |
| Current Performance Level (include specific measure): | Used Truck Invenory is $9,543,821/ Monthly sales of $2,098,137/4.55 months supply |  |  |
| Goal (what do you want to achieve?) | I will reduce my used inventory months' supply on hand from 4.55 months to 2.5 months within 6 months. |  |  |
| Goal Performance Level (include specific measure) | Goal $5,245,343 used truck inventory/2.5 months supply |  |  |
| Goal Start Date: | 10/1/2024 | Goal End Date: | 4/1/2025 |
| First Check-in Date: | 11/15/2024 | Performance Objective: | Used inventory $8,469,202 /4.0 months supply |
| Second Check-in Date: | 12/31/2024 | Performance Objective: | Used Inventory $7,394,582/3.5 months supply |
| Third Check-in Date: | 2/15/2025 | Performance Objective: | Used Inventory $6,319,962/3.0 months supply |
| Fourth Check-in Date: | 4/1/2025 | Performance Objective: | Used Inventory $5,245,342/2.5 months supply |
| How does your goal align with the dealers’ vision? | This goal aligns with our company's vision to be the company that best understands and satisfies the product, service and needs of our customers by insuring we have the right used inventory at the right time and increase customer satisfaction. |  |  |
| What are the potential benefits of achieving your goal? | Achieving the goal will reduce expenses(flooring costs, increase Gross profit, Free up stale capital so we can better invest in more important parts of the business that increases overall customer satisfaction. |  |  |
| What are the potential consequences if you don’t achieve your goal? | If we don’t acieve our goal flooring costs will remain elevated which will lower our profitibility, employee morale, investment in future projects and in turn, lower over-all customer satisfaction. |  |  |
| Why is the goal important to you? | This goal is important as it aligns with our over-all company goal of being the best dealership group in the country. Our desire to have the highest customer satisfaction and having the right size inventory supports this goal. |  |  |
| Potential Obstacles | Used Truck Values continue to fall, Salespeople motivation to sell at a loss, ownership reluctancy to take lossesm, New Truck Sales Dept. push-back for trade-in values |  |  |
| Potential Solutions | Re-evaluate inventory every 60 days and price to market conditions, re0evalueate pay plan and increase incentives to sell aging used inventory, highlight and explain plan in full to ownership emphasizing paybcack and future performance, ensure we get the best and correct values on used equipment the first time using multiple wholesalers, industry resources and aution reports. |  |  |
| BOTTOM LINE! Financial Impact of Achieving Your Goal (expressed in dollars) | The short-term impact on the used truck department will be significant as the plan will result in $2,000,000 due to inventory being overvalued. But, long term the Used Truck department will become profitable again. In the next 12 months there will be 1.8M increase in gross profit and $275,000 reduction in floor plan expenses. |  |  |

What specific actions or steps will you take to accomplish your goal?  What will you do differently or improve? For each, be sure to include necessary resources, who is accountable, the measurable result, and dates.

| Specific action/step | Necessary resource(s) | Accountable person(s) | Expected result | Start, End, & CHeckpoint Dates |
| --- | --- | --- | --- | --- |
| Complete market analysis and inventory audit to identify high value stock for reduction | Inventory list, Auction report, Industry resources JD Powers Truck paper etc, wholesalers | Used Truck Manager | Reduction of $716,000 in used truck inventory | Start: Oct 1, 2024 End: Oct. 31, 2024 checkpoint: Oct. 15, 2024 |
| Implement dynamic pricing and launch marketing campaigns aimed at promoting aged used inventory | Values from above in New Inventory report, Marketing dept, Truck Paper, Websit and social media | Used Truck Manager and Marketing Manager | Further reduction of $716,000 in used truck inventory | Start Nov. 1, 2024 End: Nov. 30, 2024 checkpoint: Nov 15, 2024 |
| Evaluate sales performance and adjust strategies based on customer feedback | Sales analysis reports, up to dale list from step 1, Marketing dept | Used Truck Manager, Accounting dept and Marketing Manager | Further reduction of $716,000 in used truck inventory | Start: Dec. 1, 2024 End: Dec. 31, 2024 checkpoint Dec. 15, 2024 |
| Continue promotions and assess sales strategies to target an additional inventory reduction | Sales analysis reports, up to dale list from step 1, Marketing dept Truckpaper, social media campaings and website promotion | Used Truck Manager, Marketing Manager, Accounting dept | Further reduction of $716,000 in used truck inventory | Start: Jan 1, 2025 End: Jan 31, 2025 checkpoint: Jan. 15, 2025 |
| Focus on trade-ins and partnerships with other dealers/wholesales to achieve further reductions | Wholesalers and contactos at other dealerships, sales analysis report, up-to date list from step 1 | Used Truck Manager and Wholesale manager | Further reduction of $716,000 in used truck inventory | Start: Feb. 1, 2025 End: Feb. 28, 2025 checkpoint Feb. 15, 2025 |
| Review Over-all inventory reduction progress and make necessary adjustments to reach goal | Sales analysis reports, up to dale list from step 1, Marketing dept Truckpaper, social media campaings and website promotion | Used Truck Manager and Marketing Manager | Further reduction of $716,000 in used truck inventory | Start: Mar. 1, 2025 End: Apr. 1, 2025 checkpoint Mar. 15, 2025 |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |

As you work toward your goal, it’s important to have interim check points with specific, measurable objectives so your team can hold themselves accountable. If everyone knows the goal and objectives, you don’t have to spend your valuable time micromanaging.

Once you’ve accomplished your goal, added or adjusted policies, procedures, and behaviors, now what? How will you ensure you and your staff do not fall back into the previous habits that produced poor results? Be specific.

New policies a will be implemented that states any truck over 60 days old gets re-priced to market and after 120 days must be disosed of through wholesalers or auctions. Also, trade-in responsibility and exposure/losses will be shared with the new truck department equally after 120 day disposal.

Describe any planning or implementation meetings conducted as part of development of your plan.

There will be a kick-off meeting with Used truck Manager, Controller, Marketing Manager and dealership VP to discuss and layout the plan, monthly sales meetings with the sales team and Used Truck manager, weekly Marketing manager and Used Truck Manager and mid month update meeting with Used Truck Manager and delaership VP.

| Sponsor Signature: |  |
| --- | --- |