| Name | Troy Powers | Class # | ATD 051 |
| --- | --- | --- | --- |
| Dealership | Rihm Kenworth | Date | 10/18/2024 |

| Current Situation or Challenge to be Addressed: | Reduce Expenses in truck reconditioning |  |  |
| --- | --- | --- | --- |
| Current Performance Level (include specific measure): | YTD Spend is $122,526, anticipated annual cost is $163,368 |  |  |
| Goal (what do you want to achieve?) | Reduce this expense by 30%. |  |  |
| Goal Performance Level (include specific measure) | $114,357 annualized expense in 2025 |  |  |
| Goal Start Date: | 1/1/2025 | Goal End Date: | 6/30/2025 |
| First Check-in Date: | 2/1/2025 | Performance Objective: | Staff hired and handling 6 used trucks per month |
| Second Check-in Date: | 3/1/2025 | Performance Objective: | Internal recon team is handling 12 trucks per month |
| Third Check-in Date: | 4/1/2025 | Performance Objective: | Team needs to be processing 18 trucks per month at this point |
| Fourth Check-in Date: | 5/1/2025 | Performance Objective: | Team needs to be handlng 25 trucks per month |
| How does your goal align with the dealers’ vision? | It drives a reduction in expenses and this is one of our goals to help us achieve the needed profitability for our dealership. |  |  |
| What are the potential benefits of achieving your goal? | Reduced expense, developmental area for new employees, more quality control in our finished product, and increased control on the timeliness of trucks being ready to sell. |  |  |
| What are the potential consequences if you don’t achieve your goal? | Conitnued over spending, continued risk of delays in getting trucks front line ready. |  |  |
| Why is the goal important to you? | This goal alingns with our values of being effective and efficient as a company. |  |  |
| Potential Obstacles | Space constraints, hiring staff, and training how we want the job done. |  |  |
| Potential Solutions | Repurposing of bay that payloader is parked in, recruitment in high school career fair, and appropriate training. |  |  |
| BOTTOM LINE! Financial Impact of Achieving Your Goal (expressed in dollars) | Savings estimated at $49,010 in first year. (Total saving of $154 per truck we sell) |  |  |

What specific actions or steps will you take to accomplish your goal?  What will you do differently or improve? For each, be sure to include necessary resources, who is accountable, the measurable result, and dates.

| Specific action/step | Necessary resource(s) | Accountable person(s) | Expected result | Start, End, & CHeckpoint Dates |
| --- | --- | --- | --- | --- |
| Repurpose bay for detailing | 40 hours of time to clean, dispose of junk, and put up benches | Service Manager | Room ready to use as detail area | Start Dec 1, 2024, complete Dec 31, 2024. Check in daily |
| Hire two part time people to do recon job | Recruiting team | HR Manager | Successful hire of staff | Start Nov 1, 2024, hire by Nov 30, 2024 |
| Train Staff | Body Shop foreman | Service Manager | Staff trained and capable of successfully doing the job | Dec 1, 2024 and trained by Dec 31, 2024 |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |

As you work toward your goal, it’s important to have interim check points with specific, measurable objectives so your team can hold themselves accountable. If everyone knows the goal and objectives, you don’t have to spend your valuable time micromanaging.

Once you’ve accomplished your goal, added or adjusted policies, procedures, and behaviors, now what? How will you ensure you and your staff do not fall back into the previous habits that produced poor results? Be specific.

Monitor the number of used trucks that are getting reconditioned offsite. Analyze the reason why when this happens and adjust staff to accommodate work load as need emerges.

Describe any planning or implementation meetings conducted as part of development of your plan.

Meeting with Service, Body Shop, Used Truck, and Sales Director to define expectations and determine how much lead time must be given to new team.

| Sponsor Signature: |  |
| --- | --- |