### Departmental Action Plan for Financial Recovery

Overall Objective:
To eliminate our annual loss and achieve sustainable financial growth by optimizing revenue streams, reducing costs, and improving operational efficiency. The goal is to improve South Bends absorption by 10% within 12–18 months (June 2026) and position the store for long-term success.

### Specific Desired Results:

- Revenue Growth: Increase annual revenue by 10% before Jan 1 2026 through new market expansion, product diversification, and improved sales strategies.

- Cost Reduction: Achieve a 5-10% reduction in operational and overhead costs through efficiency improvements in service and Bodyshop, renegotiated contracts with our vendors, and strategic outsourcing doing what we deem best for business.

- Improved Cash Flow: Enhance cash flow by improving receivables collection, optimizing inventory management, and reducing unnecessary expenditures, targeting a 20% improvement in working capital within 12 months.

- Employee Performance: Align employee KPIs with organizational financial goals, holding department managers accountable, improving productivity by 10% and increasing employee engagement and retention.

- Strategic Partnerships: Establish at least 3 to 5 new customers in Service and Bodyshop that contribute directly to gross profit and operational efficiencies.

- Positive Cash Flow: Achieve a break-even or positive cash flow position within the first 6 months.

### 1. Root Cause Analysis

- Action: Conduct a deep financial audit to identify major revenue losses, cost inefficiencies, and operational bottlenecks.

- Focus: Financial review, departmental performance, competitive landscape, and customer feedback.

- Managers working in the business – Hire an asst parts manager for Dave so he can get out and grow the business.  A 3% increase in our yoy #s will bring in an additional $115K in SB alone and the cost will be split between both stores.

- We also need to review the Bodyshop cost during the next budget period.  I have a plan to cut cost.

- Timeline: completed by March 1, 2025

### 2. Revenue Growth

- Actions:

  - Explore new markets and customer segments.

- Diversify product/service offerings. – bring in more Liberty products!

- Implement stronger cross-selling, upselling, and subscription models.

- Conduct a pricing audit and optimize prices. Stay competitive in our market

- Timeline: 3-6 months.

- Desired Results: 10% increase in revenue showing December 31, 2025.

### 3. Cash Flow & Funding

- Actions:

  - Tighten receivables collection, optimize inventory, and forecast cash flow more effectively.

  - Explore debt financing, equity investment, or government grants for capital infusion.

  - Implement lean processes to eliminate inefficiencies.

  - Automate routine tasks and renegotiate vendor contracts.

- Timeline: 1-3 months.

- Desired Results: 20% improvement in working capital within 6 months.

### 4. Talent & Culture

- Actions:

  - Align employee goals with financial targets.

  - Enhance talent retention programs and employee development initiatives.

  - Foster a high-performance, cost-conscious culture.

- Timeline: Ongoing.

- Desired Results: 10% increase in employee productivity and 15% improvement in employee retention.

### 6. Monitoring & Iteration

- Actions:

  - Establish KPIs, dashboards, and monthly performance reports.

  - Conduct quarterly reviews and adjust strategies as needed based on results.

  - Weekly management meetings

- Timeline: Ongoing.

- Desired Results: Transparent tracking of progress, with course corrections implemented to stay on track for financial recovery.

### Conclusion:

This action plan aims to drive immediate recovery and long-term growth by focusing on key areas: revenue optimization, cost control, cash flow management, strategic partnerships, and employee performance. By achieving the specific desired results within the outlined timelines, the organization will not only reverse its losses but position itself for sustained financial success. Regular monitoring and strategic flexibility are essential to achieving these objectives.