# Departmental Action Plan Template

Student Name: Jeremy Reed

Class & Student Number: A-051

Academy Week (Var II):

# Current situation or challenge you want to address: (must be quantifiable)

Current monthly Used Truck volume averages.

28 Units

$117,736 GP

# Overall Objective and Specific Desired Results:

Increase Used sales volume 40% by December 30th, 2025.

28 units will be raised to 40 units per month

$117,736 monthly gross profit will be raised to $164,830 per month

# Describe your action plan in detail (be specific and include before and after Measurements)

### 1. Implement CRM

- Implement CRM: Ensure all customer interactions, sales pipelines, and follow-ups are tracked in CRM

- Segment Customers: Use CRM data to segment customers by behavior, demographics, and purchase history, allowing for targeted communication and offers.

- Automate Follow-ups: Set up automated reminders and email campaigns for follow-ups, upsells, and cross-sells to maximize sales opportunities.

### 2. Sales Executive Incentives

- Set Clear Sales Targets: Define monthly sales goals that contribute to the 25% increase. Break it down to target an incremental growth of ~3% per month.

- Performance-Based Incentives: Offer tiered rewards for sales executives—bonuses, commissions, or non-monetary rewards like trips, TCI Swap, or recognition—for hitting monthly targets, and CRM utilization.

### 3. Month-over-Month Gains

- Track Progress Monthly: Use CRM & Halo to monitor progress towards sales targets and adjust strategies based on performance.

January: 30units = $125,580			July: 36 units = $149,130

March: 32 units = $133,430			September: 38 units = $156,980

May: 34 units = $141,280			November: 40 units = $164,830

- Review Data and Pivot: At the end of each month, review which approaches worked best, adjust incentive plans if necessary, and implement the most successful tactics for the next month.

# Timeline:

Describe specific short term and long-term checkpoints to monitor progress

### Short-Term Checkpoints (Monthly)

- Sales Growth: Target 3% growth per month. Track actual sales using Halo vs. target using CRM.

- Sales Executive Performance: Monitor individual sales targets and adjust incentives for underperformers.

- Lead Generation & Conversion: Track the number of leads and conversion rates. Adjust campaigns if needed.

- CRM Utilization: Monitor CRM data entry and automation, ensuring follow-ups and tasks are logged.

### Long-Term Checkpoints (Quarterly)

- Cumulative Sales Progress: After 3 months, aim for 9% growth; after 6 months, 18%. Adjust if behind.

- Sales Forecast: Adjust projections based on first quarter Used Truck market & sales performance.

- Sales Team Productivity: Assess the productivity of the sales team using CRM activity data.

- Customer Satisfaction: Gather feedback to ensure alignment with customer needs and adjust follow-up times with Service Advocates and Sales Reps.

### .

# Meeting with Stakeholders (dealership personnel)

Describe what behavior change is needed to support desired goal.  Address required coaching, training and/or consequences (PINO, Gain, Pain).  Include timelines / Accountability / Monitoring process

- Who:

- What:

- By When:

- How:

### a. Who:

- Sales Executives: Responsible for increasing sales.

- Sales Managers / GMs: Oversee team performance and provide coaching.

### b. What:

- Sales Executives: Increase activity (calls, meetings), use CRM effectively, and focus on upselling/cross-selling.

- Sales Managers / GMs: Provide regular feedback, monitor CRM usage, and ensure targets are met.

### c. By When:

- Sales Executives:

  - Start CRM usage and increase activity immediately.

  - Achieve 3% growth per month, with full adherence by Month 2.

- Sales Managers / GMs:

  - Begin coaching immediately, review performance monthly.

  - Adjust strategy after 3 months.

### d. How:

- Coaching & Training:

  - Sales Executives: CRM training, sales skills workshops, and weekly check-ins.

  - Sales Managers / GMs: Regular one-on-ones and performance reviews.

- Incentive Structure (PINO, Gain, Pain):

  - Gain: Bonuses for meeting targets, GP & CRM utilization.

  - Pain: Performance improvement plans for underperformers after 2 months.

- Accountability & Monitoring:

  - Daily: CRM tracking.

  - Weekly: Friday Sales Zooms for updates.

  - Monthly: Performance reviews and adjustment of tactics if needed.

### Timeline Summary:

| Action | By When | Responsible |
| --- | --- | --- |
| Sales reps increase activity and CRM usage | Immediate - Month 1 | Sales Executives |
| Sales reps hit 3% growth | End of Month 1 | Sales Executives |
| Managers provide coaching | Ongoing, Weekly | Sales Managers |
| Review sales progress (18% growth by Month 6) | End of Month 3, 6 | Sales Managers, Marketing |

# Dealer agreement:

If you need your sponsors support or approval to implement your plan, have it signed off before you start.  If you can proceed on your own, present this action plan to your sponsor before next class.   Describe the meeting: