# Departmental Action Plan Template

Student Name: Michael Crawford

Class & Student Number: A051

Academy Week (Var II): Week 5

# Current situation or challenge you want to address: (must be quantifiable)

The current new truck inventory at Ohio Peterbilt is $98,206,000 and equals a 4.9 month supply.  This is higher than our desired level of $60,426,000 and a 3 month supply as wee average $20,142,000 per month in New truck sales. The excess inventory has hurt our profitability due to increase flooring costs.  The additional flooring cost is negatively affecting our bottom line by $188,900 per month or the potential of $2,266,800 in 2025 if we do not get new truck inventory back in line.

# Overall Objective and Specific Desired Results:

The Goal is to reduce New Truck inventory from $98.2 million to $60 million between January 1st, 2025 through June 30th, 2024 and reduce our months supply form 5 months to 3 months to bring back in-line with our company goals.

The monthly sales targets include an additional $5 million in sales per month(total of $38 million  reduction over 6 months).

The reduction in inventory will increase the overall dealership net profit by $188,900 per month or $2,266,800 per year.

# Describe your action plan in detail (be specific and include before and after Measurements)

Measurable:

Share the specific goals and objectives with the sales team and the reasons why they are important to the dealership and its stakeholders.

Track weekly inventory levels, monthly sale figures and promotional effectiveness and review with the sales team on weekly basis.

Develop dashboards to monitor inventory turn rates and sales performance in real time and make them accessible and visible to all sales employees that track the progress towards the goal.

Achievable

Analyze past sales data and current inventory mix to ensure the target is realistic based on historical performance.

Be prepared to adjust monthly targets based on market conditions and customer response .

Relevant

Prioritize inventory that aligns with current market trends, seasonal activity and customer preferences.

Ensure marketing promotions address specific customer segments such as fleet, vocational, over the road, private fleets and owner operators.

Timeline

Month 1: Conduct a thorough market and inventory analysis.  Identify top selling models and the more difficult inventory to move.  Launch initial marketing efforts specific to the model and customer mix we have on-hand.  Develop aggressive pricing strategy on all targeted inventory and develop new price list and distribute to all sales employees.

Month 2:  Implement promotional campaigns such as discounts, financing, additional warranty offers on targeted inventory.  Monitor sales daily to see how these promotions are working and adjust accordingly.

Month3: Host a major sales blitz with all departments and host open houses at all locations to showcase current inventory.  Develop sales literature and digital flyers with marketing team and distribute to all current and potential customers in our CRM system.

Month 4: Analyze sales data and adjust based on what’s selling with extra focus on underperforming inventory.  Use marketing department launch additional campaigns and more aggressive pricing strategies to targeted customers for the underperforming inventory.

Month 5: Leverage partnerships with OEM and financing institutions to enhance product offerings and buyer’s options.  Promote additional warranty, aggressive pricing, low interest rates, trade-ins etc. that we negotiated with our partners to push remaining inventory.

Month 6: Conduct final push to sell remaining inventory with all significant promotions developed throughout the last 6 months along with an even more aggressive pricing strategy.  Revie and assess overall inventory and sales performance.

Action Steps

- Market Analysis

Use the marketing team to research local market trends to identify which truck models are in demand and which units are harder to sell.  Conduct a price analysis and develop and aggressive pricing strategy for the more difficult inventory.

Engage sales team to advise of our goals and strategy and to get additional feedback on customer trends and pricing strategies.  Equip sales team with new aggressive price list based on market study along with a new sales plan to incentivize the teal to reduce inventory and take smaller deals on the more difficult to move units.

- Develop a targeted marketing campaign focusing on high-demand inventory with market pricing strategy.

Develop a very targeted marketing campaign on the more difficult inventory with less than market pricing strategy.

Create bundle offers including extended warranties, special finance rates and terms and maintenance contracts, price these aggressively and include in all marketing efforts.

- Hold required sale training for all salespeople that equips them with detailed product knowledge and effective sales techniques.

Hold weekly sales meetings to boost engagement, trach progress and provide motivation to reach goals.

- Attend every local trade show, attend industry events, host open houses and sales blitzes to increase brand visibility and engage with our current and potential customer base.

Use social media extensively to target to potential customer base the Ohio Peterbilt brand and offerings.

- Establish a referral program that incentivizes current customer to refer new buyers.  Develop market campaign through CRM to promote this new program.

Use CRM to reach out to all customers that hasn’t purchased in past 3 years or has the potential to replace their current unit with aggressive trad-in and pricing strategy.

- Do weekly review of inventory metrics to identify slow-moving stock and refine targeted market campaign and pricing strategy based on results.

Adjust future inventory orders based on the success of promotions and sales and the better moving inventory.

# Timeline:

Describe specific short term and long term checkpoints to monitor progress

Timeline

Month 1: Conduct a thorough market and inventory analysis.  Identify top selling models and the more difficult inventory to move.  Launch initial marketing efforts specific to the model and customer mix we have on-hand.  Develop aggressive pricing strategy on all targeted inventory and develop new price list and distribute to all sales employees.  Re-schedule backlog truck on order to coincide with customer requested delivery.

Inventory goal: $93.2 million ($5m reduction in new truck inventory)

Month 2:  Implement promotional campaigns such as discounts, financing, additional warranty offers on targeted inventory.  Monitor sales daily to see how these promotions are working and adjust accordingly.

Inventory Goal: $88.2 million ($5 million reduction in new truck inventory)

Month3: Host a major sales blitz with all departments and host open houses at all locations to showcase current inventory.  Develop sales literature and digital flyers with marketing team and distribute to all current and potential customers in our CRM system.

Inventory goal: $81.2 million ($7 million reduction in new truck inventory)

Month 4: Analyze sales data and adjust based on what’s selling with extra focus on underperforming inventory.  Use marketing department launch additional campaigns and more aggressive pricing strategies to targeted customers for the underperforming inventory.

Inventory Goal: $71.2 million ($10million reduction in new truck inventory)

Month 5: Leverage partnerships with OEM and financing institutions to enhance product offerings and buyer’s options.  Promote additional warranty, aggressive pricing, low interest rates, trade-ins etc. that we negotiated with our partners to push remaining inventory.

Inventory goal: $64.2 million ($7 million reduction in new truck inventory)

Month 6: Conduct final push to sell remaining inventory with all significant promotions developed throughout the last 6 months along with an even more aggressive pricing strategy.  Revie and assess overall inventory and sales performance.

Inventory goal: $60.4 million ($3.8M reduction in new truck inventory)

# Meeting with Stakeholders (dealership personnel)

Describe what behavior change is needed to support desired goal.  Address required coaching, training and/or consequences (PINO, Gain, Pain).  Include timelines / Accountability / Monitoring process

- Who: Sales Director

- What:

- By When:

- How:

First meeting is Dealer Principal with Sales Director to review goals, objectives and reasons behind the initiative.  This needs to be done the first week of the new year.

Next meeting is with the Sales Director and Marketing Manager to develop a marketing plan and strategy to move the excess inventory.  This needs to be complete before the end of the 2nd week of the new year.

Meetings with Vendors, OEM and finance companies need to take place with Sales Director and marketing Manager to determine incentives that we can use to move the excess inventory and merge into our marketing plan.

Once plan in developed, there needs to be a meeting with the entire sales team to review the goal, marketing plan and reasons behind the initiative. This will be a struggle for some salespeople as we are taking an aggressive pricing strategy and many are conditioned to hold out for higher gross profits.  This needs to be completed by January, 15, 2025 along with the plan launch.

Weekly 15 minute sales meeting will be held every Monday @ 9:00 AM with sales Director, Sales manager and Salespeople to determine progress made towards the goal, determine customer reaction and determine what marketing and pricing strategies need to be adjusted.

Bi-weekly meeting with Marketing Manager and Sales Director will take place every other Friday @ 10:00 AM to review progress and make adjustments based on sales performance and salespeople feedback.

Monthly Meeting between sales Director and Dealer principal will take place the third Tuesday of every month during scheduled KPI meeting to discuss progress and review results.

# Dealer agreement:

If you need your sponsors support or approval to implement your plan, have it signed off before you start.  If you can proceed on your own, present this action plan to your sponsor before next class.   Describe the meeting

I reviewed this plan with the owner of Ohio Peterbilt and the CFO.  They liked the plan and look forward to the difference it will potentially make to the bottom line.   We just did a similar plan for used trucks and brought our Used Truck Inventory down from $12M(6 month supply) to $7M($3.5 month supply) so they are eager for me to get started on this.  They also challenged me to put policies and procedures in place to avoid getting into this situation again in the future.