| Name | Randy Tyerman | Class # | ATD051 |
| --- | --- | --- | --- |
| Dealership | TransWestern Truck Centres | Date | 12/1/2024 |

| Current Situation or Challenge to be Addressed: | x Currently the dealership has 100 new trucks in inventory. 24 of these are aged over 151 days. |  |  |
| --- | --- | --- | --- |
| Current Performance Level (include specific measure): | The oldest one has been sitting for 657 days at the end of November resulting in $26K flooring expense and 7 with curtailment charges of 29K per month. |  |  |
| Goal (what do you want to achieve?) | We would like to reduce the aged inventory that currently is 151 days old and older, from 24 to 0 in the next 2 months. |  |  |
| Goal Performance Level (include specific measure) | 0 aged trucks over 151 days |  |  |
| Goal Start Date: | 12/2/2024 | Goal End Date: | 1/31/2025 |
| First Check-in Date: | 12/16/2024 | Performance Objective: | Move 4-5 Units |
| Second Check-in Date: | 12/30/2024 | Performance Objective: | Move 5-6 Units |
| Third Check-in Date: | 1/13/2025 | Performance Objective: | Move 6-7 Units |
| Fourth Check-in Date: | 1/27/2025 | Performance Objective: | Move 6-7 Units |
| How does your goal align with the dealers’ vision? | A comprehensive solution for all customer needs. More trucks in the hands of our customers will add to our vision of being thier first choice to help them with their bussiness. |  |  |
| What are the potential benefits of achieving your goal? | It aligins with the dealership goal for market share and overall revenue. Alows for fixed operations to make money. |  |  |
| What are the potential consequences if you don’t achieve your goal? | The biggest issue is the lost revenue and selling the unit at auctions for potenially bigger losses and no opertunitity for the fixed operation side of the business. |  |  |
| Why is the goal important to you? | Parts and service revenue for units that are sold. Health to dealership's bottom line. |  |  |
| Potential Obstacles | There is a soft market here right now for long haul trucks. Rates have not increased at all. Reluctancy to by a new unit at this time. |  |  |
| Potential Solutions | OEM sales promotion to help drive sales, spiffs for customer referalls and insentives to sell |  |  |
| BOTTOM LINE! Financial Impact of Achieving Your Goal (expressed in dollars) | The bleading will stop!! 55K back to the bottom line. |  |  |

What specific actions or steps will you take to accomplish your goal?  What will you do differently or improve? For each, be sure to include necessary resources, who is accountable, the measurable result, and dates.

| Specific action/step | Necessary resource(s) | Accountable person(s) | Expected result | Start, End, & CHeckpoint Dates |
| --- | --- | --- | --- | --- |
| Take advantage of special promotion with the OEM for end of year deals, extra sales assistance, financial options, etc. | OEM program is in place. | Sales Manager and F&I Manger | This should help customers who were on the edge about purchasing based on price | 11/20/2024, 12/31/2024 Check points at the end of each week with F&I |
| Review the pricing structure and adjust as necessary to be competitive. | Sales Manger and GM to deside the bottom price per unit. | Sales Manager | Should speed up the negotiating step. | 12/02/2024 01/31/2025 Check points to align with performance objective time line.Adjustments made as required. |
| Direct people to our website, advertise on Facebook marketplace and other online platforms. Promote new trucks at our parts and service counters | Website updated and display have been installed in the parts department to draw attention. Sales people to list units on marketplace. | Sales Cooridinator and Sales Staff | Traffic into the sales department | 12/02/2024 12/06/2024 |
| Each unit moved will have a spiff of $1000.00. | Funds have been provided. | General Manager Sales Manger | A little motivation to sell | 12/02/2024 12/06/2024 |
| A customer referral program to also be put in place for each unit sold for $1000.00 | Funds made avaialbe | General Manager Sales Manager | Rewards for customers. Bring in new business. | 12/02/2024 12/06/2024 |
| Follow up with existing customers that were in the market to buy a truck from our CRM data. | CRM Tools are available | Sales Person | Hopefully draw in customers who are looking and waiting for a deal. | 12/02/2024 01/31/2025 |
| Improve trade-in offers to incentivize purchase. | Sales manger to offer top dollar. | Used Truck Manager | Will also help fill the gap for customer needs as requests for units under 100K | 12/02/2024 01/31/2025 |

As you work toward your goal, it’s important to have interim check points with specific, measurable objectives so your team can hold themselves accountable. If everyone knows the goal and objectives, you don’t have to spend your valuable time micromanaging.

Once you’ve accomplished your goal, added or adjusted policies, procedures, and behaviors, now what? How will you ensure you and your staff do not fall back into the previous habits that produced poor results? Be specific.

A policy has been put in place to help capature some of the costs do to cancellations with non refundable deposits. It will be enforced.

Describe any planning or implementation meetings conducted as part of development of your plan.

In speaking with our sales manager, the sales team is under extreme pressure to move these units, a portion of these units came from a couple of order cancellations which have proved to be a bit of a challenge. The End of Year program runs till December 31 and has proven to be a very tight timeline, we hope that it will be extended into next year. The goal is to move as many be then. All deals are being looked at and recorded in our CRM, which is how everything is now monitored. The spot rates are really affecting the customers’ choice to purchase a new unit, and a lot are looking at used due to price. A timeline could not really be given at this time on a drop-dead date. He is feeling the pain. In conversation with our general manager, he feels the same pain as the sales manager, only 10 times worse. He believes that we are doing everything that we can do to try and move the aged inventory. This should have been done months before. Short of letting the sales manager go, which may or may not solve anything, as 2 of our competitors have already done our last resort would be to take them to an auction. Which they may end up doing closer to Q2 next year. We have an experienced salesperson coming on board at the beginning of January and his job will be to help get these over the curb. The whole dealership is committed to help getting these trucks into customer hands and any lead brought forward that result in a sale will be rewarded.

| Sponsor Signature: |  |
| --- | --- |