# Departmental Action Plan Template

Student Name: Trey Courtney

Class & Student Number: A051-15

Academy Week (Var II): Var II

# Current situation or challenge you want to address: (must be quantifiable)

We have made significant investments in our Salesforce CRM platform but are not getting the Sales Staff engagement that we expected.  Our current average number of customer contacts for all of our salesmen is 37.8.

# Overall Objective and Specific Desired Results:

Out of 15 salesmen, seven do not have any contacts logged in Salesforce.  This shows that they are not using the tools provided to them.  Five salesmen have between 2 and 50 contacts, and three salesmen have 100 or greater.  Our goal is to have every salesman log all customer interactions and increase our average to 85 per month within 6 months.

# Describe your action plan in detail (be specific and include before and after Measurements)

Initial Meeting with all Truck Salesmen and Sales Managers to go outline the plan goals and what we expect from them over the next six months.  We will recognize the salesmen that are already meeting or exceeding our expectations and have them share their insights on how they are using our CRM tool effectively.

Provide one-on-one training with our IT Department to address any lack of knowledge on how to log customer interactions within Salesforce.

Conduct monthly status meetings with Sales Managers to track our progress and highlight any salesmen that need additional training or motivation.

Milestone Goals:

Date			Avg. Customer Contacts

Starting Point – 	01/09/2025		37.8

Month 1 Goal - 	02/07/2025		46

Month 2 Goal - 	03/07/2025		54

Month 3 Goal - 	04/04/2025		62

Month 4 Goal - 	05/02/2025		70

Month 6 Goal - 	06/06/2025		78

Ending Goal - 		07/04/2025		85

# Timeline:

Describe specific short term and long term checkpoints to monitor progress

Initial Meeting – 01/09/2025

Training Window – 01/13/2025-01/24/2025

Monthly Check-In’s with Sales Managers – 01/09/2025 - 07/04/2025

Plan Review and Follow-Up – 07/04/2025

# Meeting with Stakeholders (dealership personnel)

Describe what behavior change is needed to support desired goal.  Address required coaching, training and/or consequences (PINO, Gain, Pain).  Include timelines / Accountability / Monitoring process

- Who: Sales Managers, Salesmen

- What: Increase customer contacts logged in Salesforce from an average of 37.8 to 85.

- By When: July 4th, 2025

- How: Sales Staff training and coaching by Sales Managers

# Dealer agreement:

If you need your sponsors support or approval to implement your plan, have it signed off before you start.  If you can proceed on your own, present this action plan to your sponsor before next class.   Describe the meeting: