| Name | Justin Olmeim | Class # | 443 |
| --- | --- | --- | --- |
| Dealership | Fury Motors | Date | 7/27/2024 |

| Current Situation or Challenge to be Addressed: | Increasing our turn rate to lower our holding costs. It's gotten a bit excessive. |  |  |
| --- | --- | --- | --- |
| Current Performance Level (include specific measure): | We have an extremely high monthly holding cost, due to the amount of aged used units in our inventory. I need to eliminate $4 million in used inventory bringing me down to a manageable , turnable amount of vehicles. Holding this much inventory, that we are simply NOT turning fast enough is costing us big dollars monthly. I also have an 8 month supply of new inventory based on our poor turn rate. I started on this project in June prior to class, but have an entirely new outlook on how I should go about it since class. |  |  |
| Goal (what do you want to achieve?) | Diminish our used inventory from nearly $7 million, down to $3 million of the in-demand inventory. My inventory goal is 125 used units, at a lower in-demand price point. Our avg used vehicle in inventory cost is $31,370. This value is too high for my local market. |  |  |
| Goal Performance Level (include specific measure) | I want to see in provision, the inventory value lower from $7 million down to $3 million. In turn this lower investment amount will increase our turn rate. |  |  |
| Goal Start Date: | 8/1/2024 | Goal End Date: | 11/1/2024 |
| First Check-in Date: | 8/15/2024 | Performance Objective: | Eliminate the oldest and under performing units and send to auction/wholesale. Create hard 60 day turn rule |
| Second Check-in Date: | 8/19/2024 | Performance Objective: | Eval on remaining units and create an exit strategy for the remaining "pain". Retail, auction, inner store transfers? |
| Third Check-in Date: | 9/2/2024 | Performance Objective: | Eval on what has sold retail/wholesale. Reprice/what needs to go to auction/what can we retail |
| Fourth Check-in Date: | 9/16/2024 | Performance Objective: | Used car meeting every 14 days to eval as a team and discuss price, exit strat, wholesale, identify issues |
| How does your goal align with the dealers’ vision? | In 2024 the used car market is running the car world. We need a harder focus on aged, pricing and turn rate to maximize our profit. The dealers vision is to have an extremely healthy, faster turning inventory and hold gross without having a large amount of holding costs. |  |  |
| What are the potential benefits of achieving your goal? | Increased turn rate. Increased profits. Lower holding costs. Healthier dealership financials. Happier sales people. Decreased costs of doing business. |  |  |
| What are the potential consequences if you don’t achieve your goal? | The rinse and repeat will continue. Without changing the process, we won't change the outcome. Aged will increase. Profits will continue to decline. Turn over of staff due to lack of income. |  |  |
| Why is the goal important to you? | The dealership is my baby. If it fails, I fail. The health of my stores financials, turn rate on aged and untimately netting more money are all super important to me. |  |  |
| Potential Obstacles | Heavy losses on currnet aged units. Slower traffic for 1st half of 2024. Auction values are down compared to when we acquired some of these units. Short answer: moving them off the lot. |  |  |
| Potential Solutions | Take the pain now before the market tips the wrong direction. They will never be worth more than they are now. Maximize the return of lack there of. |  |  |
| BOTTOM LINE! Financial Impact of Achieving Your Goal (expressed in dollars) | Holding costs for June were $312k. By eliminating roughly half of this, would save us $150k monthly in holding costs. |  |  |

What specific actions or steps will you take to accomplish your goal?  What will you do differently or improve? For each, be sure to include necessary resources, who is accountable, the measurable result, and dates.

| Specific action/step | Necessary resource(s) | Accountable person(s) | Expected result | Start, End, & CHeckpoint Dates |
| --- | --- | --- | --- | --- |
| Review current used inventory dollars and levels | Vauto, DMS | Used car manager | We have a lot of aging units that are slow moving or over priced | Start: asap End: sameday |
| Reevaluate all inventory over 60days old | Vauto | Used car manager, GSM | Some of our units have been in inventory almost 1 year | ASAP Sameday |
| Identify units that we have no exit plan for and make plan | Vauto, DMS | Used car manager, GSM | 50/50 will go to auction. The rest we attempt retailing for 30 days, repriced. | Start: asap End: 30 days Checkpoint: 15 days |
| After 30 days, remaining aged goes to wholesale/auction. Down to 125 units, under 60 days old | Manheim | Used car manager GSM | We will take the most pain this route, but it has to be done | Start: 30 days End: 7 days |
| Create aged car process and cap units at 125 | DMS | GSM | Creating a process and holding everyone accountable will keep our holding costs at a minimum | Start: asap End: 30 days |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |

As you work toward your goal, it’s important to have interim check points with specific, measurable objectives so your team can hold themselves accountable. If everyone knows the goal and objectives, you don’t have to spend your valuable time micromanaging.

Once you’ve accomplished your goal, added or adjusted policies, procedures, and behaviors, now what? How will you ensure you and your staff do not fall back into the previous habits that produced poor results? Be specific.

Weekly reports on used inventory, showing inventory dollars and unit count. This is found at a glance within Vauto, but good to sit and review as a team. Holding everyone accountable for their part within the new process.

Describe any planning or implementation meetings conducted as part of development of your plan.

Multiple meetings have already taken place since class. We are already in the process of making this happen. We meet 3 times weekly anyways, and this has been our hot topic lately. Holding costs made my jaw drop. We had to make a change immediately. Thanks for pointing this out to me!

| Sponsor Signature: |  |
| --- | --- |