| Name | Tyler Tolbert | Class # | N443 |
| --- | --- | --- | --- |
| Dealership | Pine Belt Chevrolet Buick | Date | 11/1/2024 |

| Current Situation or Challenge to be Addressed: | UVI and PDI days to ready has increased from 3 to 7 and we need to readjust our process to get it back to 3. This is causing issues with our sales numbers and preventing us the inventory necessary to hit our goals on the variable side. |  |  |
| --- | --- | --- | --- |
| Current Performance Level (include specific measure): | 7 days til the vehicle is front line ready. |  |  |
| Goal (what do you want to achieve?) | I want to achieve a clean process where 3 days is the max time for UVI and PDI's to be complete. |  |  |
| Goal Performance Level (include specific measure) | 3 days once a vehicle hits the service department |  |  |
| Goal Start Date: | 11/1/2024 | Goal End Date: | 11/30/2024 |
| First Check-in Date: | 11/9/2024 | Performance Objective: | Drop a day on the time til the vehicle is frontline ready (be at 6) |
| Second Check-in Date: | 11/16/2024 | Performance Objective: | Drop a day on the time til the vehicle is frontline ready (be at 5) |
| Third Check-in Date: | 11/23/2024 | Performance Objective: | Drop a day on the time til the vehicle is frontline ready (be at 4) |
| Fourth Check-in Date: | 11/30/2024 | Performance Objective: | Drop a day on the time til the vehicle is frontline ready (be at 3) |
| How does your goal align with the dealers’ vision? | This goal aligns with the dealer's vision because our vision, especially in the service department and as a plea from sales, is to make all available cars available. |  |  |
| What are the potential benefits of achieving your goal? | The potential benefits of hitting this goal is improved absorption in service, higher ELR in service, GROI per vehicle will increase because of floorplan interest payments, focus of used and new vehicles will be on day's supply and turn of inventory, avoids overage units, increase opportunities for service to touch more vehicles and for sales to sell more vehicles, ultimate goal is to make the most money available throughout total dealership. Also, we will have more room in our small parking lot as vehicles won't pile up and get stuck in service. |  |  |
| What are the potential consequences if you don’t achieve your goal? | Potential consequences of not hitting our goal is lost money in the service department, sales department, and the parts department. Our GROI would continue to remain low. Our used and new car departments will suffer as we lack access to sell the inventory we have which will also result in our turn to be affected negatively. |  |  |
| Why is the goal important to you? | This goal is important to me because I want the dealership to be successful and for all departments to flourish. I am in the new car department and want inventory to be up on the front line and not taking up space in the service department parking lot. Our ultimate goal is to sell more cars and more new cars sold equals more trades, more business and more income for everyone. |  |  |
| Potential Obstacles | Potential obstacles are getting all departments to buy in on the idea of less than a 3 day front line ready goal to be achievable. We've recently had a change in management in the used car department and the service department and neither of them were a part of the team that achieved the 3 day consistent UVI and PDI turn to the front line, so it is an abstract idea at the moment for some. |  |  |
| Potential Solutions | Potential solutions is to reimplement the process that was what lead the first team to success and analyzing how we can readjust what we are doing now to get back to that. Show it is possible and accomplish it a few times to show how simple it can be. Then make it consistent. |  |  |
| BOTTOM LINE! Financial Impact of Achieving Your Goal (expressed in dollars) | The average cost for a new vehicle to sit on our lot per day is roughly $82 (Compostite p. 8 box 12). If it takes just 4 days for one of my Buick Envista's, whose profit is already small at nearly $1500 on average and has an average turn of 30 days, I would only have 14 more days (fiscal, not working days) to sell the vehicle and stay in the positive. I risk the lost of a lot of profit by letting these vehicles take more and more time to get front line ready. This is the same concept for used vehicles as well, but at roughly $92 a day. I plan to shave off 4 days of front line ready time, my total inventory is kept on the lot stays around 150 units (used: 40-50 new: 80-90). Our goal for inventory turn is 30 days on used and 60 days on new. So in 30 days, I plan to save a total of roughly $15,000 on used vehicles and about $30,000 on new in 60 days. Total amount saved across the 60 day period: $60,000 to the bottom line. |  |  |

What specific actions or steps will you take to accomplish your goal?  What will you do differently or improve? For each, be sure to include necessary resources, who is accountable, the measurable result, and dates.

| Specific action/step | Necessary resource(s) | Accountable person(s) | Expected result | Start, End, & CHeckpoint Dates |
| --- | --- | --- | --- | --- |
| Meet with department heads and address the situation, go over plan set in place and make adjustments needed through discussion | All the department heads | All department heads | To come to a conclusion of an action plan and what each head can do to make a change that will align their department with intended goal. | Nov 1, 24 Checkpoints will be each Friday of Nov. |
| Clean up Detail department and make their workplace organized and process oriented | Cleaning supplies, time to spend organizing, pressure washer | Detail department head, myself | More open space and organized department so their process will result in less time a vehicle spends back there | Nov 2, 24 Checkpoint: Nov 10, 24 |
| Have our exit strategy for each used vehicle bought expressed to service dept | Communication between used car dept and service dept | Used car manager and service manager, our service assistant manager | Less confusion on what all should be done to each used vehicle bought | Nov 2, 24 Checkpoint and end date: Nov 30, 24 |
| Create a max limit of spending on used vehicles | Known and written set goal be shared with everyone | Used car manager and service manager | Quicker decisions made for what fixes are to be made on used vehicles purchased | Nov 2, 24 Checkpoint and end date: Nov 30, 24 |
| List out what fixes on UVI's are needs and which ones are wants | The list | Used car manager and service manager | Have the used car manager and the service manager be on the same page for decisions | Nov 2, 24 Checkpoint and end date: Nov 30, 24 |
| Define and write out a clear check in process for new vehicles when they get in | Folders and team members for helping organize | Lot manager, service manager, myself | Have new vehicles on the lot the same day they come in | Nov 2, 24 Checkpoint and end date: Nov 30, 24 |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |

As you work toward your goal, it’s important to have interim check points with specific, measurable objectives so your team can hold themselves accountable. If everyone knows the goal and objectives, you don’t have to spend your valuable time micromanaging.

Once you’ve accomplished your goal, added or adjusted policies, procedures, and behaviors, now what? How will you ensure you and your staff do not fall back into the previous habits that produced poor results? Be specific.

In our weekly department head meeting, I will make it a point to bring up these changes to see where we are with it and if it can be improved upon any more. I will also spend some of my own personal time in each of these departments and with each member of service to maintain a personal relationship with them which in hopes will provide me the time where I can really get their true opinion of changes made and time where they can open up to me and offer advice on how we can become better in the future with getting used and new vehicles up and ready to the front line. Detail is especially a goal of mine because I feel they can be easily overlooked and need to be encouraged.

Describe any planning or implementation meetings conducted as part of development of your plan.

The meeting opens up with each department head going over their gross numbers, sales, and needs as a department which is heard by each department head (GM, Fleet Manager, Service Manager, Used Car Manager, Finance Manager, Title Clerk, Parts Manager, Detail Manager, New Car Manager). We go into conversation about anything that is brought up that needs immediate attention. This meetings' main purpose is to achieve open communication throughout the departments and to be sure we are all on the same page as much as possible. If we are aware of each others' struggles, we feel we can better assist each other in becoming successful.

| Sponsor Signature: |  |
| --- | --- |