## Slide 1: Time to Line Optimization
Best Idea – VO1
Juan C. Ledesma
Class 445

## Slide 2: Step 1 – Assessment of Current Situation
How is the process running at this time?
  Time to line is not being measured so no base data
Who is involved in the process?
  Sales Manager
  Sales Representatives
  Service Advisors
  Workshop Foreman
  Technicians
  Parts Manager
  External Body Shop
  Photographer
What are the areas of responsibility per team member?
  Not clearly defined
What are the current results?
  Wide variances in time to line too erratic to determine a baseline

## Slide 3: Step 2 – Outline Process Definition
Set Objectives
Map process
Define process tasks
Evaluate staffing requirements
  Pay-Plan modifications
  Designate process champion
Team member responsibilities
Consider external influences that may affect the process

## Slide 4: Set Objectives
NADA Guide: 72 hrs
Current Performance
  No base data but estimated at 20 to 30 days
Initial Target: 10 days
Target by Dec 31st.: 5 Days*
  Workshop currently under remodel due to fire incident so capacity is limited at this time

## Slide 5: Map Process
 |  |  |  |  |  |  |  |  |  |  | Decision to Retail |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  | Open Recon RO and Place at designated Area |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  | Determine Parts Needed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Trade-In Evaluation by Pre-Owned Sales Manager |  |  |  |  | Workshop Evaluation to Determine Recon Work |  |  |  |  |  |  |  |  |  |  |  |  | Order Workshop Parts if Necessary |  |  |  |  |  | Order Body Parts if Necessary |  |  | 
 |  |  |  |  |  |  |  |  |  |  | Decision to Wholesale |  |  |  |  |  |  | Perform Mechanical Repairs |  |  |  |  |  | Set Appointment with Bodyshop |  |  | 
 |  |  |  |  |  |  |  |  |  |  | Wash & Detail |  |  |  |  |  |  | CP0 Certification |  |  |  |  |  | Perform Bodyshop Repairs |  |  | 
 |  |  |  |  |  |  |  |  |  |  | Offer to Wholesellers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Wash & Detail |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Photograph |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Upload to Website |  |  |  |  |  | 

## Slide 6: Define Process Tasks
Evaluation Process – the Pre-Owned Sales manager will determine if this is a vehicle we can and want to buy based on the market values and workshop recommendations.
Decision Process – based on the amount of work necessary to recondition the vehicle, availability of parts and costs the decision to wholesale or retail will be determined. Parts Department and Workshop input will be crucial.
The Reconditioning Process - the program Champion will coordinate all necessary Departments and external suppliers to ensure the parts and services are conducted with efficiency

## Slide 7: Evaluate Staffing Requirements
For the Process to smoothly work, the right people must be in place to ensure that all tasks are performed
  Pay-Plan that rewards target achievement individually and for the process as a whole with deductions for poor performance.
  The program champion will be the team member that will ensure communication across all staged of the process, coordinate with each process link and follow-up on the tasks and resolve any unexpected issues.

## Slide 8: Team Member Responsibilities
Pre-Owned Sales Manager will be responsible for the entire operation including the appraisal of each vehicle, determination to buy a vehicle and whether to Retail or Wholesale
Parts Manager provide an accurate cost and availability of parts necessary for recon, place orders and supply the in a timely manner
Designated Pre-Owned Service Advisor will promptly open the necessary RO and inform the Workshop Manager that a vehicle is in line for recon work
Workshop Manager will assign the appropriate tech, based workshop load, availability and the skill level required to perform the recon work
Assigned Tech will focus on performing the recon work assigned
Car wash staff will prioritize the finished vehicle and inform the photographer immediately
Photographer will be responsible for photographing and uploading all photos and videos to the website
Program Champion will ensure all team members perform their tasks diligently and assist or substitute whenever necessary and possible. In the case of external body work needed, will also coordinate the appointment, delivery and pickup of the vehicle to and from the body shop.

## Slide 9: External Influences
External issues that may affect the process must be taken into consideration such as:
  Delays due to carrier delays, back orders, damaged or defective parts
  Body shop capacity – given that we don’t have our own body shop we would need to work with at least two external suppliers to ensure constant availability
  Stop-Sale / Stop-Delivery campaigns that may delay the vehicle time to line schedule
  Workshop capacity issues
These situations will be monitored by the program Champion and evaluated with the Pre-Owned Sales Manager in conjunction the team member(s) affected in the process to quickly decide on the course of action to be taken

## Slide 10: Step 3 - Monitoring
Daily reporting from every team member to the program Champion to ensure a quick response to any situation
Weekly reporting from the program Champion to the Pre-Owned Sales Manager to evaluate each case and make process adjustments
Monthly team meeting to communicate the results of the process give feedback on each team member’s performance and brainstorm improvement ideas based on recent experience

## Slide 11: Conclusion
Given that there has never been a formal reconditioning process tied to performance metrics, the fact that one will be defined assigning responsibilities to each department and team member; will greatly improve the time to line
As the process is carried out and is further developed, reductions in the amount of days to time to line will improve eventually reaching the 72 hr. NADA Guide