| Name | Mitch James | Class # | N445 |
| --- | --- | --- | --- |
| Dealership | Chuck Hutton Toyota | Date | 8/29/2024 |

| Current Situation or Challenge to be Addressed: | Current time to lot for used cars is not measured. |  |  |
| --- | --- | --- | --- |
| Current Performance Level (include specific measure): | Currently, we have no specific measure for time to lot. |  |  |
| Goal (what do you want to achieve?) | To create a documented system for accurate metrics for time to lot. |  |  |
| Goal Performance Level (include specific measure) | 100% accurate documentation for time it takes from the moment a used car is acquired until it is ready for sale on the lot. |  |  |
| Goal Start Date: | 9/2/2024 | Goal End Date: | 9/30/2024 |
| First Check-in Date: | 9/9/2024 | Performance Objective: | Data collection: implement system to track the start and end times for each step. |
| Second Check-in Date: | 9/16/2024 | Performance Objective: | Utilize a digital tracking system or software that records timestamps for each step. |
| Third Check-in Date: | 9/23/2024 | Performance Objective: | Document the process; create a step-by-step guide that outlines the entire process from acquisition to the lot, including who is responsible for each step |
| Fourth Check-in Date: | 9/30/2024 | Performance Objective: | Establish baselines and set target benchmarks |
| How does your goal align with the dealers’ vision? | Achieving this goal aligns with our vision which emphasizes effiiciency, profitabtblity, customer satisfaction and competetive advantage. |  |  |
| What are the potential benefits of achieving your goal? | Potential benefits will lead to faster inventory turnover, reduce holding costs, improve cash flow and positively effect net profit. Accurate baselines allow for clear tracking of progress and hold individuals or teams accountable for their part in the process. |  |  |
| What are the potential consequences if you don’t achieve your goal? | Without an accurate baseline, we cannot measure progress effectively or be able to set realistic and acheivable goals. |  |  |
| Why is the goal important to you? | An accurate and standardized process is critical for making informed decisions, improving efficiency, and ensuring the dealership’s competitiveness and profitability. |  |  |
| Potential Obstacles | • Resistance to change from staff. • Resource limitations, such as insufficient staff or budget. • Communication gaps between departments. • Unexpected increases in inventory. • Technology or system failures. • Inaccurate data tracking. • External factors like supply chain delays. • Training and skill gaps among staff. |  |  |
| Potential Solutions | • Provide targeted training and incentives to staff. • Prioritize resource allocation and invest in necessary tools and technology • Improve inter-departmental communication through regular meetings. • Develop a contingency plan to handle unexpected increases in inventory. • Ensure robust technology and data tracking systems are in place. |  |  |
| BOTTOM LINE! Financial Impact of Achieving Your Goal (expressed in dollars) | The data here is missing until we get a good baseline for our current time to line for used cars. Numbers run in August showed us at 5.7 turns per year while NADA Guide is 12. Numbers also showed our used cars stopped adding anything positive to the NET profit on the 28th day it is stock. We must first get the baseline, then we can drill down on different processes from there. In turn, reducing time to line should increase our used car turn. |  |  |

What specific actions or steps will you take to accomplish your goal?  What will you do differently or improve? For each, be sure to include necessary resources, who is accountable, the measurable result, and dates.

| Specific action/step | Necessary resource(s) | Accountable person(s) | Expected result | Start, End, & CHeckpoint Dates |
| --- | --- | --- | --- | --- |
| Implement a standardized tracking process for time to lot with clear guidelines. | Tracking tools, software | GSM, Fixed Ops Manager, Used Car Managers | Accurate and consistent time-to-lot date | 09/02-09/09 |
| Train staff on the new process and the importance of accurate data entry. | Training coordinator, documentation | Operations Manager | Full staff adoption of the new process with high data accuracy | 09/09 - 09/16 |
| Regularly review and audit the tracking process to ensure ongoing accuracy and effectiveness. | Review meetings | GSM, Fixed Ops Manager, Operations Manager and Used Car Manager | Continuos improvement and mainteanance of the tracking process. | 09/16 - 09/30 |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |

As you work toward your goal, it’s important to have interim check points with specific, measurable objectives so your team can hold themselves accountable. If everyone knows the goal and objectives, you don’t have to spend your valuable time micromanaging.

Once you’ve accomplished your goal, added or adjusted policies, procedures, and behaviors, now what? How will you ensure you and your staff do not fall back into the previous habits that produced poor results? Be specific.

1. Regular Monitoring and Reporting: • Action: Establish a routine monitoring system where the time to lot is tracked and reported on a weekly basis. This report should be reviewed by the management team during regular meetings. • Purpose: Continuous monitoring ensures that any deviations from the goal are identified early and can be corrected before they become systemic issues. 2. Accountability Structures: • Action: Assign clear ownership of the time-to-lot process to specific team members, such as department heads or team leads, with defined performance metrics. • Purpose: This creates accountability and ensures that specific individuals are responsible for maintaining the standards that have been set. 3. Ongoing Training and Reinforcement: • Action: Schedule regular training sessions to reinforce the importance of the new process and to update staff on any changes or improvements. • Purpose: Ongoing training helps ensure that all team members stay aligned with the process and understand the importance of maintaining high standards. 4. Incentives and Recognition: • Action: Implement a recognition program that rewards teams or individuals who consistently meet or exceed time-to-lot targets. • Purpose: Positive reinforcement encourages adherence to the new processes and motivates staff to maintain high performance levels. 5. Process Audits and Reviews: • Action: Conduct quarterly audits of the time-to-lot process to identify any areas where staff might be slipping back into old habits. Use these audits to make necessary adjustments. • Purpose: Regular audits help ensure that the process remains effective and that any potential regressions are caught and addressed quickly. 6. Feedback Loops: • Action: Establish a feedback loop where staff can report challenges or suggest improvements to the process. Encourage open communication between management and staff. • Purpose: Engaging staff in the process improvement helps them feel invested in maintaining the new standards and provides valuable insights that can prevent backsliding. 7. Standard Operating Procedures (SOPs) and Documentation: • Action: Update and maintain detailed SOPs that outline the new processes. Ensure that these documents are accessible to all staff and regularly reviewed. • Purpose: Having clear, documented procedures helps prevent misunderstandings and ensures consistency in how the time-to-lot process is executed. 8. Leadership Commitment: • Action: Ensure that leadership consistently communicates the importance of the time-to-lot goal and models adherence to the new processes. • Purpose: Leadership commitment reinforces the significance of the goal and sets the tone for the entire organization to follow. 9. Continuous Improvement Mindset: • Action: Foster a culture of continuous improvement where staff are encouraged to always look for ways to enhance efficiency and reduce time to lot. • Purpose: This mindset helps keep the team focused on maintaining and improving performance over the long term.

Describe any planning or implementation meetings conducted as part of development of your plan.

This all starts September 2, 2024.

| Sponsor Signature: |  |
| --- | --- |