| Name | Nate Wilson | Class # | N445 |
| --- | --- | --- | --- |
| Dealership | Wilson Motor Co. | Date | 9/1/2024 |

| Current Situation or Challenge to be Addressed: | We have not done a good job of properly converting our leads into sales. We are below industry average in multiple categories and it's costing us sales. |  |  |
| --- | --- | --- | --- |
| Current Performance Level (include specific measure): | Internet Leads: 7% closing Phone ups: 20% closing Walk- ins: 30% Overall closing ratio is 25% |  |  |
| Goal (what do you want to achieve?) | We need to get to a total overall closing ratio of 33%. We will raise our internet by 3%, our phone by 5% and our overall by 8%. This would be an increase of 35 units from our previous month. |  |  |
| Goal Performance Level (include specific measure) | We will monitor daily and weekly to make sure the sales people are properly doing their tasks in Vin Solutions and entering them all. We have done a poor job with our lead answers especially on internet leads. This should be an easy fix. |  |  |
| Goal Start Date: | 9/1/2024 | Goal End Date: | 12/31/2024 |
| First Check-in Date: | 9/30/2024 | Performance Objective: | Would like to see a minimum of an increase overall of 2%. |
| Second Check-in Date: | 10/31/2024 | Performance Objective: | 4% |
| Third Check-in Date: | 11/30/2024 | Performance Objective: | 6% |
| Fourth Check-in Date: | 12/31/2024 | Performance Objective: | 8% |
| How does your goal align with the dealers’ vision? | This increase will put us in line with our OEM goals set by Ford and Nissan. We have a lot of competition around us, especially with Ford and our goal is to keep more than our fair share of market share. |  |  |
| What are the potential benefits of achieving your goal? | Gross and Net profit will go up due to more sales, and sales professionals and managers production will go up because they will see the results. |  |  |
| What are the potential consequences if you don’t achieve your goal? | Just keep burning through customers that are produced through our advertising dollars |  |  |
| Why is the goal important to you? | Our overall sales and profit are obviously the two biggest measures of success in a variable ops department. Make money! |  |  |
| Potential Obstacles | Easier said than done to change the way people do their jobs. We have people that have been doing things the same way for awhile and breaking habits can be very difficult. |  |  |
| Potential Solutions | Holding people accountable and leading by example. Also multiple spiffs for doing the action correctly, as apposed to only rewarding results. |  |  |
| BOTTOM LINE! Financial Impact of Achieving Your Goal (expressed in dollars) | If we are able to increase our sales by 35 units per month that is an increase of gross profit of just over $80k with our average from the last 3 months |  |  |

What specific actions or steps will you take to accomplish your goal?  What will you do differently or improve? For each, be sure to include necessary resources, who is accountable, the measurable result, and dates.

| Specific action/step | Necessary resource(s) | Accountable person(s) | Expected result | Start, End, & CHeckpoint Dates |
| --- | --- | --- | --- | --- |
| Better email outline for sales guys | Managers need to develop one | Managers and myself | Responses on email leads will raise a minimum 15% | This will be done by 9/15 |
| Better phone process (I hate scripts, but a general direction is imperative) | Managers put together as a team | Managers and myself | More appointments off of phone calls. | "Script outline" done by 9/15 |
| Set minimum phone call and email daily goals | Motivation! | All the sales people, but managers also being held accountable that they are holding the sales guys accountable. | Appointments will go up and appointments lead to sales. | Start date by 9/15 |
| Manager Turns: We don't do a good job once the client is here | Managers and sales people working together once people are here. | Managers and Sales people | This has to be done to get our closing ratios where they need to be. | 100% manager turn rate by 9/15 |
| Daily one on ones | Manager and Sales People | Managers | Better daily action plan and confirmation of appointments and follow ups | These will start by 9/15 |
| Sales meetings in line with our progress or lack of | Closely monitoring our progress to be able to train and follow up where we know we need to help | Managers and myself | This will allow us to better stay in line with where our ultimate goals line up | Sales Meetings are Saturday mornings so starting with 9/21 |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |

As you work toward your goal, it’s important to have interim check points with specific, measurable objectives so your team can hold themselves accountable. If everyone knows the goal and objectives, you don’t have to spend your valuable time micromanaging.

Once you’ve accomplished your goal, added or adjusted policies, procedures, and behaviors, now what? How will you ensure you and your staff do not fall back into the previous habits that produced poor results? Be specific.

The processes we put in place will help us reach our goals, but that just means we continue the processes and set new goals. There is always room for improvement and ways to get better. In sports the goal is to be 1% better every day you go to practice. There is no reason this can't be the same. Early on, you can do a lot better than that, but once things are rolling, you can still do 1% better.

Describe any planning or implementation meetings conducted as part of development of your plan.

We do a weekly managers meeting on Monday mornings. This is a great time to go over our weekly progress and things we can work on for the week.

| Sponsor Signature: |  |
| --- | --- |