# SMART GOAL – VO2

Andrew Marshall – N445

Current Challenge:

72% of our voluntary turnover occurs within the first 12 months of employment, which indicates a need to enhance our early-stage engagement and retention efforts. The primary challenge is that new team members leave before their potential can be fully realized, often because of gaps in onboarding and early career development. This plan aims to improve our first-year retention by reinstituting a comprehensive onboarding process, structured check-ins, and development programs.

Overall Objective and Desired Outcomes:

The goal of this initiative is to reduce first-year voluntary turnover from 72% to 40% over the course of 12 months. This will be achieved by establishing key retention practices focused on early-stage team member engagement, with frequent and structured touchpoints, training, and career development opportunities.

Action Plan (Expanded):

1. Pre-Hire Engagement and Recruitment Strategy

Objective: 	Engage potential new hires before they officially join Sewell to set the tone of their career from the very start.

Actions:

Pre-Hire Communication: After accepting an offer, every new team member will receive a welcome packet that outlines the onboarding process, company values, team expectations, and a personal video message from their direct supervisor.

Engagement via Technology: Use automated tools like preboarding portals via our HRIS (UKG) and virtual introductory sessions to give them information about Sewell’s history, their team structure, and what to expect on their first day.

Objective Measurement: Track new hires’ engagement with preboarding materials. We will measure this by email open rates and participation in virtual preboarding sessions, with a target of 90% of team members engaged in 50% of material before their first day.

2. Week 1 - Comprehensive Orientation Program

Objective: 	Ensure every new team member is fully oriented, with a clear understanding of expectations, company culture, and logistics.

Actions:

“Sewell 101” Orientation (3 days): A structured orientation will be conducted on the first 3 days of employment, covering company history, team structure, critical onboarding logistics (e.g., logins, parking, dress code), meeting with managers, team building exercises, and a day of community volunteer service.

Supervisor Introduction: Each new team member will be paired with their immediate supervisor for a personalized tour and team introduction.

Buddy System: Assign a peer ‘buddy’ for the first 30 days to help them acclimate to the company culture and answer informal questions. NO ONE eats alone for the first 30 days. The buddy is responsible for making sure this happens, even if the buddy isn’t part of the lunch each day.

Objective Measurement: Track 100% completion of the Day 1 orientation for all new hires. Post-orientation feedback surveys will be issued immediately, with a goal of a minimum 85% “Perfectly Satisfied” score.

3. Month 1 - Role-Specific Training

Objective: 	Equip the new hire with the necessary tools, systems, and knowledge to succeed in their specific role.

Actions:

Departmental Overview: Provide hands-on training for job-specific tools (e.g., CRM systems, reporting structures) and assign daily tasks to give them a sense of responsibility from the start.

Team Integration: Schedule one-on-one meetings with key team members in the first week to build relationships.

Objective Measurement: Ensure that 100% of new hires complete their role-specific onboarding plan by the end of Week 3, as verified by supervisors via an assigned checklist in UKG. Post-week one, new hires should complete a quiz testing in UKG of their understanding of core job functions with a target pass rate of 90%.

4. End of Month 1 - First Checkpoint Review

Objective: 	Review the team member’s progress, experience, and initial feedback on their onboarding.

Actions:

Checkpoint Review Meeting: Conduct a formal one-on-one review with the direct supervisor and HR representative to discuss early achievements, challenges, and areas of improvement.

Personal Development Plan (PDP) Creation: Create a unique PDP for EVERY new hire that outlines specific development goals for the next three months.

Objective Measurement: 100% completion rate of Month 1 reviews. Feedback forms in UKG will be used to measure satisfaction levels, aiming for at least 80% of new hires reporting a smooth onboarding experience.

5. Month 2 - Career Path Workshop

Objective: 	Provide team members with an early understanding of career development opportunities at Sewell.

Actions:

Career Workshop: A workshop to explain the difference between a job and a career, presenting clear growth paths within the company. Highlight internal promotion success stories and provide resources for ongoing professional development.

Objective Measurement: Track attendance with a goal of 100% participation. New hires will be asked to complete a career aspirations survey afterward, with at least 85% of them expressing satisfaction with their perceived career path at Sewell.

6. End of Month 3 - Formal Performance Review

Objective: 	Conduct a formal review of job performance, culture fit, and development progress at the 90-day mark.

Actions:

Performance Metrics Review: Assess key performance indicators (KPIs) specific to the role, including productivity, team integration, and feedback from peers and supervisors.

Cultural Fit Assessment: Ensure alignment with company values and provide feedback on how to deepen their connection with the team.

Career Development Update: Review the progress made on their PDP from Month 1, updating as needed.

Objective Measurement: Ensure 100% of new hires receive a 90-day performance review. Team members are expected to meet at least 70% of their role-specific KPIs by this point, with improvement plans in place for those who do not.

7. Month 6 - Service Excellence Refresher and Touchpoint

Objective: 	Reinforce company service standards to ensure high-quality service delivery across all team members.

Actions:

Service Refresher Training: A one-day interactive workshop focused on Sewell’s service standards, designed to inspire ownership of customer service excellence.

Mid-Year Checkpoint: Conduct a 30-minute meeting with Team Resources to discuss progress, lingering challenges, and additional training needs.

Objective Measurement: Track training completion for 100% of the new team members. Measure service impact through post-training quizzes, aiming for 85% accuracy in customer service-related scenarios.

8. End of Month 9 - Leadership Training & Check-in

Objective: 	Begin the conversation around leadership opportunities and prepare team members for potential advancement.

Actions:

Leadership Introduction Workshop: Offer insights into Sewell’s leadership framework and pathways to leadership roles.

Objective Measurement: Aim for 100% participation in leadership sessions. Feedback surveys post-workshop should reflect at least an 80% satisfaction score in the course.

9. End of Year 1 - Final Review and Retention Evaluation

Objective: 	Conduct a formal year-end review to discuss performance, personal and professional growth, and long-term career goals. Assess overall retention and turnover rates.

Actions:

Annual Performance Review: Review all KPIs, job performance, team integration, and leadership potential.

PDP Assessment: Evaluate progress made on the personal development plan and set goals for the second year of employment.

Objective Measurement: Retain 50% of new hires throughout their first year, reducing turnover from the current 72%. Every team member will have completed a year-end review with documented feedback and new goals.

Interim Performance Checkpoints (Summary of Above)

- Pre-Hire (Week 0):

- Track pre-hire engagement (emails opened, virtual sessions attended).

- Target: 90% of hires engage with preboarding content.

2.	Day 1 Orientation:

- Track completion of the Day 1 orientation.

- Target: 100% orientation completion, 85% satisfaction rate via post-session survey.

3.	End of Week 1:

- Role-specific training completed.

- Target: 100% of hires pass role-specific quizzes with a 90% pass rate.

4.	End of Month 1 Checkpoint:

- Formal review of job performance, feedback from supervisors, and PDP creation.

- Target: 100% completion rate of Month 1 reviews, with 80% satisfaction from team members on onboarding.

5.	End of Month 3 Checkpoint:

- 90-day performance review, KPI assessment, and cultural alignment check.

- Target: 70% of team members meet KPIs, 100% completion of performance reviews.

6.	End of Month 6:

- Service excellence training completed, progress review.

- Target: 85% success rate in post-training assessments, 100% completion of mid-year check-ins.

7.	End of Month 9 Checkpoint:

- Leadership training participation.

- Target: 100% participation and 80% satisfaction with leadership growth opportunities.

8.	End of Year 1:

- Retention evaluation and year-end review.

- Target: Retain 50% of new hires, reduce voluntary turnover to 50% from 72%. Every team member receives a year-end review with updated goals.

Desired Results:

By executing this plan, Sewell aims to significantly reduce first-year voluntary turnover from 72% to 50% within a year, while establishing a structured, measurable, and proactive approach to retaining new hires. This will lead to longer tenure, more engaged team members, and stronger career growth within the company.