| Name | Adrian D. Mosley | Class # | N446 |
| --- | --- | --- | --- |
| Dealership | Malcolm Cunningham Chevrolet North Point | Date | 12/5/2024 |

| Current Situation or Challenge to be Addressed: | Current problem is staffing issues with high turnover rates. Another problem is management is inconsistent with communication and expectations. The last problem is vehicle inventory. The challenge is limited inventory due to supply disruptions. |  |  |
| --- | --- | --- | --- |
| Current Performance Level (include specific measure): | Current staffing performance level is losing 10 out of every 15 sales team member hired. The current sales team consists of 2 New Car Managers, 2 Pre-owned Managers and a GSM. As a Team the sales manager strenth level is a solid 75 with strong experience in the business and knowledge of processing deals. The inconsistent communication and working together with the sales floor is keeping them from performing at 100. Vehicle inventory is where we fall short. The mindset of vehicle availabilty vs what we want causes us to settle for the trades we receive. |  |  |
| Goal (what do you want to achieve?) | I would like to start with putting a recruitment strategies such as using targeted jobs ads and recruitment agencies to attract experienced candidates. We could offer referral bonuses for current employees. We will offer ongoing training in sales. I would like to set up leadership training programs focusing on communication, conflict resolution and team management. Establish clear goals and perfromance metrics for managers. Regularly review and provide constructive feedbackon the managers. I would implement advanced inventory managment software to track and forecast demand accuratley. Diversify sourcing options ro reduce dependency on single supplier. Strengthen relationships with manufacturer and distributors for priority allocation. |  |  |
| Goal Performance Level (include specific measure) | Management goal performance is the hightest level. Proper management will help maintain employees and help them keep vehicle inventory clean. |  |  |
| Goal Start Date: | 1/1/2025 | Goal End Date: | 3/31/2025 |
| First Check-in Date: | 1/1/2025 | Performance Objective: | Management training |
| Second Check-in Date: | 1/31/2025 | Performance Objective: | Hiring and staffing progress |
| Third Check-in Date: | 2/15/2025 | Performance Objective: | Inventory and 45 day turn. |
| Fourth Check-in Date: | 3/31/2025 | Performance Objective: | Verify management has implemented training, verify new hire retention, and check inventory. |
| How does your goal align with the dealers’ vision? | My goals align with the dealership's principles, as effective management skills will help retain higher-level managers and maintain a strong sales team. Additionally increased product knowledge will contribute to improved inventory management and growth. |  |  |
| What are the potential benefits of achieving your goal? | Achieving my goal has the potential to generate increased revenue for the dealership, attract higher-level clientele, strengthen management and staffing, and enhance inventory quality. |  |  |
| What are the potential consequences if you don’t achieve your goal? | If the goals are not met, the dealership risks a cycle of ineffective management and high employee turnover. This will lead to us struggling with inventory and the possibilty for overall failure." |  |  |
| Why is the goal important to you? | This is a family-owned business was established in 2005. The success of employee's lives is deeply tied to the company, therefore making it both a personal and professional proirity to me. |  |  |
| Potential Obstacles | Introducing innovative approaches to seasoned professionals. |  |  |
| Potential Solutions | Implementing effective training programs and assembling the right management team. |  |  |
| BOTTOM LINE! Financial Impact of Achieving Your Goal (expressed in dollars) | The Dealer Principal aims to sell 200 cars per month, generating a gross profit of $700,00. Currently, we're averaging 81 cars sold and $96,000 in gross profit. In order to reach the $700,000 target , we need to focus on aligning our staffing , management, and inventory strategies. With the right adjusments, the financial results will follow. |  |  |

What specific actions or steps will you take to accomplish your goal?  What will you do differently or improve? For each, be sure to include necessary resources, who is accountable, the measurable result, and dates.

| Specific action/step | Necessary resource(s) | Accountable person(s) | Expected result | Start, End, & CHeckpoint Dates |
| --- | --- | --- | --- | --- |
| Leadership Training with managers. | NADA, Larry Hawkins School of Automotive sales. | Stefan Stevenson | Better Leadership and knowledge skills for management. | 01/01/25 03/31/25 check point 02/15/25 |
| Set multiple interviews before and better onboarding class to train. | NADA, Larry Hawkins School fo Automotive Sales | Stefan Stevenson | High-level sales team | 01/01/25 03/31/25 check point 02/15/25 |
| Inventory tools for sales manager | Click or tap here to enter text. | Stefan Stevenson | Better inventory | 01/01/25 03/31/25 check point 02/15/25 |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |

As you work toward your goal, it’s important to have interim check points with specific, measurable objectives so your team can hold themselves accountable. If everyone knows the goal and objectives, you don’t have to spend your valuable time micromanaging.

Once you’ve accomplished your goal, added or adjusted policies, procedures, and behaviors, now what? How will you ensure you and your staff do not fall back into the previous habits that produced poor results? Be specific.

Every Monday morning manager meeting with Dealer Principal, CFO, and Control. To discuss issues and growth .

Describe any planning or implementation meetings conducted as part of development of your plan.

Having outside agents coming and train staff.

| Sponsor Signature: |  |
| --- | --- |