| Name | Tony Peckham | Class # | N444 |
| --- | --- | --- | --- |
| Dealership | Korf Motors | Date | 11/13/2024 |

| Current Situation or Challenge to be Addressed: | Lead response time amd conversion rate. We currently have a very slow lead response time and conversion rate. Currently well below the goal set by ownership and industry. We need to address the lead respose time along with conversion. I feel both are related in the automotive world and relate to profitability directly. |  |  |
| --- | --- | --- | --- |
| Current Performance Level (include specific measure): | 2 hours and 41 minutes is our current lead response tine and a 12.3% conversion of leads to appointments. |  |  |
| Goal (what do you want to achieve?) | Goal is to have a 3 minute response time and a 62% conversion rate. Our conversion rate is the leads turned into appoinments and/or remote sales quotes. In order to measure correctly a remote sales quote of OTD or payment will quauify as a appoinment. Will be marked in CRM accordingly. |  |  |
| Goal Performance Level (include specific measure) | Will measure progress in the CRM. We will measure response time om a daily/weekly and month to date. Measurements taken nightly and posted on group me. |  |  |
| Goal Start Date: | 11/13/2024 | Goal End Date: | 1/2/2025 |
| First Check-in Date: | 11/20/2024 | Performance Objective: | To see response response time daily below 30min and average and MTD below one houe See coversion rate up to 14% Doing a one week measure to check engagement. |
| Second Check-in Date: | 12/4/2024 | Performance Objective: | To see response time daily below 10 minutes and last MTD as well as MTD. To see conversion rate increase up to 25% This will 3 week check up on prigress and shows areas for improvement. |
| Third Check-in Date: | 12/18/2024 | Performance Objective: | To see daily response time at 5 minutes or less and MTD to be 7 minutes average. Target for conversion is set at 45%. This is a big jump but feel processes should be in place and results should be drastic. This will our 5 week check up and again let us know how we can improve and what we can train on. |
| Fourth Check-in Date: | 1/2/2025 | Performance Objective: | Our morning meeting. Our goal is to see last month at end of month have a last week average of 3 min response time. A last we average of the same. To show last months average response time to be less that 5 min and a lead conversion of 60% or greater |
| How does your goal align with the dealers’ vision? | This aligns will dealer plan as Paul Tew set down and help with this plan of action. His quote "Speed Kills! Slow responses and poor quality response kill your lead!" |  |  |
| What are the potential benefits of achieving your goal? | The benefit will be increased sales volume which will result in more profit. Faster turn of inventory will result in less holding cost. More sales will result in sales consultants having better pay checks. Selling more will result in more trades increasing sales and service sales.In nut shell more profitability. Will also result in better CSI and online reviews. More surveys will will help CSI as with that one bad survey won't kill your score if you have a few more than usual. May also result in more repeat and referral business. More google reviews. |  |  |
| What are the potential consequences if you don’t achieve your goal? | Well at current levels the leads that buy some where else will continue.We will continue same performance. If your not growing and moving then we are dying. Worst case I not able to become a managing partner, the store sells due to lack of performance. Best case we maintain and justify not adjust for our performance. Which trust me in this group…NOT going to happen! |  |  |
| Why is the goal important to you? | As store becomes more priofitable and I show the fitness to be a effective GM I'll be reward oppournity to buy in to this store and others as group grows. If for some reason would need to find other employement would have proven track record. Needless to say more sales, more gross equals bigger pay checks. |  |  |
| Potential Obstacles | Biggest obstacles. First is buy in. You have to have your team see your vision and get the buy in. WIIFM! What's in it for me? Need to make sure they know with this work will result in rewards.Making sure we are working with them as managers to help them grow and learn. Making sure we celbrate all victories. |  |  |
| Potential Solutions | Celebrate all victories ans success. Do it daily. Place a board with red and gree days. Green days we will celebrate when we beat our goal. We we miss will be a red day and we will not say a word. Rewards. Sales consutant with most confirmed appointmets will receive a $100.00 CASH bonus. If we reach our goal on January 2nd. We have planned a dinner for emplyees and spouses for January the 18th and NOT McDonalds. |  |  |
| BOTTOM LINE! Financial Impact of Achieving Your Goal (expressed in dollars) | This is a good questions. We feel whem reaching our goals we have another 10 car deals closed. At a average gross of $1,300.00 this will result in $13,000.00. $789..95 dealer handling $7,899.95. At at $2,400.00 pack used and figuring 7 to be used $16,800.00. With other 3 sales being new at $1,800.00 per unit pack $5,400.00. Looks to be $43,099.95 additional gross with out adding a employee or advertising expense. Of course you will have commisions of 14% average This would be around $5,900.00 but the profit off of the trades in will easily off set this. |  |  |

What specific actions or steps will you take to accomplish your goal?  What will you do differently or improve? For each, be sure to include necessary resources, who is accountable, the measurable result, and dates.

| Specific action/step | Necessary resource(s) | Accountable person(s) | Expected result | Start, End, & CHeckpoint Dates |
| --- | --- | --- | --- | --- |
| Appointment board on showroom | CRM linked to menu board | Rick McAllister | Sales floor to see todays appoinments and focus on engagement. | 11/13/24 was installed and linked to CRM. I turn on every morning amd all managers are to make sure on. Unbstalkled on Dec/18/2024 |
| Group me text | To utilize in group chat making sure everyone is receiving text. | Tony Peckham | By doing a nightly check out we will see our pace and know id we are ion target or lost focus. | 11/13/2024 and I set a alarm in my phone at 7:00 making sure to send out this text. I have no end date set and in 67 days will be a habit. Will be easier to do than not, |
| Training | Classes with our CRM Privider VinSolutions | Jeremey Kind | With continued training we will know how to utilized the tool for better follow up and results recording. | 11/26/2023 is our first group login and training session for 30 minutes. This again we have no end date set and we feel should be on going. |
| AI | Finding a AI provider that helps us keep leads engaged. We have started a trial offer with Podium. | Paul Tew and Tony Peckham | After hours and high traffic times keeping the lead engaged while we are not able to responded | Started search in October but now have focus. We have a call with Podium Dec,3rd to go over results. We will discuss tool and Paul may have another one he wished to try. We plan to hgave AI provider by Dec/30/2024 |
| Lead Board | CRM Reports on Lead Response time and Conversion | Rick McAllister | To visually see in meeting room the times and results everyday. Thik will be like sales board. Silent Accountability. | Startr date 11/18/2024 Daily we will do this with not set end date |
| Store vs Store | Group Me | Paul Tew | The 5 stores will compete for the best response time and conversion percentage. Each store is putting in $200.00 for a pot od $1,000.00 that will go in to bonuses how seen fit. | Starts Dec/1/2024 with and end date of Dec/31/2024. Thios will be interesting, One employee said the store with less leads has a better chance of winning. But our largest voume store has done the best past 90 days. |
| Continued imput form employees | Open conversation and ideas | Tyler Schuelke-Tony Peckham-Rick McAllister & Paul Tew | To get ideas how to becoome better and to implenment some of these ideas to get a better process. | 11/16/24 Saturday morning meeting quickly go over our plan and ask staff to write down ideas amd we will go over in Wednesday morning meeting. I think this type of coimmunication will not have a end date as well. |

As you work toward your goal, it’s important to have interim check points with specific, measurable objectives so your team can hold themselves accountable. If everyone knows the goal and objectives, you don’t have to spend your valuable time micromanaging.

Once you’ve accomplished your goal, added or adjusted policies, procedures, and behaviors, now what? How will you ensure you and your staff do not fall back into the previous habits that produced poor results? Be specific.

Document Policies and Processes Write Them Down: Have a clear, written policy or procedure document that everyone can reference. Update Regularly: Periodically review and adjust as necessary to reflect the current environment or lessons learned. 2. Set Key Performance Indicators (KPIs) Monitor Results: Track metrics that reflect success (e.g., lead response times, sales numbers, customer satisfaction scores). Review Regularly: Schedule time to analyze KPIs weekly or monthly to ensure you're meeting targets. Create Accountability Systems Assign Roles: Ensure Sales manager Rick Mcallister is responsible for maintaining and auditing compliance with policies. Peer Reviews: Use peer accountability, such as team reviews, to keep everyone aligned. Regular Check-Ins Daily/Weekly Meetings: Use brief, focused huddles to reinforce direction and discuss progress. Monthly Deep Dives: Have more detailed sessions to review policy effectiveness and discuss adjustments. Foster a Culture of Consistency Lead by Example: Model the behaviors and adherence to policies you expect from others. Celebrate Wins: Recognize and reward teams and individuals who excel in following the updated systems. Dashboards: Implement visual tools to provide real-time tracking and feedback. Response ti,e posted on menu board live. Team Input: Regularly ask your team for feedback on what’s working and what’s not. Customer Perspective: Gather insights from customer satisfaction surveys to identify any slippage. Continuous Training Reinforce Policies: Include policy reviews and best practices in regular training sessions. Upskill Staff: Provide development opportunities to adapt to new challenges. Plan for Accountability Post-Change Audits: Schedule periodic reviews or audits of adherence to policies and performance metrics. Refresher Initiatives: Periodically revisit and reinforce the reasons behind the changes to prevent backsliding. Address Resistance Quickly Tackle Challenges Head-On: Address any behaviors or attitudes that risk undermining progress. Adapt Policies: Be flexible enough to refine processes when feedback or data indicates it’s needed. Evaluate Long-Term Progress Quarterly Goals: Break larger objectives into smaller quarterly goals. Strategic Reviews: Every 6–12 months, evaluate the system’s overall impact and recalibrate as needed.

Describe any planning or implementation meetings conducted as part of development of your plan.

Key Participants Rick McAllister-Tyler Schuelke-Paul Tew-Tony Peckham Identify Challenges: Review current lead follow-up weaknesses (e.g., response times, conversion rates, incomplete tasks). Draft of the new lead follow-up policy. Assigned roles and responsibilities for implementation.

| Sponsor Signature: |  |
| --- | --- |