| Name | Evelyn Nugent Kopf | Class # | N477 |
| --- | --- | --- | --- |
| Dealership | Towne Ford | Date | 10/28/2024 |

| Current Situation or Challenge to be Addressed: | Used Car Department has been in the red for over a year. |  |  |
| --- | --- | --- | --- |
| Current Performance Level (include specific measure): | Every month the department looses an average of 43K |  |  |
| Goal (what do you want to achieve?) | Stop the bleeding. We need to turn this department from a negative profit center to a positive profit center. |  |  |
| Goal Performance Level (include specific measure) | The used car department needs to break eveb in 3 months and start to turn a profit in 6 months |  |  |
| Goal Start Date: | On Board Used Car Manager | Goal End Date: | 10/30/2024 |
| First Check-in Date: | 11/1/2024 | Performance Objective: | Used Car Manager fully on board. Training completed, All accounts set up and working. |
| Second Check-in Date: | 11/30/2024 | Performance Objective: | Lower the 55% of Old and Dead Inventory dollars to 10% |
| Third Check-in Date: | 12/31/2024 | Performance Objective: | All Used Car inventory should be < 60 days old |
| Fourth Check-in Date: | 1/31/2025 | Performance Objective: | Used Car Department breaking even per Jan Financial Statement |
| How does your goal align with the dealers’ vision? | Breaking even and eventually turning a proft in the department is very much aligned with the dealerships goals and vision. |  |  |
| What are the potential benefits of achieving your goal? | The used car department is the only department at the dealerhsip not turning in a profit. Breaking even/turning a proft would have substancial benefits for the dealership. |  |  |
| What are the potential consequences if you don’t achieve your goal? | Not acheivent the goal is not an option. This department needs to stop being a drain for the company. |  |  |
| Why is the goal important to you? | Aside from the financial implications (my compensation is a percentage of the Dealership's net proft), the goal is important for the rebuilding of the sales department. |  |  |
| Potential Obstacles | Roadblocks with the offloading of dead inventory, new used car manager not working out or fitting in our culture, market slow down due to recesion in tech industry. |  |  |
| Potential Solutions | Work agressively with the management of inventory, stay close to the development of used car manager and address any issues quick, pay close attention to developments in the tech sector and adapt our acquisition plan quick. |  |  |
| BOTTOM LINE! Financial Impact of Achieving Your Goal (expressed in dollars) | An extra $43,000 a month (500K+ a year) in net profit to the dealership, if we break even. Turning an average profit of 20K a month in this department will provide ~750K annually to the dealership's bottom line. |  |  |

What specific actions or steps will you take to accomplish your goal?  What will you do differently or improve? For each, be sure to include necessary resources, who is accountable, the measurable result, and dates.

| Specific action/step | Necessary resource(s) | Accountable person(s) | Expected result | Start, End, & CHeckpoint Dates |
| --- | --- | --- | --- | --- |
| On Board new Used Car Manager | HR, Director of Sales, IT, Sales Mgrs | Director of Sales | Used Car Manager will be empowered with necessary tools and knowledge to positively impact the used car inventory and sales of used cars | 10/15/24-11/1/2024 Checkpoint dates are daily |
| Review used car inventory to offload Old and Dead Invetory | Used Car Manager, Director of Sales | Used Car Manager | Offload Old and Dead inventory to bring frozen capital down. Old and Dead Inventory should be no more than 10% of total inventory | 10/15/2024 - 11/15/2024 Check point dates are daily, |
| Aquire new inventory | Used Car Manager, Sales Managers, Sales Associate, Direcltor of Sales | Used Car Manager | Fresh Inventory or units < 30 days old should account ofor 60% | By 11/15/2024 Check points daily |
| Improve "time to market" of used cars | Service Manager, Used Car Manager, Advisors, Used Car techs, detailer, Business Office | Service Manager and Used Car Manager | Used Cars should be on the frontline ready for sale <4 business days from aquisition | 11/1/2024 Ongoing. |
| Improve marketing of used car inventory by focusing funds based on ROI | Used Car Manager, Director of Sales, Sales Mgrs, Sales Associates | Director of Sales | Increase the leads for used cars by 50% | 12/01/2024 |
| Implement spiff for sales associates - spiff on old and dead units | Director of Sales, Used Car Manager, Sales Associates, Sales Mgrs, HR (for documenting spiff), Business Office | Director of Sales | Sell off Old and Dead inventory so that this inventory is < 10% of inventory | 10/15/2024-11/30/2024 Checkpoints: daily progress. Goal must be met by 11/30/2024 |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |

As you work toward your goal, it’s important to have interim check points with specific, measurable objectives so your team can hold themselves accountable. If everyone knows the goal and objectives, you don’t have to spend your valuable time micromanaging.

Once you’ve accomplished your goal, added or adjusted policies, procedures, and behaviors, now what? How will you ensure you and your staff do not fall back into the previous habits that produced poor results? Be specific.

We will discuss durig our weekly Department head meetings. Sales, Invenotry, heat Sheet will be reviewed daily - I have a dashboard that provides me updates on all KPIs daily and on demand updates throughout the day.

Describe any planning or implementation meetings conducted as part of development of your plan.

Weekly Meetings with Sales Leadership

| Sponsor Signature: |  |
| --- | --- |