| Name | Lyndsey Krenzen Manning | Class # | 448 |
| --- | --- | --- | --- |
| Dealership | Krenzen Auto | Date | 11/19/2024 |

| Current Situation or Challenge to be Addressed: | Price to Market |  |  |
| --- | --- | --- | --- |
| Current Performance Level (include specific measure): | 33% of our used intentory is priced over market value |  |  |
| Goal (what do you want to achieve?) | Reduce the percentage of used vehicles over 105% price to market from 33% to 15% within the next six months. |  |  |
| Goal Performance Level (include specific measure) | Have 75%-85% used inventory priced to market |  |  |
| Goal Start Date: | 12/1/2024 | Goal End Date: | 5/31/2025 |
| First Check-in Date: | 1/1/2025 | Performance Objective: | Conduct inventory audit and competitor analysis. |
| Second Check-in Date: | 2/3/2025 | Performance Objective: | Implement trained pricing strategy (vAuto) |
| Third Check-in Date: | 4/7/2025 | Performance Objective: | Review progress, adjust strategies if necessary, and conduct follow-up training. |
| Fourth Check-in Date: | 5/1/2025 | Performance Objective: | Evaluate if the goal of reducing the percentage over 105% price to market to 15% has been achieved. |
| How does your goal align with the dealers’ vision? | This aligns with Krenzen Auto's goal of being simple, straightforward, and stress-free by implementing a clear and transparent pricing structure that fosters customer trust. By utilizing data-driven pricing strategies and training staff, customers experience a more effortless purchasing process with less negotiation and confusion. Ultimately, this approach enhances customer satisfaction and promotes lasting relationships, while also supporting the dealership's financial objectives. |  |  |
| What are the potential benefits of achieving your goal? | Achieving a simple and transparent vehicle pricing goal can lead to increased customer satisfaction and loyalty, as well as a reduced sales cycle time. It enhances the dealership's reputation, differentiating it from competitors and attracting new customers. Additionally, effective pricing strategies can improve profitability by maximizing sales while maintaining competitive prices. |  |  |
| What are the potential consequences if you don’t achieve your goal? | Not achieving simple and transparent vehicle pricing can lead to decreased customer satisfaction, loss of trust, longer sales cycles, a negative dealership reputation, and reduced profitability. These factors can ultimately discourage potential customers and harm the overall effectiveness of the dealership. |  |  |
| Why is the goal important to you? | Achieving simple and transparent vehicle pricing is incredibly important to me for a few key reasons. First, it helps build trust and loyalty with my customers, making them more likely to come back and recommend us to others. I want our dealership to be known for fairness and integrity, which I believe enhances our reputation in the community. |  |  |
| Potential Obstacles | Staff members might be resistant to change, particularly if they are accustomed to traditional sales strategies that involve negotiating prices. Implementing systems or tools to clearly communicate pricing can be a challenge, especially if current technology is outdated or insufficient. Some customers may not fully grasp value propositions behind pricing, leading to misunderstandings or dissatisfaction. |  |  |
| Potential Solutions | Hold team meetings and trainings to discuss benefits and address concerns. Share positive stories from satisfied customers to build confidence. |  |  |
| BOTTOM LINE! Financial Impact of Achieving Your Goal (expressed in dollars) | $592,000 Front End $318,000 Back End/Additional $910,000 Estimated GROI Current: 135% Guide: 144% Impact of up to $1,000,000 a year. |  |  |

What specific actions or steps will you take to accomplish your goal?  What will you do differently or improve? For each, be sure to include necessary resources, who is accountable, the measurable result, and dates.

| Specific action/step | Necessary resource(s) | Accountable person(s) | Expected result | Start, End, & CHeckpoint Dates |
| --- | --- | --- | --- | --- |
| Analyze Current Pricing with vAuto | vAuto | Used Car Manager/ Inventory Manager | Pricing more accuate | 12/1/24. Check pricing weekly. On going |
| Training Sales & Inventory Teams | vAuto access & Rep | Sales Team Lead | Deeper understanding of pricing structure | Weekly |
| Monitor & Adjust Pricing regularly. | vAuto | Inventory Manager/ Used Car manager | No more "Set it and forget it" pricing | Weekly, on going |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |

As you work toward your goal, it’s important to have interim check points with specific, measurable objectives so your team can hold themselves accountable. If everyone knows the goal and objectives, you don’t have to spend your valuable time micromanaging.

Once you’ve accomplished your goal, added or adjusted policies, procedures, and behaviors, now what? How will you ensure you and your staff do not fall back into the previous habits that produced poor results? Be specific.

Continuous education and training, weekly meetings to discuss pricing and new ideas, performance reports to the dealer/ management staff.

Describe any planning or implementation meetings conducted as part of development of your plan.

Planning and implementation meeting with the sales managers on using vAuto.

| Sponsor Signature: |  |
| --- | --- |