| Name | Daniel Lehr | Class # | N451 |
| --- | --- | --- | --- |
| Dealership | Lehman Motors | Date | 12/26/2024 |

| Current Situation or Challenge to be Addressed: | Low turn impacting GROI in the pre-owned department |  |  |
| --- | --- | --- | --- |
| Current Performance Level (include specific measure): | Pre-owned turn rate of 5.3 |  |  |
| Goal (what do you want to achieve?) | Drastically improve turn and GROI |  |  |
| Goal Performance Level (include specific measure) | Aiming to get to benchmark turn of 12 |  |  |
| Goal Start Date: | 1/2/2025 | Goal End Date: | 7/1/2025 |
| First Check-in Date: | 1/31/2025 | Performance Objective: | Turn rate of 6.975 |
| Second Check-in Date: | 3/15/2025 | Performance Objective: | Turn rate of 8.65 |
| Third Check-in Date: | 5/17/2025 | Performance Objective: | Turn rate of 10.325 |
| Fourth Check-in Date: | 6/30/2025 | Performance Objective: | Turn rate of 12 |
| How does your goal align with the dealers’ vision? | Providing convenient transactions that value the customer's time and provide convenience |  |  |
| What are the potential benefits of achieving your goal? | Increased ROI along with a measurable improvement in total obsorbtion |  |  |
| What are the potential consequences if you don’t achieve your goal? | Aged units dragging down gross, but more importantly net. Freezing cash flow needed to improve perfomrnace |  |  |
| Why is the goal important to you? | My role is validated by my ability to run a profitible department that not only supports sales staff but also drives business to our fixed ops departments. |  |  |
| Potential Obstacles | Service department struggles, stress on fixed ops when customer ROs are robust, sourcing quick-turning units |  |  |
| Potential Solutions | Increasing service customer courtasy appraisels, reducing service workload and increasing trade vehicles. |  |  |
| BOTTOM LINE! Financial Impact of Achieving Your Goal (expressed in dollars) | $488,961 total gross increases year over year. A 147% improvent over current performance with NADA benchmark turn. |  |  |

What specific actions or steps will you take to accomplish your goal?  What will you do differently or improve? For each, be sure to include necessary resources, who is accountable, the measurable result, and dates.

| Specific action/step | Necessary resource(s) | Accountable person(s) | Expected result | Start, End, & CHeckpoint Dates |
| --- | --- | --- | --- | --- |
| Lower list prices to market (Currently at 103%) | V-auto/profit time | Pre-Owned Manager | Increased lead activity on fresh units | 1/2 and ongoing process |
| Streamline reconditioning process | Dedicated service schedule/iRecon | Service Manager Pre-Owned Manager | Quicker time to lot merchanidsing | 1/2. Checking every month mid-month |
| Wholesal fewer off-brand trades | V-auto/profite time | Pre-Owned Manager NC Manager | Increased gross keeping the best offbrand units | 1/2. With wholesale exit strategy for units not turning within 14 days |
| Turn invenory quicker out of loaner fleet. No exit plan for loaner use currently. | Loaner log/iRecon | Pre-Owned Manager NC Manager | Troubled units ready to turn on the lot | 1/2 pulling vehicles based on age in fleet.weekly checkpoint |
| Incresae aquisiiton channels | Adding ACV auction account as source for vehicles | Pre-Owned Manager | Larger selection of quicker turning units | 2/1, ongoing to add additional channels |
| Increase digital ad spend for pre-owned inventory | Team Velocity | Pre-Owned Manager Website providor Marketing Coordinator | Increase in VDPs and lead activity | 3/1 checkpoint monthly |
| Add video elements to F&I and lead response | Camera/Phone integration. CRM tools | Sales Staff Marketing Coordinator | Increase in lead response and closing F&I product | 3/1 checkpoint monthly. Annual review of F&I content |

As you work toward your goal, it’s important to have interim check points with specific, measurable objectives so your team can hold themselves accountable. If everyone knows the goal and objectives, you don’t have to spend your valuable time micromanaging.

Once you’ve accomplished your goal, added or adjusted policies, procedures, and behaviors, now what? How will you ensure you and your staff do not fall back into the previous habits that produced poor results? Be specific.

One of the best ways to ensure not going backwards is showing Sales Staff where we have been and how we got to the levels of improvement laid out in our plans. Personally, the NADA Academy is great at shining a light on benchmark performance and showing what is possible to make varialbe operations a strong arm of the dealership body.

Describe any planning or implementation meetings conducted as part of development of your plan.

Meeting with all 3 departments will help produce an aligned goal. Meetings will be conducted on a monthly basis to ensure things are headed in the right direction.

| Sponsor Signature: |  |
| --- | --- |