STRENGTHS

- Service staffs’ ability to learn and be coached on the job as they go

- Age, extremely young service staff learning from the ground up.

- Lots of incoming business, both new and old customers coming to a relatively new store. Only open 5 years but lots of return business.

- All new technicians and training, most of our techs have been with us less than a year and have all been trained up to level 2 Chrysler Techs

- The used car dept is huge at this store and is constantly selling and trading for vehicles providing a massive influx of internal tickets. The GM allows for more work to be done on most UVI’s

- CSI scores are generally pretty good for this location

Weaknesses

- Service advisors are rude and not well trained

- The service dept is outdated and dirty and does not gel well with the flow of the dealership

- There is not a lot of visibility to the service dept, and they are struggling to reach customers with marketing

- The service manager is new to the business and the store and the area. Learning to lead and submit warranty is a huge problem

- Opening and closing tickets correctly in a timely manner

- Slow to finish tickets

- Not good at aftermarket installation

Opportunities

- New store with new employees

- Youth in the service dept with the advisors and the technicians

- Tons of customers in the market and not enough shops

- Tons of used vehicles on the lot and coming in for service

Threats

- Turnover is our number one threat at this store, we cannot afford to lose a technician or a trained service employee. The pool to hire from is too small

- Parts and shipping to this small delta town slows down work in progress and sometimes makes things more difficult to close customers

- Our service depts youth is one of its greatest strengths but also a major threat when they do not know how to handle customers or problems arise.

- Too much work causes long delays and hold times. This causes decreased customer satisfaction and over bad surveys.

Objectives

- All service employees will be graded on CSI scores

- Improve customer satisfaction and work turnout

- Create a better working environment

- Improve productivity and sales in the shop

Strategies

- Training! We will train all service employees

- Shop meetings every morning! Quick and easy!

- Tracking every day at the end of the day to measure progress

- Work with sales dept to grow UVI tickets

- Work with Sales and GM to pick up more advertisement and value

- Facelift the service dept, new paint and new interior

Tactics

- Service manager must hold shop meetings every morning with advisors and technicians (parts manager should attend)

- Meeting every afternoon with advisors and GM to go over tracking on the day

- New pay Plan geared towards CSI scores and GROSS. Must hit each stair step to receive bonuses.

- Hire shop wash guy to clean and pick up around the shop after renovations

- Training session once a quarter mandatory for service advisors and manager

- Tech training mandatory to stay at Chrysler level 2 certified

Action Plan

Go over CSI score and Surveys daily		Service Manager			Oct 1

Start Training Classes 				Service Advisor			Oct 1

Track Technician Classes 				GM / Manger				Oct 1

Daily RO meeting					Advisors and Manger			Oct 5

Dail Service and Parts meeting			Service Manager 			Oct 10

Daily advisor meeting				GM / Advisors 			Oct 10

Remodel Service area				GM				      	Oct 15

Track tech hours and productivity 			Service Manager			Oct 30

Implement Pay plan with CSI bonus		GM 					Nov 10

Hire new clean up guy				Service Manager			Nov 10

End of month tracking meeting 			GM / Service Manger 		Nov 29

Synopsis

We have a great opportunity to create a lasting experience at this store with the youth and inexperience that comes with a young store and employees. There is a huge market for used car shoppers and the sales dept has exploded over the last 3 years. That is giving the shop the ability to work on any make and model and the equipment to do so the opportunity to boom. We need to stay focused on training and implementing the right work environment for our employees and our customers as this shop begins to grow. The better we get early on at the little things the more we will pick up later as we get better and faster at getting vehicles in and out of the shop. We can only control the things we have in front of us and that is how we treat the customers and how pull vehicles in and out of work.

If we can schedule correctly and treat the customers well this shop that grew double this year could potentially continue to double next year on this path. A few slight cosmetic upgrades and additional tech could lead to major productivity improvements.

This store should be a very profitable and well-run machine moving forward.